Jerry
M1 Statement for Software

References

References are external documents (papers, files, articles, and photocopies) which are mentioned to give further information about topics in the document. Remember to write the accurate path for the reference file.

Enclosures

Enclosures are external documents (papers, files, articles, and photocopies) which are an essential part of the document itself, but which cannot be put into the word format.

Revision Information

| Created: | Revision | Name | Comments |
| --- | --- | --- | --- |
| 24.02.2006 | 0.1 | Majbritt Christensen | Initial revision in PVCS |
| Modified |  |  |  |

Contents

1	Introduction	2

2	Results and open issues M1	2

3	Conclusion	4

# Introduction

# Results and open issues M1

|  | Completed on: Initials and Date |
| --- | --- |
| - Binding statement for all defined SW features (including initial (P)ICS, PIXIT etc. required for System Test planning of agreed conformity assessments and certifications) | OK with constraints. Some requirements are still open, which might endanger further milestone. Refer to Jerry SW Requirement Clarification. |
| - Product specific component projects have reached C1 ……………………. | NA. Feature driven and Agile process. |
| - Memory Requirements fixed | OK. Reuse Aries. |
| - Testability of the features by S2 in the field guaranteed | NA. No S2 SW milestone. |
| - Feasibility of implementation and approval ensured | OK. Refer to Feasibility studies. |
| - Product specific user interface specification available | OK. VF ODM product with VF Simply UI. |
| - Software Supplier Management: Review of contracts, ready for signature (must be ensured that contracts can be signed after M1) | NA. SISL is handled as internal team. |
| - Negotiations by Procurement performed | NA. SISL is handled as internal team. |
| - Contract checked by Legal Department | NA. SISL is handled as internal team. |
| - Contract approved by Global Line Manager | NA. SISL is handled as internal team. |
| - Contract approved by Head of SW development | NA. SISL is handled as internal team. |
| - Resources provided by the department up to M3 | OK with constraints. -Effort for bugfix not yet covered. -all clarified requirements introduce additional efforts. Therefore additional resources needed in both SISL and Beijing needed. |
| - Product specific Architecture Document available | OK Reuse Aries. But ASP issue is open. |
| - Software Quality Assurance Plan (SQAP) completed | OK with constraints. Return rate is open. |
| - Software Project Management Plan (SPMP) completed | OK. |
| - Product Integration Plan available and reviewed | OK |
| - Integration Matrix | OK |
| - Planning of Integration Phases for defined IPs (+ detailed phase planning for IP 1); number and content of all IP’s defined | OK Feature driven and Agile process. Refer to IM plan. |
| - Test Plan WBIT (White Box Integration) available | OK with constraints. Feature driven test plan available. Not for WBIT. |
| - Test Specification WBIT (White Box Integration) for IP 1 available (latest before WBIT of IP 1) | OK with constraints. Feature driven test plan available. Not for WBIT. |
| - Integration Scenario for each Integration Phase | OK |
| - Reviews completed without blocking points | OK with constraints. No direct connection between SISL and PEK. |
| - Consistence with component schedules given | NA. Feature driven and Agile process. |
| - Core Integration Team nominated (appointed specialists form CA, L1, PS and SP) | OK with constraints. -2 CIT members in BenQ are required, but only one candidate available. The other one is open. -PS support not yet finalized -No SP changes |
| - Configuration Management Plan available | OK. Refer to SCMP. |
| - Project Database created | OK |
| - Detailed Primavera project plan up to M3/S4 is available, showing dedicated resources by name and on department level for external consultants | OK |
| - Update Risk Management Plan | OK |
| - Requirements and responsibilities fixed for all software deliverables which need to be adapted or tested | OK |
| - Creating in Defect Tracking Tool (Clear Quest) a new Project for Defect Tracking. Registration Form issued including Project Responsibilities, Roles and Suppliers. Project in Clear Quest created | OK |
| - Scope and schedule for implementing of the SW (EMC, service SW logic, accessories) is available for the individual HW statuses and has been agreed with HW and Accessories (-> Layer 1 proposed to postpone this checkpoint from M0 to M1) | OK |
| - Format of release notes and delta description of all SW parts agreed with QM, PM and System Test | OK |
| - AT command list available | OK. Reuse Aries. |
| - SW boot concept for internal test and test at operator defined and agreed with at least System Test, Global Product Management | OK. Reuse Aries. |
| - Update concept defined and agreed with at least System Test, Service and production | OK with constraints. SWUOTA not committed. |
| - Trace concept defined | OK. Reuse Aries. |
| - SW Variants: Operator specific MMI, MMI languages, SIM-Lock, Initialization, applications | OK with constraints. VF ODM product. Language group not yet finalized due to memory consumption. |
| - SW customization feature list overview created | NA. VF ODM product. No SW variants. |
| - Key applications defined | NA. VF ODM product. No key application. |
| - PSQA plan built up and provided to PQA | Open. |

# Conclusion

Jerry SW M1 is OK with some constraints as stated above, which might endanger sprints milestone and further control milestones. Besides, all open requirements after M1, and new features/requirements should be handled as Change Request, i.e. delay control milestones consequently.