## change description
file name | description | date | name
Jerry tooling plan |  | 2006-02-17 | BF

## Jerry, uppercase option 2
Project Jerry
Quantities over lifecycle | 450k |  |  |  | tool making |  | TC | Tool-Changes
Peak | 65k/month |  |  |  | optimisation |  | TT | Tool transfer and set-up
Share Europe/China | 100% China |  |  |  | FOT (First parts out of tool) |  | TM | Trimming and measuring
Milestones |  |  |  |  | S0 28.02.2006 |  |  | M1 50% Data 21.03.2006 |  | 80% Data 04.04.2006 |  |  | S15 100% Data 25.04.2006 |  |  |  | S2 24.05.2006 |  |  |  |  | S25 27.06.06 | [5 empty] | S3 08.08.06
Pilotrun-Assembly Production | [31 empty] | Pilotrun
Modification Packages | [21 empty] | 1. Mod. Package 27.06.2006 | [5 empty] | 2. Mod. Package 08.08.06
Prototype Parts | [17 empty] | B1+ Devices | [6 empty] | B2 Devices
| Feb 06 |  |  |  | March 06 |  |  |  |  | April 06 |  |  |  | May 06 |  |  |  | June 06 |  |  |  |  | July 06 |  |  |  | Aug 06 |  |  |  |  | Sept 06 |  |  |  | Oct 06 |  |  |  | Nov 06 |  |  |  |  | Dec 06 |  |  |  | Jan 07
| 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5
Quantities for Prototype Shop | [11 empty] | 612 pcs.
Max. dispo plan for critical parts | [31 empty] | 0 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25 | 16.25
Uppercase
Tool overview
Pre prodcution tool 1 cav | [12 empty] | Tool making | Tool making | Tool making | Tool making/FOT |  | TM | TM |  | TC | TC | TC | SOT | TM | TM | TC | Tool trimming/TOT | Tool trimming/TOT | TOT/cpk | 5 | 10 | 20 | 20 | 20
Tool 1, 2 cav | [21 empty] | Tool making |  |  |  | FOT | TC | TC/FOT | TM | TM | TM | TT | cpk | 5 | 15 | 25 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
Painting
Yield | [29 empty] | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85%
net Capacity (Basis: Moulded parts) | [29 empty] | 0 | 4.25 | 8.5 | 17 | 21.25 | 29.75 | 21.25 | 34 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5
Printing
Yield | [29 empty] | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
net Capacity (Basis: Moulded parts) | [29 empty] | 0 | 4.0375 | 8.075 | 16.15 | 20.1875 | 28.2625 | 20.1875 | 32.3 | 40.375 | 40.375 | 40.375 | 40.375 | 40.375 | 40.375 | 40.375 | 40.375 | 40.375 | 40.375 | 40.375 | 40.375 | 40.375 | 40.375 | 40.375 | 40.375
IMD window
Tool overview
Pre prodcution tool 1 cav | [11 empty] | Tool making | Tool making | Tool making | Tool making | Tool making/FOT |  | TM | TM |  | TC | TC | TC | SOT | TM | TM | TC | Tool trimming/TOT | Tool trimming/TOT | TOT/cpk | 5 | 10 | 20 | 20 | 20
Tool 1, 2 cav | [20 empty] | Tool making |  |  |  |  | FOT | TC | TC/FOT | TM | TM | TM | TT | cpk | 5 | 15 | 25 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
Moulding
Yield | [29 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
net Capacity (Basis: Moulded parts) | [29 empty] | 0 | 5 | 10 | 20 | 25 | 35 | 25 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
Speaker cover
Tool overview
Pre prodcution tool 1 cav | [12 empty] | Tool making | Tool making | Tool making | Tool making/FOT |  | TM | TM |  | TC | TC | TC | SOT | TM | TM | TC | Tool trimming/TOT | Tool trimming/TOT | TOT/cpk | 5 | 10 | 20 | 20 | 20
Tool 1, 4 cav | [21 empty] | Tool making |  |  |  | FOT | TC | TC/FOT | TM | TM | TM | TT | cpk | 5 | 15 | 25 | 40 | 50 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
Moulding
Yield | [29 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
net Capacity (Basis: Moulded parts) | [29 empty] | 0 | 5 | 10 | 20 | 25 | 35 | 25 | 40 | 50 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
assembly min | [29 empty] | 0 | 4.0375 | 8.075 | 16.15 | 20.1875 | 28.2625 | 20.1875 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
Yield | [29 empty] | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
net Capacity (Basis: Plated parts) | [29 empty] | 0 | 3.8356 | 7.6712 | 15.3425 | 19.1781 | 26.8494 | 19.1781 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5
Mounting frame
Tool overview
Pre prodcution tool 1 cav | [12 empty] | Tool making | Tool making | Tool making | Tool making/FOT |  | TM | TM |  | TC | TC | TC | SOT | TM | TM | TC | Tool trimming/TOT | Tool trimming/TOT | TOT/cpk | 5 | 10 | 20 | 20 | 20
Tool 1, 2 cav | [21 empty] | Tool making |  |  |  | FOT | TC | TC/FOT | TM | TM | TM | TT | cpk | 5 | 15 | 25 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
Moulding
Yield | [29 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
net Capacity (Basis: Moulded parts) | [29 empty] | 0 | 5 | 10 | 20 | 25 | 35 | 25 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
Sidebutton1 1k
Tool overview
Pre prodcution tool 1cav | [12 empty] | Tool making | Tool making | Tool making | Tool making/FOT |  | TM | TM |  | TC | TC | TC | SOT | TM | TM | TC | Tool trimming/TOT | Tool trimming/TOT | TOT/cpk | 5 | 10 | 20 | 20 | 20
Tool 1, 4 cav | [21 empty] | Tool making |  |  |  | FOT | TC | TC/FOT | TM | TM | TM | TT | cpk | 5 | 15 | 25 | 40 | 50 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
Chroming
Yield | [29 empty] | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
net Capacity (Basis: Moulded parts) | [29 empty] | 0 | 4.75 | 9.5 | 19 | 23.75 | 33.25 | 23.75 | 38 | 47.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5
Sidebutton2 1k
Tool overview
Pre prodcution tool 1cav | [12 empty] | Tool making | Tool making | Tool making | Tool making/FOT |  | TM | TM |  | TC | TC | TC | SOT | TM | TM | TC | Tool trimming/TOT | Tool trimming/TOT | TOT/cpk | 5 | 10 | 20 | 20 | 20
Tool 1, 4 cav | [21 empty] | Tool making |  |  |  | FOT | TC | TC/FOT | TM | TM | TM | TT | cpk | 5 | 15 | 25 | 40 | 50 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
Chroming
Yield | [29 empty] | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
net Capacity (Basis: Moulded parts) | [29 empty] | 0 | 4.75 | 9.5 | 19 | 23.75 | 33.25 | 23.75 | 38 | 47.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5
Keypadlock (switch)
Tool overview
Pre prodcution tool 1cav | [12 empty] | Tool making | Tool making | Tool making | Tool making/FOT |  | TM | TM |  | TC | TC | TC | SOT | TM | TM | TC | Tool trimming/TOT | Tool trimming/TOT | TOT/cpk | 5 | 10 | 20 | 20 | 20
Tool 1, 4 cav | [21 empty] | Tool making |  |  |  | FOT | TC | TC/FOT | TM | TM | TM | TT | cpk | 5 | 15 | 25 | 40 | 50 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
Chroming
Yield | [29 empty] | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
net Capacity (Basis: Moulded parts) | [29 empty] | 0 | 4.75 | 9.5 | 19 | 23.75 | 33.25 | 23.75 | 38 | 47.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5
assembly min | [29 empty] | 0 | 4.75 | 9.5 | 19 | 23.75 | 33.25 | 23.75 | 38 | 47.5 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
Yield | [29 empty] | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
net Capacity (Basis: Plated parts) | [29 empty] | 0 | 4.5125 | 9.025 | 18.05 | 22.5625 | 31.5875 | 22.5625 | 36.1 | 45.125 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5
Batterycover
Tool overview
Pre prodcution tool 1 cav | [12 empty] | Tool making | Tool making | Tool making | Tool making/FOT |  | TM | TM |  | TC | TC | TC | SOT | TM | TM | TC | Tool trimming/TOT | Tool trimming/TOT | TOT/cpk | 5 | 10 | 20 | 20 | 20
Tool 1, 2 cav | [21 empty] | Tool making |  |  |  | FOT | TC | TC/FOT | TM | TM | TM | TT | cpk | 5 | 15 | 25 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
Moulding
Yield | [29 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
net Capacity (Basis: Moulded parts) | [29 empty] | 0 | 5 | 10 | 20 | 25 | 35 | 25 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
Printing
Yield | [29 empty] | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
net Capacity (Basis: Moulded parts) | [29 empty] | 0 | 4.75 | 9.5 | 19 | 23.75 | 33.25 | 23.75 | 38 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5
Yield | [29 empty] | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
net Capacity (Basis: Plated parts) | [29 empty] | 0 | 4.5125 | 9.025 | 18.05 | 22.5625 | 31.5875 | 22.5625 | 36.1 | 45.125 | 45.125 | 45.125 | 45.125 | 45.125 | 45.125 | 45.125 | 45.125 | 45.125 | 45.125 | 45.125 | 45.125 | 45.125 | 45.125 | 45.125 | 45.125