95 Obsidian
M1 Statement for Project Management

References

References are external documents (papers, files, articles, and photocopies) which are mentioned to give further information about topics in the document. Remember to write the accurate path for the reference file.

Enclosures

Enclosures are external documents (papers, files, articles, and photocopies) which are an essential part of the document itself, but which cannot be put into the word format.

Revision Information

| Created: | Revision | Name | Comments |
| --- | --- | --- | --- |
| 27.02.2006 | 0.1 | Tony Stokholm | Initial revision |
| Modified |  |  |  |
| 27.02.2006 | 0.2 |  | Updated with Obsidian information |
| 03.03.2006 | 0.3 |  | Updated |

Contents

1	Introduction	2

2	M1    Implementation Release	2

2.1	Project Management	3

3	Conclusion	5

# Introduction

This document is the basis for the M1 milestone declaration. Section 2 contains the M1 checklist according to the MEP 7.01 and section 3 gives a statement to the milestone.

# M1    Implementation Release

| ## Project Management | Completed on: Initials and Date |
| --- | --- |
| - Detailed Primavera project plan up to M3/S4 is available, showing dedicated resources by name and on department level for external consultants | Ok |
| - RMEA created; risk evaluation has to access low or high project risk regarding quality (including scrap risk, return rate), time to market, sales fit, and financials. In case of DS is not planned at the same date as M3/S4 risks of DS have to be evaluated explicitly. | RMEA on Quality made. Vinzenz: TTM, Sales fit, financials |
| - Approved, prioritized and finalized planning of quantity and delivery dates for samples other than Acquisition samples available | Ok |
| - Cost management meeting has been held | Ok |
| - Number of pre-series devices for field test defined | Ok |
| - Standard variants for start of series production are defined by PM and fixed in the product contract | Ok (RU Plan) |
| - Device, module and delivery lists created for standard variants according to first variant specification (SAP in status 35), A999 – Variant for calculation | Ok |
| - Features of accessories/device incl. Cables specified | Ok |
| - Strategic screens and icons have been ordered at design agencies | Vinzenz |
| - The REA Team declares M1 for the device and accessories | Vinzenz |
| - Ramp-up figures are updated (according to capability of the supply chain) | Missing RU Plan |
| - Project organization chart defined | Vinzenz / Tony |
| - Key-operator approvals (normally 3 Operators) defined, which are necessary to reach DS | Ok |
| - CR light procedure and organization is installed | Ok |
| - Limited Editions: roadmap for limited editions in relation to standard phone roadmap is available from PM LE (not applicable for corporate phones). | NA |
| - Limited Editions: planning of quantities is available (if possible on monthly basis) from PM LE. | NA |
| - CD: CD concept incl. Timeline available | NA |
| - Contracts with partners ready for signature | Vinzenz |
| - Definition of key operators for customer/vendor interoperability test (for all new technologies which require customer/vendor interoperability test) finalized and sent to System Test | Ok |
| - Total volume for PS/DS defined (volume which has to be produced between PS and M3/S4 in a limited series production) | Missing RU Plan |

| - The business case should include the additional risks and costs for PS/DS (like scrap risk, return rate, etc.) for the agreed pilot run volume | Vinzenz |  |
| --- | --- | --- |
| - Country / Operator specific Approval (Update) |  |  |
| - Approval feasibility has been clarified | Vinzenz / (Carsten) |  |
| - Approval requirements (technical parameters, etc.) | Vinzenz / (Carsten) |  |
| - Implementation plan for approvals (deadlines and responsibilities) | Vinzenz / (Carsten) |  |
| - Approvals required for DS are defined | Vinzenz / (Carsten) |  |
| - Local type approval and network approval requirements (required documentation, required hardware, time schedule) collected and matched with standard project plan | Vinzenz |  |
| - Definition of the key operators (ordered by priority) which should get support from System Test during operator approval finalized and sent to System Test | Vinzenz |  |
| - Number of SW variants for the key operators defined and sent to System Test | Vinzenz |  |
| - Definition which other operators (besides key operators, ordered by priority) and to which extent these operators are supported by System test during operator approval finalized and sent to System Test | Vinzenz |  |
| - Planned availability of SIM cards needed for the operator approval support by System Test | Ok |  |
| - Recycling | Ok |  |
| - Recycling concept is defined |  |  |
| - Create implementation plans for: |  |  |
| - Development |  |  |
| - Production |  |  |
| - Logistics / handling |  |  |
| - Deadline agreement for M4 for the predecessor product is available | Vinzenz |  |
| - Patents |  |  |
| - Patent/ license is clarified, own invention disclosures have been made, potential license fee estimated and integrated in Business Case | Ok |  |
| - New terms released by PM; check upon violation of registered brands/ trademarks started | Vinzenz |  |

| - Variant Management |  |
| --- | --- |
| - Disposition variants in SAP/Demand Planer available | Ok |
| - Variant strategy defined (minimum quantity, cost allocation) | Vinzenz |
| - Kick-off meeting with mechanical design and layout production data held | Ok |
| - Language groups are fixed | Ok |
| - Variant concept available | Vinzenz |
| - HW Variants: Variant concept available e.g. HW variants (keypads, charger, displays, logo positioning on casing and display, additional parts i.e. metal clip …) | Ok / Vinzenz |
| - SW Variants: Operator specific MMI, MMI languages, SIM-Lock, Initialization, applications | Ok/ Vinzenz |
| - Packaging adjustment (standard, customer specific…) | Ok / Vinzenz |
| - First draft of customization guide is available | Vinzenz |
| - User Guide: User guide concept incl. timeline available. User Guide languages are defined | Vinzenz |
| - Bundling possibilities | Vinzenz |
| - Target number of variants and target countries for PS/DS volume defined | Vinzenz |

# Conclusion