95 Obsidian
M1 Statement for Mechanics

References

References are external documents (papers, files, articles, and photocopies) which are mentioned to give further information about topics in the document. Remember to write the accurate path for the reference file.

Enclosures

Enclosures are external documents (papers, files, articles, and photocopies) which are an essential part of the document itself, but which cannot be put into the word format.

Revision Information

| Created: | Revision | Name | Comments |
| --- | --- | --- | --- |
| 01.12.2005 | 0.1 | Majbritt Christensen | Initial revision in PVCS |
| Modified |  |  |  |

Contents

1	Introduction	3

2	Results and open issues M1	3

3	Conclusion	5

# Introduction

The document contains the basis for the commitment for the M1 for the Obsidian product.

# Results and open issues M1

| - 50 % CAD data ready and provided to suppliers | Done |
| --- | --- |
| - Recycling concept is defined/updated | Pending |
| - Draft TTDs (Technical Terms of Delivery) in Revision Level 0, based on 50 % data for mechanical and electromechanical (product-specific) parts created and coordinated with suppliers and SCM (PT & QM2) as base for supplier’s feasibility study, TTD available on supplier side | Done |
| - Design-FMEA (Construction-FMEA) for mechanical and electromechanical parts has been performed, risk analysis/assessment is done | Done Sidekey. Front and rear case assembly. |
| - PSQA-Plan (development-internal test and qualification plan for mechanical components and system) defined and documented and provided to PQA | Ongoing, Internal review in CW 10, review with QM 13.03.06 |
| - Detailed Primavera project plan up to M3/S4 is available, showing dedicated resources by name and on department level for external consultants | done |
| - Kick-off meeting with PM and LPD held (Adjustment of documentation procedure and documentation responsibilities for variants) | N/A |

# Open points

## Time schedule

The B2 painted variant is not included in the detailed primavera plan jet.

The Nolato development plan is included here:

## Platform components.

The following platform components are not released on the M1 date. Blue text is comments from Petra Braun team leader for EL-Mec in KLF.

| CONNECTOR/BATTERY 3-POL/X85 FCI is just changing the production to the final destination in Malaysia and has to deliver the final quality documents. The part itself is ok and used at Polaris in Production. | A5B00075536067 | C39334-Z97-C467 | RAW | 20 |
| --- | --- | --- | --- | --- |
| CON B2B/20-POL/0,4MM/H1,0MM/SMD/MALE This is the male connector which has not been ordered yet by BenQ directly. But I think this one should be fully released, same as the female part. | A5B00075508425 | V39334-Z97-C457 | RAW | 20 |
| NANO-IO/JACK/PITCH=0,8MM/H=2,0MM/SMD/12P The Project milestone I4 is just declared. | A5B00075411792 | C39334-Z93-C364 | RAW | 20 |
| CONNECTOR CARDREADER TRANSFLASH HINGE Alps has delivered the latest Quality documents today. | A5B00075496653 | C39334-Z97-C448 | RAW | 20 |
| CONNECTOR COAX SOCKET SWITCHED SMD Hirose has to deliver some additional quality documents... | A5B00075530183 | C39334-Z97-C382 | RAW | 20 |

# Supplier set-up

The supplier set up will be as list below. Lumberg/Greenpoint will deliver the B1, B1+ and B2 quantities during development.  PVD and painted raw parts can not be mixed.

The painted variant will applied the same color and process as the Philippe project there for is no time left for process optimization. Nolao has only to deliver to a B2 painted test run in CW33.

# Ramp-up plans & Time schedule

- The final M1 ramp-up plan is included:

The MD development time schedule which is the basis for the detailed primavera planning is.

# MD performance description

The commitment for the MD is based on the following input to the performance description.

# MD Risk list

# Conclusion

Based to the above can the M1 be declared.