## Slide 1: S68 OPC Requested Status Report
Thomas Neumann
Technical Project Management
28-Feb-06
TPM : Thomas Neumann
TPM RD : Andreas Lang
TPM BO : Kristina Normann
TPM BA : Jan Strecker

## Slide 2: Schedule
Recent Achievements
DS: 23.02.06 (vs. 24.02.06 as of M1)
Ramp Up Quantity reduced to 60k until end of 03/06 (vs. 110k as of M1);
Current Number of S68 produced: 8.7k
Current First Pass Rate: 88% (<1% Side Keys)
Outlook:
S4: 31.05.06 (vs. 31.05.06 as of M1)

## Slide 3: Quality Gate Rating Polaris (S68) DS Status
CONTRACT
Time-to-market
DS declared on February 23, 2006 vs. M1 target of February 24, 2006
SCM
Allocation
Orders (78k) exceed current ramp-up quantity (60k vs. 110k at M1)
BTO (35k) is covered
BTS (43k): 25k are covered, 18k not covered
Material availability
Currently only one keypad supplier (DK UIL) released
Delivery reliability for Mechanical parts from Lumberg (Front Cover, Rear Cover and Battery Cover) not given
Production Technology
Manual 100%-control is in place due to breaking south catchers -> New parts arrive 27-Feb-06
Still ~ 80 % yield due to side key tactility
Cosmetically quality of CF
Receiver falling off at assembly
Mixed delivery CR (with/without rework)

## Slide 4: Quality Gate Rating Polaris (S68) DS Status
R&D
Mechanics
Fixation of Nano I/O connector still problematic
Tactility of side keys still critical . Tool modification done, but parts out of the modified tool not available before 28-Feb
Battery cover fixation still not sufficient, modified parts expected end of this week
High Failure rate of drop Tests; Strong deformations of front cover (accepted by PM) which lead to difficulties in pressing the keys (cosmetic and handling issue)
Static load resistance of LCD glass and display lens not high enough. Breakage with 120N possible.
Sweat resistance and release of Ni-Ions of you DK-UIL keypad still not as expected
System Test
All approvals and certificates are available
QM
Overall Product Quality
Current Return Rate estimation: 16% (SW+HW) at Delivery Start. RR over lifecycle 12.5%.

## Slide 5: Quality Gate Rating Polaris (S68) Measures, Responsibilities and Due Dates
Q-Gate Axis | Measure | State | Due Date | Owner
SCM | 100% manual Inspection | pending | 28-Feb-06 | Klaus Doerne
 | Install SD-QM employee at CCC | done | 20-Feb-06 | Ralf Zieminski
 | Increase number of shifts per week | open | 01-Mar-06 | Klaus Doerne
QM | Improve Front Cover | done | 27-Feb-06 | Klaus Kroesen
 | Improve Battery Cover | done | 24-Feb-06 | Klaus Kroesen
 | Improve Side Keys | done | 27-Feb-06 | Klaus Kroesen
 | Improve Injection Parameter of Display Lens | pending | 27-Feb-06 | Klaus Kroesen
 | Repeat Tests test to verify improvements | open | 03-Mar-06 | Stefan Bischof

## Slide 6: Required Management Support
The S68 DS Milestone has been declared:
S68 Project Team:
Milestone declaration (23-Feb-06)
Head of CM Phil Mulholland:
Accepts the milestone declaration (23-Feb-06)
Head of PHE Dr. Jochen Eickholt
Accepts the milestone declaration (28-Feb-06)

## Slide 7: Backup

## Slide 8: Financial Status

## Slide 9: S68 Budget (as of 31st January 06)
Comment :
Account: E981-0390
M0 declared 13.07.2005
(Originally planned 31.03.2005)
M1 declared 28.09.2005
M3 planned 31.05.2006 (originally 31.07.2006)
Efforts after M3: 0‘45 Mio
Platform:
04/05: 1/8 of X75 Platform
Decision of Sep 05: migration to Rel.1  no platform costs of X85 SG2 Rel.2 Platform
05/06: ¼ of X75 Platform
EGK-Factor: 85er Gen.
03/04: 1,3
04/05: 2,21
05/06: 2,04
Forecast includes:
530.000 € charging of samples
Actual includes:
+ 256.000 liabilities

## Slide 10: S68 BOM (as of S3)

## Slide 11
MTA

## Slide 12: Schedule
Today
PTR
Pilot Run
W49
W50
W51
W52
W01
W02
W03
W04
W05
W06
W07
W08
W09
W10
Ramp Up
B2.3 PR
ΔPTR
Hardware
Milestones
AS
S3HW
PS
DS (57k)
2k
3k
14k
16k
17k
18k
Software
PTR
Pilot Run
Ramp Up
B2.3 PR
ΔPTR
Hardware
1.7k
1k
5k
8k
Software
Milestones
AS
S3HW
PS
DS (5k)
M1/ S25 Schedule
Actual
B3

## Slide 13: Current problems Hardware Front Cover
“South Catchers” break off Front Cover -> During Clip On Battery Lid
-> During Free Fall
-> Qualification of this solution was done with B1+, Reference Dimension and Min. Force fixed within TTD
The Problem has been re-occurred with B3 again.
-> ChiChen does not ensure Process Stability tough specified within TTD
-> Reference Dimension was not communicated correctly from Lumberg (Integrated Supplier) towards ChiCheng
Solution:
The Tooling has been improved 2 times.
-> Parts with first improvements at factory since 16-Feb-06, but mixed with old parts (only 0.1% failure).
-> Parts with final improvements at factory since 27-Feb-06, clean delivery

## Slide 14: Current problems Hardware Front Cover
“Side Keys” clamping -> Bad Tactile Feeling of lower Side Keys
-> Qualification of this solution was done with B1+, based on Parts out of Prototype Tooling
The Problem has been occurred with B2.3
-> Lumberg has made a mistake with the mass Production Tooling (Parts too big)
-> Post galvanizing process not stable, thus galvanic aggregates at some areas
Solution:
The Side Key Tooling has been improved.
-> Improved Parts at factory since 27-Feb-06
The Rear Cover Tooling has been changed (in order to increase stability over mass production)
-> First Parts out of modified tool expected at factory 09-Mar-06

## Slide 15: Status Software
DS declared based upon SVN22
nCCPI: 740000
Return Rate: 8%
Following SWV have been released by QM:
SVN20 for E+ only
SVN21 for 2.5k max
SVN22 unlimited
SW- Operator Approval
Operator | Req. | AS | 1st Shipm. | Comments
TMO |  | 27.01.06 | 17.03.06 | Release expected with SVN26
Orange |  | 27.01.06 | 14.03.06 | Release expected with SVN25
VF |  | n/a | n/a | Not listed
O2 |  | 31.01.06 | 03.03.06 | According to O2 demand, all certificated have to be in place -> Release expected with SVN26
E-Plus |  | 16.01.06 | 24.02.06 | Limited Release with SVN20. Unlimited Release expected with SVN26

## Slide 16: Price/ Volume Evaluation
 | MBeta | M0 | M1 | M2 | S3 | %
Turn Over | € 294.092.600 | €132.750.150 | €117.216.000 | €105.462.000 | €99.792.000 | 195%
BOM | €64,80 | €62,58 | €58,04 | €58,90 | €61,85 | 11%
Quotation; K.Y. Lee, 17.01.06 BenQ Brand Launch
….
"More important is [average selling price] and [profit] margins," Mr. Lee said.

## Slide 17: Major Problems during Project Realization
Assembly of Front cover
-> Gluing of Mg Screw Bosses not stable over process
-> Several Redesigns and ad hoc measures performed
-> Impact upon Project Budget, BOM and Ramp Up Quantity
Battery Release Mechanism
-> Battery Release Mechanism not Fun to use
-> “South Catchers” break off
-> Several Redesigns and ad hoc measures performed
-> Impact upon Project Budget, BOM and Ramp Up Quantity and Quality
Availability/Yield of Front Cover
-> Several Redesigns necessary due to problems above
-> Tool Crashes shortly before Ramp Up
-> Impact upon Ramp Up Quantity and Quality
Keypad Quality
-> Double Click of Navi Ring
-> Several Redesigns and ad hoc measures performed
-> No Impact (2nd source not yet released)

## Slide 18: Major Problem Causes
Pre Development done within Product Development
-> No experiences with Metal Houses
-> No experiences with Metal Keypads
-> No experiences with Slim Designs
Selection of in proper Supplier
-> Selection was based on Metal Case only, assembly concept was not taken into account
-> Techn. Proposals (Screw Bosses/ South Catchers) have not been reviewed thoroughly
-> Communication was not perfect due to local and cultural distance
Integrated Supplier Concept
-> Interfaces and Responsibilities not well structured
-> Mismatch between specifications/ requirements given to Sub Suppliers
-> Very Long Lead Times/ Complicated Logistics
Migration Siemens -> BenQ
-> Lost Enthusiasm of some Project Team Members located in Ulm due to new site strategy
-> Permanent change of Team Members (Headcount Reduced to 60 at Ulm Site )