## Slide 1: Siemens COM MD Swift M0 Declaration (Delta Doc to M0 Document HW+Production)
Heike Evangelista, Munich, 01.07.2005

## Slide 2
Overview
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 3: A. Change History
Date:
29.04.2005
01.07.2005
08.07.2005
Version:
1.0
1.1
1.2
Responsible:
Heike Evangelista
Heike Evangelista
Heike Evangelista
Change:
M0 HW + Production Delta template created
Update all sections, include signatures
Update p.9. „added features

## Slide 4: B. Open Issues
Topic | Responsible | Until when
Improve Project timeline and DS back mid of March 2006 | SW Platform J. Kockmann/ B. Shen | CW29
Finalise variant concept (operator variants) | A. Hauenstein - APM | M1
Finalise Packaging and UM concept | H. Evangelista | CW30
Finalise AD Portfolio depending on result on BT Stereo CR | K. Fischer | CW30
Define final branding and final naming | K. Schmal | M1
Staff Rea team with GPM and PMM (starting 4 wks before M1) | A. Hauenstein | CW29/30
Revision of single source risks and evaluate measures if necessary | H. Evangelista/ A. Macura | CW30
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5
C. Swift-Project Folders & Documents
1 Introduction & Product Profile
1.1 Product Profile
1.2 Windows of opportunity
1.3 Enthusiasm model
1.4 Main differentiation within MP portfolio
2 Strategy & Positioning
2.1 Highlights
2.2 Target Group & Product Story
2.3 Key Product Arguments
2.4 Performance Profile
2.5 Competition
2.6 SWOT
2.7 Lifecycle Management
2.8 Limited Editions
2.9 Accessories
2.10 Applications
2.11 Sales Strategy
3 Specification
3.1 Design & Mechanics
3.2. Featuring
3.3 Platform Concept
3.4 User Interface
3.5 Customization
3.6 Variants
3.7 User Manual / Packaging
3.8 Production
3.9 Quality
3.10 Customer Care
3.11 Patents
4 Financials
4.1 Swift Business Case
4.2 Sensitivity Analysis
4.3 Opportunities
5 Timeline and Project Organisation
5.1 Target Project Schedule
5.2 Product Project Organisation
5.3 Ressources
5.4 Risk Assessment
5.5 M0 Signatures
Design Documents
Design Renderings and Mockups
Design Decision Matrix
Design Acceptance Test Results
Q-Gate M0
Q-Gate M0 HW+Production held on 08.04.05
Q-Gate M0 to be held on 06.07.05
Steckbrief at M0
Released on 26.06.05
HW architecture
Platform Overview and Site Strategy
M0 deliverables
M0 HW+Production documentation
M0 Delta documentation
M0 signatures
SW feature list
Detailed PD SW feature list
User Interface
UI principles: UI styleguide
UI concepts: basic description for new concepts
UI usability test results
Milestones & ressources
Milestones and ressources until M1 planned in Primavera
PSR M0 Declaration
PSR approval on M0 HW+Production on 04.05.05
PSR approval on M0 on 13.07.05 (tbc)
M0 Document
Project controlling
Accompanying documentation
All Swift related documentation can be found at: https://ims.icn.siemens.de/livelink/livelink/Open/331502833
PD internal documents
Team Declaration
M0 HW+Production on 15.04.05
M0 (complete) on 01.07.05
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6: 2.4 Performance Profile
Technology
Source: K. Schmal
Hardware
Weight
Dimensions
Standby Time / Talk Time
Display
Camera
tbd
90 x 46.3 x 16.3 mm
Up to 330 h / 300 min
262K colours, TFT, 2.0 inches, QVGA, transflective
Integrated 1.3-megapixel camera
Flash
Improved LED flash
Software
Messaging
Multimedia
Free Memory Capacity
Internet Access
Network Type
Data Transfer
Connectivity
MMS, extra-long SMS, ptt, IMPS, e-mail
MP3, AAC, AAC+(+), 3D Java engine
Up to 16 MB internal memory, MicroSD card slot
WAP 2.0
Tri-band 900 / 1800 / 1900
GPRS / EDGE Multislot Class 10
Bluetooth®
Battery
Li-Ion 570 mAh
Video recording / playback
 /  additionally streaming and progressive download

## Slide 7: 2.9 Accessories Launch: 03/06, Portfolio: all regions
Accessories
Fashion
& Carry
Energy
Office
Car
Solutions
Handsfree
Portable
Multi-
tainment
Compatible with 65 or 75 series*
Phone only
For bulk only
* Backwards compatible
Products compatible with 85 series
Case
Li-Ion Battery
570 mAh
EBA-140
1)
Remarks:
Standard case to be selected from existing AD portfolio
Stereo Headset and USB cable ready for bundling
New AD product, launch with POLARIS in 2/06
Car Kit EASY with universal phone fixation and GPS preparation, launch with FINCH in 1/06
launch with IBIS in 05/06
New AD product, launch with PLOVER in 2/06
Car Kit
Bluetooth®
HKW-710*
Car Kit
Bluetooth® Portable
HKW-700
Headset Bluetooth
HHB-700/710
Car Kit
Bluetooth® SIM
HKW-720*
Headset Stereo
HHS-150
3)
2)
6)
Headset Bluetooth®
Stereo HHB-750
Travel Charger EU/UK
ETC-100/110
Car Charger Plus
ECC-100
DeskTop Stand
EDS-100
Headset Purestyle
HHS-120
Headset Basic
HHS-100
Headset
HHS-110
Car Kit Portable
HKP-100
Data Cable USB
DCA-140
2)
Headset Bluetooth
BASIC
Headset Bluetooth
PREMIUM
3)
3)
Passive Holder
Universal
4)
Bluetooth *
Mobile Music Set
5)
Sync Station
DSC-100
Data Cable serial
DCA-100
Music Cable
6)
Car Kit
Bluetooth Portable
Low
3)
Compatibility only if CR for support of BT Stereo without Gimmick chip will be implemented
Headset Bluetooth
CLIP
3)
Source: K. Fischer
Notes: <number>
<footer>
<header>
<date/time>

## Slide 8: 2.11 Sales Strategy Business
Sales Strategy
Product | WE | EE | AMEA | LAM | CHN |  |  |  | 
2‘470k | 1.301k | 576k | 245k | 75k | 273k |  |  |  | 
Notes: <number>
<footer>
<header>
<date/time>

## Slide 9
Featuring
3.2 Featuring (1/3) List of Features - Software
Preconditions:
X75/X85 SW platform provides the feature set for all devices of X85 SGold2 products
  X75 SGold2 is basis feature set (Minos&Hydra) for X85 SGold2 generation
  X85 SGold2 adds additional features to the X75 SGold2 platform:
Main added SW features for Swift based on X75 SGold2 platform:
QVGA display resolution and permanent Status Line
Upscaling of videos to QVGA resolution
Multimedia features in SW w/o Gimmik Chip
Nano-I/O
MicroSD card support
Two speaker concept (incl. acoustic shock prevention)
Display power off in standby mode and support of Signal LED
OMA PoC (TBD)
H.264 Video Decoding (TBD)
Improved LED Flash
Direct calling line
Speaker independent Name and Digit Dialling (SIND/SIDD)
X75 SGold2 SW Feature list :https://ims.icn.siemens.de/livelink/livelink/Open/329897340
Swift „Steckbrief“: https://ims.icn.siemens.de/livelink/livelink/Open/332091627
Source: Hien
Notes: <number>
<footer>
<header>
<date/time>

## Slide 10
Featuring
3.2 Featuring (2/3) List of Features - Hardware
HW Features | 
Frequencies* | 900, 1800, 1900
Transmission Mode* | GPRS/EGPRS(EDGE) class 10
Primary Display | 240x320, 256k color, TFT, 2 inch
Secondary Display | none
Touch Screen | none
Camera | 1.3 Mpixl
Flash (light) | LED
WLAN | none
IrDA | none
Bluetooth | yes (TI-Solution)
Wireless Sensor Connectivity | none
Built-in Sensor | none
A-GPS | none
Audio Broadcast | AAC/AAC+/AAC++/MP3/AMR NB/MIDI/WAV
Multicolor LED (Keypad) | none
EL foil illumination | none
Battery | 570 mAh Sanyo battery pack
2nd Audio Jack | none
Side keys | 2+2
Hearing Aid Compatibility | no
* = SAR Target 0,8 W/kg 1gr. average
Source: Bachl
Notes: <number>
<footer>
<header>
<date/time>

## Slide 11
Featuring
3.2 Featuring (3/3) Check vs. Requirements – as of 29.06.05
Top Level Requirement List:
Showstopper* in Summer, if not implemented in Rel. 3:
Source: Evangelista
Description | Type
OMA DRM 2.0 (incl. Java) | General
SyncML 1.1.2 DM/DS (settings update; also for SWUOTA) | General
OMA PoC for S-Gold2 based 75 Gen products | General
H.264 decode - based on SW solution (tbd.) | General
Backward compatibility of Rel. 3 with Rel. 2 products (Swift, Ibis, Brambling, Polaris, Plover) | General
Vodafone UI application flows | Vodafone
backup&help (enhancement according to OGDR3.1) | Orange
Packet video progressive download (enhancement according to OGDR3.1 -- FastTrack) | Orange
Kodiak (poc) | Orange
DoJa2.5 lite | i-mode
Full i-Mode DRM | i-mode
* Swift will not be accepted in Global Operator portfolio! Estimated volume impact up to 700k!
Notes: <number>
<footer>
<header>
<date/time>

## Slide 12: 3.4 User Interface (1/8) UI Hardware
QVGA display
    new layout principles including a permanent status line
one color LED for service light indication
Keypad
    5-way navigation key
    send-/end key
    2 softkeys
    media player front key: easy access to music & videos
    Joker key = Direct calling key: easy access to one end user defined addressbook entry
    push-to-talk side key
    camera side key
    volume side key (+/-)
Camera
PaT
Volume
LED
Unser Interface
Source: Grudszus

## Slide 13
4 Financials
Financials
Removed for confidentiality reasons!
Contact Th. Teistler or A. Hauenstein
Notes: <number>
<footer>
<header>
<date/time>

## Slide 14
5.1 Project Schedule - Preliminary Milestones and Synchronization Points
Project Management
M0 13.04.2005 reached 01.07.2005 01.07.2005
S0 25.04.2005 reached 19.08.2005 19.08.2005
M1 26.08.2005 26.08.2005 26.08.2005
S15 22.07.2005 26.08.2005 26.08.2005
S2 30.09.2005 30.09.2005 30.09.2005
S25 16.12.2005 23.12.2005 27.01.2006
M2 17.02.2006 17.02.2006 17.03.2006
S3 03.03.2006 03.03.2006 31.03.2006
PS 17.04.2006 17.04.2006 tbd
DS 28.04.2006 28.04.2006 26.05.2006
S4 31.07.2006 31.07.2006 31.07.2006
M3 tbd tbd tbd
w/ SW Platf. Int‘l
All Milestones and Synchronization Points have to be reworked with Target DS mid of March by CW29!
Schedules of predevopment Projects will be incorporated in HW and SW platform declarations.
Contact: Michael Crutziger (HW), Ulrike Harke (SW), Michael Weigang (overall)
Chinese SW
HW+Production
Planning
Notes: <number>
<footer>
<header>
<date/time>

## Slide 15
5.2 Project Organization (2/3) PD Team
Technical Projectmanager (PL-T) |  |  |  |  |  | 
Kockmann, Jürgen | (Project Planning, Interface PBM, Mechanics, Production, Material, Procurement) |  |  |  |  | 
Markus Hohenleitner | (Interface 85er Platform, Hardware, Software, Systemtest) |  |  |  |  | 
R&D |  |  |  | Production / Material |  | Qualitiy Management
HW |  | MD |  | SD TLM MD LCM |  | QM HW
RF |  | MD Swift |  | Schroeter, Dirk |  | Kühling, Heiko
Ebbinghaus, Ralph |  | Berchtenbreiter, Andreas |  | Alexander Macura |  | 
 |  |  |  | PT1 SMD / Reflow |  | 
FM Radio |  |  |  | Lars Mittelstaedt |  | QM SW
Christensen, Stehen |  |  |  | Mike Hessel |  | Hohmann, Ulrich
 |  |  |  | PT2.1 FBG-Test |  | 
BB |  |  |  | Georg Rosskothen |  | 
Bachl, Christian |  |  |  | PT2.2 Device-Test |  | 
 |  | SW |  | Barth, Michael (Rohde05) |  | Procurement
Display |  | Hien, Thomas |  | PT3 Assembly&Packaging |  | Dunzel, Jörg
Hässel, Uwe |  | Peter Müller |  | Kolauch, Volker - Swift |  | 
Battery |  | Signal Processing |  |  |  | 
Liebenow, Cornelius |  | Ralf Zoll |  | PT4 Prototype Shop |  | 
Camera |  |  |  | Bonau Hans-Georg |  | 
Heid, Mario |  | ST |  |  |  | Service
 |  | ST 1 |  |  |  | Schroeder, Nadine
EA |  | Alkämper, Thomas |  | SD QM |  | 
Schreiber, Michael |  |  |  | Stiller, Dieter |  | 
 |  | ST 2 Swift |  |  |  | 
LPD |  | Kohl, Erik |  |  |  | Accessories
Bartenschlager, Siegfried |  |  |  |  |  | Knapmeyer, Jens
Project Management

## Slide 16
5.1 Project Organization (3/3) Realisation Team Jour Fixe Members
Project Management
Department | Name |  | Telephone number
Accessories | Fischer, Klaus | MD AD PM | +49 89 722 24680
APE | Dunzel, Jörg | SP D PE MD | +49 30 386 30223
Applications | Minderlein, Timo | MD PBM AS | +49 89 722 56327
BA | Teistler Thomas | MD PBM BA PG55 | +49 89 722 29036
BO PL (after M1) | Shen Bojing | MD PBM BO | +49 89 722 22561
CDO | Voigt, Rudolph | MD SM CDO | +49 89 722 23973
CTO (until M0, informed until M1) | Lucas, Carlos | MD CTO TS TM | +49 89 722 23933
GPM (after M1) | N.N. |  | 
LCM | Macura, Alexander | SD FK MM LCM | +49 2842 95 5456
PCM (vor M1) | Schmal, Katja | MD PBM PM M PCM | +49 89 722 26311
PL-T | Kockmann, J. | MD PD PGG | +49 89 722 27613
PL-T Co | Hohenleitner Markus | MD PD PGG | +49 89 722 47636
PM | Evangelista, Heike | MD PBM PG85 | +49 89 722 46636
PMM (ater M1) | N.N. |  | 
Portfolio Management (until M1) | Lara, Rodolfo | MD PBM PM | +49 89 722 29142
Quality | Kühling, Heiko | MD QM PL PGM | +49 89 722 46524
Service | Thiel Anja | MD CC SLI | +49 89 722 37017
SPM | Hauenstein, Alfred | MD PBM PG85 | +49 89 722 46059
UE (until M0, informed until M1) | Grudszus, Robert | MD SM UE | +49 89 722 40439
VM Swift | Dernbach Michael | MD PBM BO VM | +49 89 722 47459

## Slide 17: 5.3 Ressources at M0
PD ressources provided by the department from M0 to M1 (planning on work-package level available in Primavera showing dedicated resources by name). Resources are reserved up to M3 (rough plan in Primavera available).
Rea-Team from M0 to M1 staffed, apart from GPM and PMM (only needed 4 wks before M1).
Project Management

## Slide 18: 5.4 Risk Assessment (1/8) PD-team
Project Management

## Slide 19: 5.4 Risk Assessment (2/8) PD-team
Project Management

## Slide 20: 5.4 Risk Assessment (3/8) PD-team
Project Management

## Slide 21
5.4 Risk Assessment (4/8) REA Team
Project Management

## Slide 22
5.4 Risk Assessment (5/8) REA Team
Project Management

## Slide 23
5.4 Risk Assessment (6/8) REA Team
Project Management

## Slide 24
5.4 Risk Assessment (7/8) REA Team
Project Management

## Slide 25
5.4 Risk Assessment (8/8) REA Team
Project Management

## Slide 26: 5.5 M0 Signatures Swift
M0 Signatures