95 Obsidian
M0 Statement for Layout & Production Data

References

References are external documents (papers, files, articles, and photocopies) which are mentioned to give further information about topics in the document. Remember to write the accurate path for the reference file.

Enclosures

Enclosures are external documents (papers, files, articles, and photocopies) which are an essential part of the document itself, but which cannot be put into the word format.

Revision Information

| Created: | Revision | Name | Comments |
| --- | --- | --- | --- |
| 29.10.2005 | 0.1 | Majbritt Christensen | Initial revision in PVCS |
| Modified |  |  |  |
| 24.11.2005 | 0.2 | Randi Bak | Initial input |
| 24.11.2005 | 0.3 | Dorte Nielsen | Initial input |
| 25.11.2005 | 1.0 | Randi Bak | Released |

Contents

1	Introduction	1

2	Results and open issues M0	1

3	Conclusion	2

# Introduction

This document will give the basis for the signing or rejection of the M0 milestone with respect to Layout and Production Data group.

# Results and open issues M0

| - Part project leader (PPL) layout and construction has been designated by the department Line Manager | done |
| --- | --- |
| - Detailed Primavera project plan from M0 to M1 showing dedicated resources by name is available | done |
| - Rough Primavera project plan from M1 to M3/S4 showing dedicated resources on department level is available | done |
| - Platform is released for start of product integration i.e. platform master schematics are available | Done same as Polaris |
| - First Product circuits schematics extracted from master schematics | Done same as Polaris |
| - Missing component- and pad-geometry have to be listed and traced | Done RF-shield missing |
| - PCB outline, barred/shielded areas and height profiles are available (>90%) | done |
| - Parts list of the calculation variant (delivery unit) for DTC measures made available within SAP PLM in status 99 | Done Note 1 |
| - The product requirements as specified in the M0 document achievable with available technologies / know-how by the specified S3 HW deadline | done |
| - Product relevant pre-development/components development are defined. Time schedule and deliveries assigned to product development schedule (I3 milestone of the pre-development is reached and available for the product development | done |
| - PCB technology, layer stack up defined and reviewed with EA, RF and dHW (If platform layer stack up not suitable confirmation from PCB-FBT necessary, if platform layer stack can not be used a supplier kick off workshop has to be held) | Done same as Polaris |
| - In case of FPC: - FPC process worked in project planning (lead time, assembly concept, logistic concept…) - outline data from MD received - test concept aligned together with MD and ST - critical parameters fixed (schematics, outline, dynamic area, track width, maximum resistant on shielding…) - first parts list distributed to suppliers (word or excel format) and ordering of long lead time (> 4weeks) components initiated - potential FPC supplier selection aligned with head of strategic procurement - FPC suppliers informed about kick off workshop meeting date - B1 and B1+ device quantity for cycle tests aligned with MD, ST2 and project manager - Component approval request started Remark: at least the due date for receiving this information has to be agreed and fixed together with related departments | N/A |

Note1:

A5B00100204035  L36880-N3340-Q  OBSIDIAN/FIRSTCALC.LIST BEFORE M0 status 99

A5B00900204034  S30880-S3340-Q  TU/OBSIDIAN/FIRSTCALC.LIST BEFORE M0 status 99

# Conclusion

Based on the results above I see no outstanding issues for the Obsidian M0 declaration for Layout & Production Data