M0 Milestone - Product is defined

SCM QM Material/Process

Project: Ruby

Material:

PD Team Project Manager (SCM QM Pro): 	Jürgen Krell

Process:

SD Team Project Manager (SCM QM CI): 	Jan Wolff

The M0- SCM QM is; declared. declared with restrictions. not declared. #### Date of declaration: 17.02.06 SIGNATORIES SCM QM; SCM QM PRO; SCM QM CI. (Project Manager PD Team); (Project Manager SD Team). Date/signature; Date/Signature; Date/Signature.

Copy of Signed Declaration

Copies:

SCM TLM LCM1

PL T

Signatories

Checklist M0- SCM QM Material Milestone

| No. | Own Milestone Requirements | Status | Owner | Ref to Restriction No |
| --- | --- | --- | --- | --- |
| 8.4.1 | Detailed Primavera project plan from M0 to M1 showing dedicated resources by name is available |  | QM PRO |  |
| 8.4.1.1 | Rough Primavera project plan from M1 to M3/S4 showing dedicated resources on department level is available |  | QM PRO QM CI |  |
| 8.4.1.3 | Product related second solutions and second sources agreed with SP and R&D (CFI) |  | QM PRO |  |
| 8.4.1.4 | Parts list (min. Populated PCB) is available in SAP PLM |  | QM PRO |  |
| 8.4.17 | Alignment with SP has been done |  | QM PRO/ PE |  |
| 8.4.2.3 | Production process Quality Manager QM CI is assigned. |  | QM CI |  |
|  | SD QM project leader for PD and SD team has been named |  | QM PRO QM CI |  |
| No. | Pre-requisites from other Groups | Status | Owner | Ref to Restriction No |
| 8.4.3 | External assemblies have been defined |  | LCM3 |  |
| 8.4.8 | Ramp Up Plan available on weekly basis (including ramp up locations and configuration /rebooting scenario) |  | LCM1 |  |
| 8.4.4 | Life cycle volumes, peak volumes and sales split and regions available |  | LCM1 |  |
| 8.4.11 | Maximum monthly capacity has been defined (incl. needed upside flexibility) |  | LCM1 |  |
|  | Procurement Supplier Strategy has been fulfilled |  | SP |  |
|  | Suppliers for Second Solution have been identified |  | SP | no 2nd solution |

Time-Schedule

M0 : 22.02.06	S0 : 22.03.06	M1 : 10.05.06	S15 : 14.06.06	S2 : 23.08.06

S25 : 01.11.06	S3 : 20.12.06	PS : CW01/07	DS : 22.02.07	S4 : 11.04.07

Ramp Up Plan

Restrictions / Open Points

| No. | Problem | Actions | Owner | Target Date | Comments |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
| 6 |  |  |  |  |  |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |
| 9 |  |  |  |  |  |
| 10 |  |  |  |  |  |
| 11 |  |  |  |  |  |
| 12 |  |  |  |  |  |
| 13 |  |  |  |  |  |
| 14 |  |  |  |  |  |
| 15 |  |  |  |  |  |