## Projects fron A -> Z
TPM 2 weekly CW 02 10.01.06
Tops | Flops
Products
Condor
* New parts for optimisation of parting line available on 10th Jan. , test results and based on this the S4 Milestone expected on 19th Jan | * SVN 24 (R9 - last exclusive maintainance of ZIDB4) now targeting in cw05 (former cw03) - rootcause for Orange NL seems to be found (missing information from network), but solution for fix still under investigation - new info on 12th Jan
Diamond
* support needed to find clever strategy in terms of SG2 vs SG3 solution (Uge,TRu)
* support needed to find clever strategy in terms high resolution squer LCD (240x240) (Uge,Tru)
* increase MD resources to speed up stack up tasks (Malpha planned for 18th Jan) (KKr)
Hawk
Project has been canceled
Hydra
Changes for full support (during SCOUT/SWUOTA) for Spamsion included in SVN13. | Still unacceptable deviation in contrast for Pluto display. (S4HW issue)
(Info) There is NO known problems with Spansion (fieldtest results) | SVN16 did not complete the toolchain.
China approval given. Production to start end this week.
Jerry
TTM critical team members allocated Block diagram & 1st schematic available based on Goldfinch Primavera top-level planning started | Project must be transferred back to Beijing around May/June timeframe (Risk on TTM and quality) PMC planning not completed due to project shifting back and forward between Beijing and Aalborg
Minos
Obsidian
• A1 boards running successfully against Real network including Camera, Display, BT, etc. • Design workshop ended out in settlement of details and colors o Black high glossy spray painting (Hydra color): 30% o Metal finish appearance (PVD): 40% o Pearl / Silver high glossy spray painting: 30% (also fall back solution to PVD) With the painting, there is a well known process and material securing the schedule With the PVD (physical vapour deposition) coating, there is a new innovative process and a surface which can give the “Wow effect” requested | • S0 declarations missing from PE, MD, LCM3 due to missing supplier selection. Meeting by PE promised at 9th Jan. S0 declarations missing from ST-QM due to the introduction of PVD and hereunder supplier selection. Meaning: Expect all to be settled 9th Jan
Philippe
S15 declared on the 6th January (as scheduled) Delivery schedule for plastic parts confirmed to be on track by supplier Nolato | MMI modules for B1 series not from right assembly tool (manual assembly done). Quality risk MMC tray one week later than required. Discusssions ongoing with supplier Alps to improve.
Polaris
AS Basic declared (BRT Retail only) | SW: S3 Basic not yet settled -> S3 Polaris endangered
SW: AS SW cannot be updated in the field -> Tooling/ Mapping Problem
MD: Several Problems with B2.3 detected, Major Problem FC too small -> Battery Release Problem, Overlap of Bettery Cover -> S3HW endangered
Swan Apoxi
SW Iteration #4: Modified MPE board - PhoneTool->RS-232->Nano I/O / Philips QVGA display driver working :-) | SWAN design acceptance: perceived appearance MISSED the target group >> CPM decided to stop the current mechanical development and to evaluate adaptations of the current design WITHOUT changing the mechanical set up (MD S0 delay by 1-2 weeks) >> Final decision on further proceedings on 09.01.2006 >> postponed to 10.01. >> S0 will be delayed to min. 20.01.06 (depending on decision on 09.01.06)
Contract fix target dates "latest e12.05" for Aplix & Teleca not reached >> not clear if Teleca will join SW planning workshop o 11./12.01.
Swift
S25 declared by Mechanics and Hardware | SCM S25 postponed to 20.01.2006, some test to be done with B2 first shot phones (glueing of keypads, quality of Perlos pre-assembled parts, soldering process in KLF )
B2 PCB first shot started on 09.01.2006, start of phone assembly in CW03 | KHVatec will change painting company bewteen B2 rund and pilot run, this will probably result in use of new color -> new color matching to be done before pilot run
HW Program Manager
Topic 1
Topic 2
Topic 3
SW Program Manager
SG2 Release Minos / Hydra
Software Versions are available as planned. | Plan is not matching to market requirements, a lot of operators gave us already the last chance where we did not perform
SG2 Release Swift
no delay due to performance issues | no chance for recovery in case of resouce conflicts between Minos/Hydra until S25.
gap between available features and executed test cases.
Gemstone Apoxi Platform
good working results at PSE Vienna | effort to bring whole project team up and running under estimated.
For line break within a cell pls. press 'Alt' + 'Enter'