## Projects fron Z -> A
TPM2 weekly CW 03
Tops | Flops
SW Program Manager
SG2 Release Minos / Hydra
SG2 Release Swift
S25 Test Coverage and pass rate are in the expected range (yesterday 71%, 65%) | Even from the overall maturity point of view S25 date can be confirmed the full integration of progressive download video and audio will be delayed by 1 week.
Gemstone Apoxi Platform
SW Project Organisation defined and ready for implementation. Swan will be as well served by Gemstone APOXI | So far no plan available how to confirm SWAN timeline based on APOXI. 1st planning workshop with suppliers give indication toward 2007.
If Swan is delayed it has massive impact on the SG3 based Gemstone SW Releases. It is recommended to use SG2 at least for Diamond.
HW Program Manager
Topic 1
Topic 2
Topic 3
Products
Swift
CPM decision: no 3 GPP Progressive Download needed for Swift, this follows Minos/Hydra decision CR raised by TPM to support FastTrack with DRM V1 | S25 SW endangered, currently delay of 5 working days
Swift B2 run started, major PCB soldering problems solved, phone assembly to start today | Pilot&Ramp Up color match at KHVatec to be done until end of CW4 (27.01.2006) - MD, CDO and SCM QM will be at KHVatec in Korea in CW04 to make tests and decision for Pilot and Ramp Up
Swan Apoxi
CPM decided for new design >> Partly reset of MD-M0 & stop of MD-S0 work items >> Availability of housing parts for Type Approval delayed >> Impact on SW development because B1 phones delayed S0/M1 delay by 2weeks / Delay of current DS date 10.10.06 approx. 2weeks (to be detailed in final M1 planning) NOTE: Designer(CPM) is "using SW to further optimze design" -> maybe further delay
M1 SW planning workshop on 11./12.01. with TTM SW team & ALL 3rd parties (PSE Vienna, IFX, Comneon, Aplix, Teleca) -> Analysis & presentation to be done by TTM SW team
PL-HW to be announced
Polaris
S3HW and Pilot postponed due to following problems: SideKey: Bad Tactility -> Modification necessary Display: Dust Introusion Problem, modification necessary, 5k parts already on stock Battery Cover, bad handling -> Modification necessary Front Cover, Tooling redesign necessary -> Tooling Change necessary Keypad: Double click of Navi keys
Philippe
First mold of the first part - the front cover - has been done
Obsidian
Minos
Jerry
Management decision on project reponsibility taken | BOM impact of change from EGR to SGL (and Aries display??)
Known and stable platform (SGL) selected
TCD feedback prepared for VF
Hydra
S4HW planned for 25/1-06 | No production in SSMC even if it was planned (missing license)
Contrast issue for PLUTO still not solved.
No timeline presented for S25, S3 and DS APAC
Hawk
Diamond
* agreement to 1,8Zoll QVGA and 1,3 Mega-Pixel Camera -> done | * Delta description SG2-SG3 still ongoing (Tru & Ugei')
* PMC re-check started (with optimized Milestone)
Condor
evaluation of 2nd RF (Hitachi) solution started
For line break within a cell pls. press 'Alt' + 'Enter'