## Projects fron A -> Z
TPM 2 weekly CW 04 (24.01.06)
Tops | Flops
Products
Condor (delete next time)
* optimisation of parting line: tests passed and decision to change all follow up tools done | * 2nd RF FEM solution - 3T Test: Condor passed, but Aries failed - analysis ongoing
* S4 / M3 Milestone done on 20th Jan (24th Jan Q-Gate and 03rd Febr. PBR)
* 3rd Color canceled because of low customer demands
Diamond
* Mα declared on 19.01.2006; first stack-up concept in place | * due to lack of MD resources (Catia training) from cw04 till cw05 only limited MD power
* PD-Team nominated; KickOff on 25.01.2006
* Decision taken to use SG2 Apoxi instead of SG3 Apoxi (17th Jan)
Hawk
PPL MD, CPM and consultant from Pochtler with designers in Taipei for ID clarification | The preferred ID out of user survey has a relatively complicated mechanical concept (time line / quality risk)
Chinese new year endangers design freeze schedule. Focus on fixing issues to secure construction progress.
Hydra
TMO approval for SVN 16 | Decrease of re-boot capacity because of larger FLASH
No timeline presented for S25, S3 and DS APAC by SW-PF... !!
Jerry
SW support resources for BEJ has been named | Not accepted by BEJ that the Device Layer resources are not present in BEJ immediately
HW and MD toplevel plan available in Primavera | SW planning still open (SW estimate from BEJ shows 340 MM effort)
Working decision from CPM to use Aries display | Still not known if surface on front part can be realised (Combination of mat and high gloss galvanised)
Minos
S3 for 09.02.2005 remains valid | Daimler Chrysler Carkit LineFit acoustical issue (female voice)
Flash problem analysis: Intel is not very supportive; Q-data not available from Intel
Obsidian
S0 declarations received from everyone but ST-QM – Discussion ongoing on Supplier selection strategy (ST-QM requires 2 separate suppliers on MD) | M1 declarations delayed from 20th Jan. till 3rd Feb. due to System breakdown in MD and introducing FM Radio in SW.
New MD-PL assigned to Obsidian. Prototype series schedule confirmed | Operator requirements still not clear. TB Settled before M1, alternatively on CR basis
50% data delivered to Lumberg 20th Jan. as scheduled | BOM is seriously above target – DTC workshop
Philippe
Promising results of first moldings (front cover, battery cover, lower case, upper case, keyset) | Orange has reduced volume from 400k to 150k (tbc). Volume recovery plan being established with other channels
Potential additional effort for Orange operator approval due to Orange S75 cancellation
Additional SW effort required to support SWUOTA with Sibley Memory flash (appr. 300hrs in Wroclaw)
Polaris
Swan Apoxi
Tapeout of A1 PCB done. S0 seems feasible in CW04 but there is still a risk. Most criti cal is MD ans SW HW-PL named (Jan Eicke Rüsen is HW-PL) | URGENT - Requested PL SW support still not available (Stuffing for essential SW topics like Primavera maintenance, Milestone tracking & document mgt., Feature list & CR handling not sufficient) / Kai Schmitz/Patric Houben are fully loaded with HW2SW alignment & Production SW, M1 SW planning, U2-project activities >> TPM is to much involvd into SW details
Swift
B2 first shot run started successfully, B2 main run on track -> build of TA devices will be done in time | QVGA "principles and concepts" do not fit to QVGA fonts (both provided by SM UE) -> if no short term solution found within this week new fonts are necessary -> implementation of new fonts will delay DS
Battery safety requirements documentation not complete for Sanyo battery, this is neccessary for Type Approval and Production start -> Sanyo is requested to provide final documentation within this week
Logo not fitting to CPM requirement. Changes from "Stanzen" to "Scheren" in progress. Samples on Friday, decision on Monday.
HW Program Manager
Topic 1
Topic 2
Topic 3
SW Program Manager
SG2 Release Minos / Hydra
NCCPI ramp down ongoing as planned | Contact to Orange still not stablished, necessary to fix use cases for video streaming
Polaris DS on track | Shopping list fullfillment only 60%, Retest Failure 15%
SG2 Release Swift
S25 on track beside Video streaming with Audio, nevertheless official date 10.2.2006 | Start of SMS on Exit Tests couppled to B2 run. Tests should start now.
Contact to Orange still not stablished, necessary to fix use cases for Fast Track
Gemstone Apoxi Platform
Project Organisation is ramping up. | CR to Budget has to be started : IFX, 3rd Parties and PSE by approx. 13 Mio more expensive than planned in PMC
Contract negotiations with IFX start to become a longrunner
Restrictive source code policy of the suppliers (IFX does not want to give Teleca inside view)
For line break within a cell pls. press 'Alt' + 'Enter'