## Projects fron Z -> A
TPM2 weekly (CW 05 31.01.05)
Tops | Flops
SW Program Manager
SG2 Release Minos / Hydra
nCCPI range of S3 captured with R6 release candidate on 1.2.2006 | Tool Chain broken during generation of SVN18. Two restarts were necessary to generate SVN19 causes a 5 day delay.
Polaris DS Bugs solved.
SG2 Release Swift
All S25 blocker solved. | Orange test contact still not established.
Only 280 product related bugs. | Unexpected risk for delivery date due to wrong font selection.
Gemstone Apoxi Platform
3 Scrum Masters certified for agile process role out. | Teleca acceptance criterias still not agreed - contract not signed.
Workload at PSE increased due to new requirements.
IFX negotiations in poor shape, especialy HW disappointed about warranty coverage.
HW Program Manager
Topic 1
Topic 2
Topic 3
Products
Swift
Pilot run color match at KHVatec successfull, color match of keypads in KW6 in Korea | Shortage of Intel Sibley Flashes during Ramp up and Q2 (360 K needed, 150K assured); STM second source qualification started: 1) samples ordered by R&D to qualify in Swift 2) CR raised to evaluate SW impacts
Adopted diamont cut logo shows good quality | Swift battery: no safety approval for breaker from Sanyo, problem is that breaker has too small plastic wall thickness, parallel approach now needed: 1) continue to get serurity documentation for current breaker 2) Sanyo to propose alternative solution and implementation plan
QVGA principles and concepts do not fit to QVGA fonts (both procided by QVGA) 1) Jumbo Mode Font had to be cancelled 2) evaluatins ongoing to adopt written text in dispaly 3) AS delay of 2 weeks (M1 plan is on 17.02.2006) 4) Impact on DS still under evaluation, depends on whole approval setup now
S25 delayed to 13.02.2006 (M1 plan is 06.02.2006) because of 1) delayed environmental tests -> B2 samples have been delivered too late by prototype shop 2) tbd: SW (depends on stability of todays delivery)
Swan Apoxi
A1 prototype run started on 31.01. | S0 not declared on 27.01.06 - MD=Material Spec & renderings missing->03.02. / SP=BOM not available->01.02. / SW will make a NON delaration bceause "feasbility of requirements can not finally confirmed"->20.02.
SW planning workshop did not reach a SW M1 planning / ALL GAP lists are reviewed but only 70% aligment, in some cases strong timeline mismatches for speific features found >> follow up sessions in CW05/06/07
Iteration 5 only reached 50% of planned feature step (iteration is NOT ACCEPTED for payment), iteration 6 will focus on M1 SW planning >> impact on project schedule to be analyzed in M1 SW planning
Polaris
South Catchers break off Front Cover due to process/ tooling problem at supplier -> Ramp Up endangered
No Feedback from regions yet with regards to SW Quality -> SW DS candidate due this week (SVN 19)
SVN 18 not successful
Philippe
SW: Philippe software from RIDB verified by smoketest,- no impact on Minos/Hydra PT: B1 (fast shot) started, phone assembly will take place in AAL MD: FOT done for all parts, beside MMC tray. Good color match between front cover and keyset | Tactility of edgekey need to be improved. FOT parts in general good, but corrections are required
Obsidian
Minos
Jerry
Aries SW has been transferred to AAL and DL work will start middle of this week | Latest ID was rejected by VF and revised design/stack-up/3D work on- going
CPM has decided to go for the Slim Lumberg instead of Nano-IO in order to supply a low cost desktop stand.
Hydra
S3 and DS Basic seems to be stable | No timeline presented for S25, S3 and DS APAC by SW-PF... !!
Over 60K products in VKL (Order stock problem)
Constantly non-performing from EPSON
SVN 18 rejected even before testing started... (crucial for Orange)
SW PF is blocking S4 for LCM (win swup problem). Down prioritized !!
Missing orders for CW 05
Hawk
Design freeze done to the extend that Pochtler can do construction until final designfreeze after Chineese New Year (M0/S0 15.02.06) | Timeline/quality risk due to complicated industrial design. Feasibility study on keypad by TopBound until 08.02.06. Results required for project scheduling.
Diamond
For line break within a cell pls. press 'Alt' + 'Enter'