## Projects fron A -> Z
TPM 2 weekly (CW 06 07.02.06)
Tops | Flops
Products
Diamond
Hawk
Negative feedback on keypad feasibility, designers in Taipei look into other design concept (conventional keypad mounting) Timeschedule under evaluation
Hydra
interim solution installed in production (100% screening of OP variants) | Production stopped due to problems with SVN 16 and 17 (init sequence)
Stable confirm of S3 and DS | Side-keys are torn off during packing of TMO UK variant.
Jerry
Industrial design WS with Perlos and designers in CW6 | Accessories for Slim Lumberg still not confirmed
Chromed front part has been dropped | Discussion about having the 3 simply keys above the display re-opened
Need to change RF to B6E in order to get enough room for sidekeys and Cadilac antenna in stack-up
MD timeline now also shows DS in end of September
Minos
"Flash Issue": INTEL feedback did not help; now 10 DOA (dead on arrival) + 9 latest production devices will be finally analyzed => results in S4 decision
"Vibra Sound": samples to be analyzed
Obsidian
• S0 declared • Supplier selection strategy settled between PD, MD & QM - Lumberg/Greenpoint for PVD; Nolato for painting | • M1 delayed to 13th Feb due to recalculation of RU in production on basis of new Sales figures & due to the late Supplier selection • HW PL/TPM-R&D leaving BenQ-Siemens
Philippe
SW: Everything implemented except for updates for new GCF version 3.21.0 MD: Phone assembly done with FOT's. In general the construction looks good. PBR agreed to continue project despite Orange cancelled the project | Tactility of edgekey need to be improved.
Polaris (1st contribution today!!!)
Hot Run (Pre-Pilot) started | Low yield at Factory, due side keys problem -> Hot Run suspended
South Catchers seem to be stable enough | Shortage in Front Covers due to massive Re-Work at Lumberg Site
Tool Change to improve South Catchers already done | S3 HW still open due to several mechanical problems (3 weeks delay!!)
Swan Apoxi
1st AUDIO CALL with A1 prototype boards (modem build SW, no display, cmaera, etc.) | S0 declared on 03.02.06 - declared by all departments except SW / SW NON delaration because "feasbility of requirements can not finally confirmed"->20.02.
Contractual issues with PSE Wien, IFX & 3rd parties regarding APOXI platform SW - OPEN QUESTION: "Who is allowed to deliver which SW to whom ?"
SW support from PSE Vienna: >> Agreed delivery schedule for prototype run SW was cancelled - reason "misunderstanding between PSE & BenQ" >> device diver & production test SW area not sufficient (e.g. no driving performance during A1 run, "never ending discussions on who must drive what")
Swift
S25-SW declared in committed M1 timeline | Material avaliability issues that may impact Pilot and Ramp Up 1) Intel Sibley -> 300k for Q2 announced by Intel, min. needed for Swift 360k 2) Battery -> two fold plan installed and ongoing 3) Epson Display -> Controllershortage expected but no "official" statement from Epson yet 4) Philips Display -> B2 Display cracks in drop tests, no problems seen in B1+ 5) Semco Camera Flex -> Yield of Everlight Flash LED only 40%
CR raisen by CPM to increase M2 life cycle volume by 140K phones compared to M1 volume -> how to handle 30% flex buffer? | Approval start shifted by 2 weeks from 17.02.2006 to 03.03.2006 due to QVGA font issue -> goal is to improve timeline by one week to 24.02.2005
HW Program Manager
Topic 1
Topic 2
Topic 3
Wireless Connectivity Program Manager
Bluetooth
Unplugfest in Vancouer last week(iop, security, robustness: >>Swift/Polaris: 21 Bugs found: not implemented puts, started but not removed implementations due to cancel. Minos/Haydra: New A2DP/AVRCP implementation partners: new test results. Kestrel: >>15 bugs, problems in Robustness testing. Chipset suplier: >>BB/FW two critical bugs found voice, lpm - sco edr.
DVB-H
Supplier selection process active: >>supplier questionary complete today
Wireless LAN
Category Management Convergency is looking for a "150 Euro" WLAN enabled dual mode handy: >> ODMs from Taiwan in discussion but IFX/Comneon based development not under considaration
SW Program Manager
SG2 Release Minos / Hydra
TMO UK: Wap initialisation problem still not reproducable
SG2 Release Swift
S25 declared on time
SW for Barcelona available (V109)
Gemstone Apoxi Platform
SW Support for SWAN A1 boards ontime | Dissatisfying cooperation with PSE on working level.
For line break within a cell pls. press 'Alt' + 'Enter'