## Projects fron Z -> A
TPM2 weekly (CW 07 14.02.06)
Tops | Flops
SW Program Manager
SG2 Release Minos / Hydra
TMO UK: Wap initialisation problem solved with SVN 22 | SW Platform Project Manager Mark Oliver Passauer withdrawn by Kestrel
S3 and DS Basic declared on 11.2.2006
SG2 Release Swift
Contact to Orange stablished, requirements clarified. Inhouse tests on the open server of Packed Video/Orange started, test session planned in CW8 | Additional risk for DS timeline by evaluation of STM memories (necessary because of not committed deliveries of Intel)
Gemstone Apoxi Platform
Process of realignment of priorities between product and platform started | PSE increased effort and extented timeline for phase 2 contract.
Wireless Connectivity Program Manager
Bluetooth
Unplugfest in Vancouer (iop, security, robustness: >>Swift/Polaris: 21 Bugs found: not implemented puts, started but not removed implementations due to feature cancel. Minos/Hydra: New A2DP/AVRCP implementation partners: new test results. Kestrel: >>15 bugs, problems in Robustness testing. Chipset suplier: >>In phone test platforms , qualification relevant BB/FW bugs found voice, lpm - sco edr found and reported to supplier.
MPE Contract next week: Overview missing, mismatches detected >> Latest contract appendix versions provided from IFX/Comneon or requested from CTM, R&D needs to be available for review.
DVB-H
Supplier selection process active: >> supplier questionary completed, technical requirement coverage with remaining suppliers(TI, Renesas, Philips) ongoing
Wireless LAN
Category Management Convergency is looking for a "150 Euro" WLAN enabled dual mode handy: >> ODMs from Taiwan in discussion but IFX/Comneon based development not under consideration
Dirk Lehmann is leaving us mid of March, new nomination to have time for handover asap required.
HW Program Manager
Topic 1
Topic 2
Topic 3
Products
Swift
Battery compromize on safety requirements found: start with PTC (B1 solution) and switch asap to breaker (B2 solution) | Side key metaldomes crack between 0-50000 cycles, requirement is 150000 cycles -> evaluation is ongoing but first risk releases are already done for Ramp Up
Drop tests results of B2 within QM requirements -> counter measures after B1+ have reduced amount of PMU ball cracks | STM qualification -> first risk releases need to be done starting on Friday, SW indications regarding performance issues will need 2-3 weeks
S25 BOM is 12% above M1 target -> S25 blocker
Sweat test (see Kestrel) is at the moment a not calculated return risk
Swan Apoxi
Indications from current ongoing SW M1 planning shows further delay on top of "design delay" & need for higher PSE budget
M1: further delay of 3-4 weeks expected due to “open SW M1 planning”
Design: 2 days after design freeze (MD-S0), design dept./CPM raised a CR  further One-2-one delay of DS
Polaris
S3 SW, ST und SW QM declared | S3 HW still pending due to: 1) Side Key Problem 2)South catchers
E+ limited release received based upon SVN20 | Production suspended until 2 problems above solved
FCC Early Grant received
Philippe
Philippe is back in the Orange Global port folio | Failures in drop test and static load test. Solutions found for all but one: BGA breaks in drop test. Root cause is being analysed using experience with similar previous problem in Minos.
Obsidian
M1 declared by AD, dHW, RF, LPD, EA, ST and MD | M1 declarations missing from SW due to missing resources for CarKit Linefit and from SCM+QM due to changed sales volume; SCM reported they need until 3rd Marts for re-calculations
B1 prototype Tape out made 13th Feb. Three weeks ahead of schedule | Mechanical schedule is critical. Resulting in DS 21th Sep.
Minos
Jerry (TPM at Beijing today)
WS in BEJ all week during CW7
2 different stack-up's with 2 different batteries (Hydra and Aries) developed with CDO Renderings should be available on 13.02.06, and mock-up available for VF meeting 15.02.06
Decisions by Roland Aubauer: - Turn Aries display 180 degrees without modifying glas and polarizors - The industrial design will only be painted or plastic, no chromed parts | Turning the display without modifications has minor impact on viewing angle. Effect can be seen by looking on an Aries or Minos up-side down.
Hydra
S3 and DS signed by ST and SW | DS basic blocked by LCM and QM due to SW issue in production. (on it's way now)
Production problem (setting issue) seems to be solved :-)
Tool chain for SVN 22 (incl bugfix) started
S3 signed by QM
Hawk
Workshop in Vienna in CW07 to reach design freeze. Participants CPM, MD PPL, Designer, Pochtler | The final feedback on the technical feasibility of the keypad concept was negative. Industrial Design is changed to use conventional keypad concept.
Evaluation of the time schedule shows that the DS on the 11.08 is not feasible. Opportunities for minimising delay are being investigated.
Diamond
* SW feature definition for Diamond critical, due to unclear process and responsibilities (CPM, CTO, PHE, Platform…., synchronisation of featurelist and GAP-lists…….) - Meeting with Geiger 15th Feb. * Detailing of mechanical concept cause more and more open issues which needs to be solved. Drive solutions - Betting, Krösen till M0 (cw10)
For line break within a cell pls. press 'Alt' + 'Enter'