## Projects fron A -> Z
TPM 2 weekly (CW 21.02.06)
Tops | Flops
Products
Diamond
keypad decision: metal domes | Unclear situation concerning Gemstone Apoxi in future! Which HW solution to be followed?
M0 (08.03.2006) endangered due to this fact!
Hawk
Contact established between Pochtler and supplier (Nolato). Face-to-face meeting planned for next week. | Still open issues on the industrial design
Time schedule scenarios based on Philippe schedule in place. Volume opportunities to be clarified. | Official supplier announcement still to be made
Hydra
Hydra declared S3/DS on the 17/2-06 | SVN23 cancelled for approval (buggy)
"Setting issue" now proven solved with SVN22
New color variants are rumpling in the background | Long lead-time for qualification of new color variants (16-20 weeks)
Jerry
Vodafone has accepted current ID with only minor modifications. VF has accepted painted front part instead of chromed. General status meeting with VF Wednesday 22.02.06 involving W. Klebsch | Tape out of A1 PCB delayed from 23.02 until 01.03
WS carried out in BEJ. Agreement of handover of HW and MD development end of June.
1st SW planning available based on Agile development involving 4 sprints
Minos
S3- / DS-basic declared; S3- / DS-'full' will be skipped
Obsidian
Philippe
B1 series running in production (stopped for 4 days due to test SW problems) | MD PL stops 01.01.06 (New experienced PL in place)
Devices for type approval selected
Tool corrections ongoing at Nolato for B2
Polaris
All Approvals available
DS SW declared and released (apart ASP retests) | Mechanical Problems still pending: 1 South Catchers; Side Keys
Production started again with 100% test (Failure due to Sourch Catchers decreasing app. 1%) | S3 blocked
Swan Apoxi
A1 WINGboard prototype run started | M1 SW plan (Microsoft Project) is not available - Main White Spots: Lower Layer & Production SW, variant handling, connectivity - but indications that DS NOT before begin 2007 confirmed
SW implementation progress in iteration 6: all MUS features implemented & positively tested / additionally 96-optional features implemented / back log from iteration 5 solved
Swift
Presentation of Swift in Barcelona was well received, special SW build worked as expected | Glueing of 12er Keypad didn't pass environmental tests, analysis is ongoing (finger prints have been found on glueing area), measures to be implemented (gloves during assembly, tests with differnt keypad assembly forces and times in KLF)
STM Flash Risk Release Process started to assure ramp up volume, qualification of STM ongoing | Epson announced ROM controller shortage on the market, share between Philips and Epson is planned to be 50/50, but Epson announced: 50% in March, 50% in April, 25% in May -> Philips to step in with 100% starting in June
HW Program Manager
Topic 1
Topic 2
Topic 3
Wireless Connectivity Program Manager
Bluetooth
DVB-H
Wireless LAN
SW Program Manager
SG2 Release Minos / Hydra
DS Milestone declared on SVN 22 | Kestrel requested futher key experts of native like Michael Roth
SG2 Release Swift
Font problem managed w/o timeline impact. | Slow progress on fast track, new timeline expected by tonight.
Gemstone Apoxi Platform
Timeout in order to redefine architecture and apporach. | Actions are centralized at head of R&D.
Object Mentor starts with agile process coaching this week. | Organization/Worksplit between CTO, R&D, TPM still not clear implemented.
No platform CM established.
For line break within a cell pls. press 'Alt' + 'Enter'