## Projects fron Z -> A
TPM2 weekly (CW 09 28.02.06)
Tops | Flops
SW Program Manager
SG2 Release Minos / Hydra
peel-off of hard-coat-layer of display lense; Nolato process-problem (solved since CW50/2005); 8D Report started;
SG2 Release Swift
Gemstone Apoxi Platform
Wireless Connectivity Program Manager
Bluetooth
DVB-H
Wireless LAN
HW Program Manager
Topic 1
Topic 2
Topic 3
Products
Swift
STM PCB built plan for cw9/cw10. Qualification of STM ongoing. | First results of still ongoing B2 environmental tests are under evaluation (Phillips display cracks, side key cracks, 12 keypad gluing failure, failed sweat test).
Carina display shortage still to be discussed in detail with Epson.
Pilot assembly is delayed by one week due to shortage of Hosiden speaker modules.
Swan native
SWAN NATIVE - team complete - 1st PD meeting held | No official statement on APOXI Time Out proceeding available
Polaris
DS declared 23-Feb. 06 | Again Tooling Problems at CCC -> polishing Tool has reduced yield (no under coverage yet)
New Battery Cover available | 21 shifts per week at factory possible, Material availability to be checked (1.3.06)
New SideKeys available
New Front Cover available
Philippe
B1 series performed successfully in prototype shop | - MD PL leaves BenQ 01.03.06. New experienced PL in place.
DS review: Opportunities for earlier delivery start. Launch strategy being planned together with CPM. Prerequisite: Successfull tool corrections for B2. Risk: Significant tool corrections ongoing for B2. Next DS review: 18.04.06
Obsidian
Mechanical design (100% CAD data) 23.02.06 as scheduled | Missing supplier commitment & RU-plan to be discussed
Primavera Bottom-up plan is finally aligned after 3 month work | M1 declaration missing from MD, SW, SQM, SCM
Plastic suppliers finally selected 13.02.06 | DS-Target changed to 08.09.06, i.e. one week delay compared to DS-Target at S0 due to late supplier selection (4 weeks)
Jerry
M0 signatures currently being collected. Only minor exceptions from some disciplines. | S0 pushed to 10.03.06 as we need to do production WS and system FMEA before S0
A1 PCB will be taped out before 09:00 on 01.03.06. A1 Build in KLF is planned on 08-09 of March, meaning that the late tape out date will be recovered.
After status meeting with VF in CW08, VF now feels a lot more confident with the project.
Hydra
S3 declared for APAC | DS not declared because of failed GCF test case by ST
SVN 24 will be blocked by SPM due to SMS failure
Request for new color (GOLD). Share resources with Obsidian. Even request for colored sidekeys and base keypad. ----- VERY critical due to high workload in mech department. -> Klaus K
Hawk
(Pre-)selection of Nolato as supplier for casing | Change requests from designer for the industrial design. Escalated to CPM. We continue construction according to current agreements.
Joint workshop with BenQ MD, Pochtler and Nolato in Vienna in CW09
Diamond
* M0 on 08.03. not reachable due to unclear SW situation (GEMSTONE Apoxi) => HAs, Uge
* project schedule can only be adapted after SW feedback => ABe, Uba
* Design requests decrease in thickness (17mm => 16mm) based on focus group feedback; concept evaluation causes incresed thickness (17mm => 18,2mm) -> concept evaluation ongoing
For line break within a cell pls. press 'Alt' + 'Enter'