## Projects fron A -> Z
TPM 2 weekly (CW 10 07.03.06)
Tops | Flops
Products
Diamond
* based on feedback of Design Acceptance test the mech. Concept still under evaluation to decrease thickness down to 16mm (support from K.Krösen available) - Concept decision expected for We. 08th March
* Currently no working antenna concept available. Most critical unknown effect in GSM900 band. Evaluation ongoing (Support J. Bauregger needed)
* Due to "SW time out" no Project planning possible (M0,M1, DS, S4). New planning conditions depends on SW input on 27th March (support Fässler needed)
* New target for "NON-M0-Declaration" on 17th March (M0 from all departements except SW, QM, TPM). Final M0 depends on SW input on 27th March (support Fässler needed)
Hawk
Successfull workshop with BenQ MD, Pochtler, Nolato and toolmaker in Vienna in CW09 | M0 and S0 declaration expected to be with exceptions/remarks. Not all check points can be closed in time but plans for doing it will be in place.
Supplier selection not finally confirmed. Nolato preselected. If changed, time schedule will not be feasible.
Hydra
Blocking issue for APAC(SMS time stamp) solved in SVN25. | SVN25 will not be released for Hydra due to new bugs. Now waiting for SVN26
Hans Bogensperger appointed as responsible driver for Hydra GOLD. | spec of golden variant shows changes of very critical parts.
Not possible to save cost on number of UG's in retail variants -> process describes otherwise.
Jerry
A1 PCB will be produced in KLF 9 & 10th of March | Parting line has to shifted 1 mm to ensure sidekey tactility
AAL DL/IM resources will fly to BEJ on schedule (13th and 25th of march) | Construction of softkeys still not agreed w. designers (3 vs. 6 keys)
Minos
Obsidian
Philippe
Project on track
Polaris
-> shortage of good quality front covers endanger planned March production quantity. 1. instable yield at alu frame supplier. 2. polluted display lenses lead to a high scrap with Ingoing Inspection at factory
Swan native
actuell Timeschedule is based on the dates: M0/SO 17.03.2006 ; M1 31.03.2006 and DS 10.11.2006; | -
additional features are FM Radio and Trans Flash Card Reader
Swift
AS Milestone reached on Friday 03.03.2006, Orange already started testing | Share of Philips display had to be increased from 50% to 70% over life cycle because of ROM Controller shortage for Epson displays -> negative impact on BOM since Philips display is more expensive than Epson display
S25 APAC Milestone to be declared this week
HW Program Manager
Topic 1
Topic 2
Topic 3
Wireless Connectivity Program Manager
Bluetooth
DVB-H
Wireless LAN
SW Program Manager
SG2 Release Minos / Hydra
SG2 Release Swift
Gemstone Apoxi Platform
For line break within a cell pls. press 'Alt' + 'Enter'

## Milestones_060307
Product projects
i | Ver. name | Status | Project | M alpha | M0 | S0 | M1 | S2 | S3 | S4 | M3 | DS | M4/M5 | Last update | Last user ID | PL
19 | V0.15 30.1.2006 Training ST FY 06/07 | Appr | Gemstone_Apoxi_Platform | 2006-01-19 | 2006-03-08 | 2006-04-14 | 2006-05-19 | 2006-09-15 | 2007-01-19 | 2007-05-18 | 2007-06-15 | 2007-02-20 | 2008-06-13 | 06. Feb. 2006 08:37 | 132 | Geiger
21 | M0.6 | Appr | Hawk |  | 2006-03-08 | 2006-03-08 | 2006-03-31 | 2006-06-12 | 2006-07-31 | 2006-09-15 | 2006-09-15 | 2006-08-11 | 2007-06-30 | 03. Mar. 2006 14:49 | 115 | Dalmose
22 | Plan_M1 Rel. 6_17.02.2006 DS declared | Appr | Hydra | 2003-12-03 | 2004-07-07 | 2004-12-02 | 2004-12-02 | 2005-03-02 | 2006-02-14 | 2006-05-26 | 2006-05-26 | 2006-02-17 | 2006-10-31 | 17. Feb. 2006 12:36 | 356 | Christiansen
23 | M0 2.1 | Appr | Jerry (VF simply) | 2006-01-17 | 2006-02-23 | 2006-02-28 | 2006-03-21 | 2006-06-20 | 2006-08-17 | 2006-10-05 | 2006-10-05 | 2006-09-22 |  | 28. Feb. 2006 11:57 | 717 | Song
29 | 2006_02_23 | Appr | Minos | 2003-10-03 | 2004-06-30 | 2004-12-02 | 2004-12-02 | 2005-03-02 | 2006-02-14 | 2006-05-26 | 2006-05-26 | 2006-02-17 | 2007-01-31 | 23. Feb. 2006 13:56 | 254 | Barner
30 | M1.01 | Appr | Obsidian | 2005-10-27 | 2005-12-02 | 2006-02-02 | 2006-03-08 | 2006-05-18 | 2006-08-18 | 2006-10-19 | 2006-10-19 | 2006-09-08 | 2006-11-23 | 03. Mar. 2006 15:33 | 919 | Stokholm
35 | M1.4 01_03_2006 ST_MO update | Appr | Philippe former Minos II | 2005-10-25 | 2005-11-18 | 2005-11-18 | 2005-12-14 | 2006-03-10 | 2006-04-26 | 2006-06-30 | 2006-06-30 | 2006-05-29 | 2007-01-31 | 03. Jan. 2006 14:40 | 115 | Dalmose
37 | Plan S25.1 _13.01.2006 | Appr | Polaris | 2005-02-15 | 2005-07-01 | 2005-09-23 | 2005-09-23 | 2005-10-21 | 2006-02-09 | 2006-05-31 | 2006-05-31 | 2006-02-24 | 2007-04-30 | 13. Jan. 2006 16:40 | 5 | Neumann
42 | M1.2 02.02.06 | Appr | QCT_6250_Onyx | 2005-10-28 | 2005-12-23 | 2006-01-19 | 2006-02-24 | 2006-05-15 | 2006-08-25 | 2006-11-30 | 2006-12-15 | 2006-10-20 |  | 10. Feb. 2006 16:05 | 717 | Feldhoff
50 | M0.3 23.02.2006 | Appr | Swan native LAM 850 |  | 2006-03-17 | 2006-03-17 | 2006-03-31 |  |  |  |  | 2007-01-19 |  | 23. Feb. 2006 19:59 | 302 | Kern
51 | S3.3 _17.02.2006 | Appr | Swift (Multimedia) |  | 2005-07-01 | 2005-09-23 | 2005-10-10 | 2005-10-28 | 2006-03-31 | 2006-08-04 | 2006-08-04 | 2006-04-28 |  | 03. Nov. 2005 11:04 | 490 | Kockmann
57 | V.0.9 | Appr | X95_MP-E+_SG3_Diamond | 2006-01-19 | 2006-03-17 | 2006-04-12 | 2006-05-17 | 2006-09-07 | 2007-01-10 | 2007-03-30 | 2007-03-30 | 2007-02-23 | 2008-06-18 | 06. Mar. 2006 12:14 | 254 | Barner
67 | Plan M0 | Scen | Swan native |  | 2006-03-17 | 2006-03-17 | 2006-03-31 |  |  |  |  | 2006-11-10 |  | 06. Mar. 2006 07:14 | 138 | Gallos
pre Projects
i | Ver. name | Status | preProject | I0 | I1 | I2 | I3 | I4 | Last update | Last user ID | PL
12 | I3: Rev 1.4 (RF AAL) | Appr | Bluetooth: Integration and Qualification of Enhanced Data Rate (3MBit/s) | 2004-01-31 | 2005-03-31 | 2005-09-30 | 2006-04-30 | 2006-09-30 | 27. Oct. 2005 12:44 | 6 | Karacelik
77 | MS Update | Scen | Bluetooth for Gen. 95 | 2006-01-27 | 2006-05-31 | 2006-09-29 | 2006-12-30 | 2007-02-28 | 01. Mar. 2006 12:57 | 257 | Karacelik
107 | Plan_I4.1 | Fini | Bluetooth X75 | 2002-12-19 | 2003-10-31 | 2004-09-30 | 2005-04-29 | 2005-09-29 | 21. Feb. 2006 12:22 | 5 | Karacelik
32 | V 0.4 I0 declaration | Appr | DVB-H 95 | 2005-12-23 | 2006-04-30 | 2006-09-30 | 2006-12-30 | 2007-03-30 | 31. Jan. 2006 14:14 | 257 | Karacelik
73 | Plan_I3.1 06.02.2006 | Appr | WLAN: Data over WLAN | 2003-09-19 | 2004-06-09 | 2005-03-31 | 2005-12-16 | 2006-03-31 | 31. Jan. 2006 14:16 | 257 | Karacelik