## Projects fron Z -> A
TPM2 weekly (CW 11 14.03.06)
Tops | Flops
SW Program Manager
SG2 Release Minos / Hydra
SG2 Release Swift
Gemstone Apoxi Platform
Wireless Connectivity Program Manager
Bluetooth
DVB-H
Wireless LAN
HW Program Manager
Topic 1
Topic 2
Topic 3
Products
Swift
Side-Key cracks -> solved - Semco implemented new stencil for side keys | S3HW blocked by SCM because of soldering problems in Process Test Run (PTR) - in pilot run PCBs need to be re-soldered at SIM card reader and SD card reader - 1or2 out of 4 SIM & SD-card reader fixation pads not properly soldered in 10% of PCBs - impact on drop test performance and usability under investiagation
Philips Display Cracks -> investigated and understood - Displays used in B2 environmental tests had partly been re-worked at Philips w/o notice | ALU front cover is overlapping in north of phone - pilot run parts will be re-worked at integrator Perlos - running change of ALU cover and slider upper case needed
Polaris
Production: Front Cover (FC) shortage siutuation is improving: - Reject rate at Ingoing Inspection due to dirty display lenses reduced - Alu frame supply seems to stabilise.
PD Team declared S3 milestone on 10-Mar
Philippe
S2/S25 declared by TPM team | SP PE PL leaves BenQ 31.03.06. No replacement confirmed.
First B2 parts received (unpainted) ahead of schedule | Significant LC volume decrease.
Obsidian -> start next meeting here
B1 prototype series running as scheduled (PCB and Mechanical tooling) FM Radio demo running (Radio part without UI); MMI (Java application running at Swift) BOM reduced and close to target BOM (Currently: 61,21 / Target: <60) | Ramp-up plan - Current status is commitment on the volume but missing final agreement and alignment for 10k in CW38 - Potentially 5-10k production volume to be shifted from CW38 to CW40
Missing M1 declaration from SD-QM
Minos
Jerry
M0 Q-gate OK | Not all S0 signatures available
A1 PCB's will be shipped to AAL today | Estimation of realistic M1 date needed for PBR
Hydra
Golden variant well started. | SVN 26 can neither be used for APAC DS due to two new GCF related bugs.
ORANGE FR & NL unlimited released granted (SVN24) | New estimate for APAC DS is mid CW12.
TTD still pending from EPSON.
Hawk
M0 declared and accepted by the OPC | Housing supplier not finally confirmed => S0 (08.03.06) delayed. Expected today. No DS impact expected
Diamond
* Concept decision taken by CM: Concept1 (Malpa) - frozen, concept2 (thickness improvement) - continue concept evaluation - final concept decsion expected on 17th March
* Due to "SW time out" no Project planning possible (M0,M1, DS, S4). New planning conditions depends on SW input on 27th March (support Fässler needed)
* M0 Milestone shifted, due to open design concept decision: taget open till decision has been done
* LCD Module: Single source with AUO critical for Diamond - how to continue? (support from Has needed)
Chameleon
First Primavera, prototype shop planning fixed and first Milestone planning available
First Top_Down Variant planning Chameleon available
For line break within a cell pls. press 'Alt' + 'Enter'