## Projects fron A -> Z
TPM 2 weekly (CW 12 21.03.06)
Tops | Flops
Products
Chameleon
M0/S0 declared on 20.03.2006
LAM 850 Variant cancelled
Diamond
* Concept decision done on 17th March: New dimensions: L84mm x W48,0mm x T15,3mm New Target for M0-Milestone 21th April 2006 | * Due to "SW time out" no Project planning possible (M0,M1, DS, S4). New planning conditions depends on SW input on 27th March (support Fässler needed)
* LCD Module: Single source with AUO under evaluation - Target for Decision 24th March
Hawk (1st presentation)
Suppliers selected for housing | Late conceptual changes required for side key and camera cover/shutter. Impact on time schedule under clarification. None or minor impact expected.
S0 declared | LCM PT2 responsibility transferred to China. Production on critical path. Potential time risk. Escalated to Mr. Bitsch and Mr. Döing.
Hydra
China Domestic approved SVN26 for launch | Still no progress on TTD for Display -- URGENT
Decrease of basic SW stability (complaints from region-sales)
Jerry
Minos
Obsidian
Obsidian signed M1 15 March and S15 at 20 March (2 weeks delay) | Ramp-up plan: 4k production volume to be shifted from CW38 to CW40. September volume shifted: 213->209k (Sales request 225k)
B1 prototype series running as scheduled (PCB and Mechanical tooling)
FM Radio demo running (Radio part without UI); MMI (Java application running at Swift)
BOM reduced and close to target BOM (currently: 61,21 (old FX); Target<60)
Philippe (2nd presentation)
General good impression of B2 parts but still some points to be corrected until pilot run. | Instable sales forecast. LC volume significantly decreased. Updated dispo plan must go out to suppliers. Might reduce confidence from supplier side. Escalation to the board ongoing
Critical performance of abbrasion test. Supplier has not established proper equipment for hardening the paint. Supplier requested to correct this.
Critical performance of butter test. Cracks in upper case. Root cause and solution being investigated.
Polaris
Orange Approval granted
CW11: >20k S68 produced
Swift
Sanyo statement regarding Battery with Breaker: "VDE test for Breaker has finished successfully and approval document will be released soon" | Pilot delivery of Intel Flashes delayed -> Pilot SMT run to be shifted by one week, start of assembly like planned next week
S25-APAC and S25-Step2 declared | Yield of Härter ALU cover Logo print ~ 50%, scratches in logo print in mass production -> reduced volume delivered for Pilot and expected of start of ramp-up -> counter measure review at Härter on Wednesday/Thursday
TA HW blocker due to voltage drop at SIM card reader -> not passed on ORGA tester but SIM card voltage within TA specification -> CR raisen to ORGA to change ORGA tester
Software test slot @ TMO shifted by 3 weeks by TMO -> TMO DS endangered due to late report of bugs found by TMO -> New TMO approval plan to be agreed between SW and Operator Approval Team
HW Program Manager
Topic 1
Topic 2
Topic 3
Wireless Connectivity Program Manager
Bluetooth
Did IFX accept to support second Bluetooth Solution?
DVB-H
What is the oficial schedule for Amethyst?
Wireless LAN
Transfer of WLAN SW Knowledge ULM-> KLF completed.
SW Program Manager
SG2 Release Minos / Hydra
SG2 Release Swift
Gemstone Apoxi Platform
For line break within a cell pls. press 'Alt' + 'Enter'