## Projects fron Z -> A
TPM2 weekly (CW 13 28.03.06)
Tops | Flops
SW Program Manager
SG2 Release Minos / Hydra
SG2 Release Swift
Gemstone Apoxi Platform
Wireless Connectivity Program Manager
Bluetooth
DVB-H
Wireless LAN
HW Program Manager
Topic 1
Topic 2
Topic 3
Products
Swift
Logo "diamont cut" process improved, current quality is accepted by CPM now | Shortage of KHVatec delivieries "Slider, Base upper case, Battery Cover" -> impact on TTV - secound source for die cast parts to be setup, but timeline > 10 week
Type Approvel problem with ORGA tester solved by changing components, TA samples to be selected for ORGA tests | TMO SW approval timeline couldn't be improved, TMO not willing to move test slots - Operator ST increased test recources to reduce risk of late found TMO bugs
Polaris
TMO Approval: All bugs solved with SVN30, Approval expected 3-Apr | Actual Sales Orders far behind Sales Forecast
Amena Approval: All bugs solved with SVN29, Approval expected 7-Apr | Orange Poland: Still 2 Bugs open, not reproducible
O2 Ger Approval: 2 Minor (But Blocking for O2!) Bugs open. Feedback available since Friday
Philippe
B2 running fine in prototype shop | Nolato has done improvements on hardening of the painting but does not fulfill our requirements yet. Additional corrective measures are being investigated.
Clarification of results of changes for butter test failure (cracks in upper case) not available until short before pilot run. Tests are performed in advance to adjust molding parameters
Still instable sales forecast. LC volume significantly decreased compared to M1. Escalation to the board has happened. Joos has send letter to the countries.
Obsidian
FOT 23th on all mechanical parts 3 days ahead of schedule. Generally all parts are looking good with exception of volume key and screw poles. Work is on-going. | PCB mounting will be delayed, due to late delivery of PCD (misunderstanding in ordering). Will not influence the final assembly but scheduled test must start later.
Great Sales-feedback from LAM and 850MHz version is therefore requested. Currently working on effort, schedules, business case, etc. Will be made with new M1, separate PMC account, etc. | Problems on schedule from GPM on operator approvals (request 10weeks from S3 to DS). Alignment ongoing.
Risk list and alignment between SCM, SQM and R&D made.
Minos
Jerry
All S0 signatures now available | M1 for PBR on Friday very critical as Q-gate cannot be performed before Friday morning
A1+ PCB on schedule for Friday or Monday | ASP concept from 65 generation not accepted by QM for Jerry project
Hydra
Now able to plan GOLD variant in PMC :-) | No feed-back from APAC of critical bugs. (asked GPM to secure this)
Hawk
LCM PT2 responsibility is transferred back from BEJ to KLF | Late conceptual changes (side key; camera cover/shutter) and construction changes. Fast prototypes postponed by 1 week
DS shift from 11.08.06 to 18.08.06 (due to the above changes and to secure volume)
Diamond
* decision for AUO as single source for LCD-module done | * Concept evaluation still ongoing for M0-Milestone (solve open issues)
* New target for M0-Milestone was set on 21th April 2006 | * Working Conditions for SW still Apoxi - Diamond APOXI Lead? - (HAs)
* Project Planning still open (up to DS) - Replanning based on Concept2 started - (ABe)
Chameleon
M1 is endangered due Shortage of KHVatec Slider delivieries for B1, - secound source is under investigation Nolato or Balda
For line break within a cell pls. press 'Alt' + 'Enter'