## Participants
TPM1- CoC Alignment WEEKLY |  | Meeting |  | today
|  | date: |  | weekly - Thursdays
minutes / moderation by: | Mario Topel | time (CET): |  | 01:30 - 03:00 p.m.
time (Taipei):
|  | room Mch: |  | tbd
|  | room KLF: |  | KLf, PL-T room
|  | room Taipei |  | tbd
|  | Dial-In: |  | Number of participants: Conference : +49 69 4035 9803 Conference Password: 136111 #
|  | present |  | x
|  | part time |  | p
|  | represented |  | r
|  | excused |  | e
|  | absence |  | a
Team Members | - Global e-mail distribution list: tbd
Team members | department | location |  | info | representative | 2006-05-30 | 2006-06-06 | 2006-06-13 | 2006-06-20 | 2006-06-27 | 2006-07-04 | 2006-07-11 | 2006-07-18 | 2006-07-25 | 2006-08-01
Holger Asmussen | BMG PHE TPM | PHE | head of TPM
Andreas Betting | BMG PHE TPM | PHE | TPM | Diamond | Ulrich Barner
Claus Dalmose / Jürgen Schmitz | BMG PHE TPM | PHE | TPM | Hawk | Ole Byrdal
Keld Christiansen / Ulrich Barner | BMG PHE TPM | PHE | TPM | Hydra
Ulrich Barner | BMG PHE TPM | PHE | TPM | Minos
Tony Stokholm / Michael Weigang | BMG PHE TPM | PHE | TPM | Obsidian | Ole Rasmussen
Claus Dalmose / Jürgen Schmitz | BMG PHE TPM | PHE | TPM | Philippe
Thomas Neumann | BMG PHE TPM | PHE | TPM | Polaris | Andreas Lang
Ralf Kern | BMG PHE TPM | PHE | TPM | Silverstone | Daniel Röhrig
Jürgen Kockmann | BMG PHE TPM | PHE | TPM | Swift | Markus Hohenleitner
Thomas Alkämper | BMG PHE TPM | PHE | TPM R&D
Peter Farrenkothen | BMG PHE TPM | PHE | PPS
Markus Feldhoff | BMG PHE TPM | PHE | TPM
Brigitte Flierl | BMG PHE TPM BO | PHE | TPM BO
Reinhard Gallos | BMG PHE TPM | PHE | TPM R&D
Ulrich Geiger | BMG PHE TPM | PHE | TPM SW
Ralf Hartmann | BMG PHE TPM | PHE | TPM Platform
Dirk Hänsel | BMG PHE TPM | PHE | TPM HW
Markus Hohenleitner | BMG PHE TPM | PHE | TPM R&D
Hasan Karacelik | BMG PHE TPM | PHE | TPM WC
Andreas Lang | BMG PHE TPM | PHE | TPM R&D
Daniel Röhrig | BMG PHE TPM | PHE | TPM R&D
Alois Zimmer | BMG PHE TPM | PHE | TPM
Lars Bonde | BMG PHE TPM | PHE | TPM | Jerry
Ole Byrdal | BMG PHE TPM | PHE | TPM R&D
Keld Christiansen | BMG PHE TPM | PHE | TPM
Ole Rasmussen | BMG PHE TPM | PHE | TPM R&D
informed parties | department | location
Additional Participants | department | location
Georg Fässler
Claus Friedel
Klaus Kroesen

## Diamond
TOPS & Flops
Diamond
|  |  | Tops | S0-HW Declaration done on 19th May on time
Release Button solution found and agreed with CPM
|  |  | Flops | SW transparency improving slowly - measures which were set up needs to be realized
Action Items
Blue marked comments: changes/updates from last protocol.
Project | N° | date | raised by | description | owner | target date | status | report / comments
Onyx | 1
Onyx | 2
Onyx | 3
Onyx | 4
Onyx | 5
Onyx | 6
Onyx | 7
Onyx | 8
Onyx | 9
Onyx | 10
Onyx | 11
Onyx | 12
Onyx | 13
Onyx | 14
Onyx | 15
Onyx | 16
Onyx | 18
Onyx | 19
Onyx | 20
Onyx | 21
Onyx | 22
Onyx | 23
Onyx | 24
Onyx | 25
Onyx | 26
Onyx | 27
Onyx | 28
Onyx | 29
Onyx | 30
Onyx | 31
Onyx | 32
Onyx | 33
Onyx | 34
Onyx | 35
Onyx | 36
Onyx | 37
Onyx | 38
Onyx | 39
Onyx | 40
Onyx | 41
Onyx | 42
Onyx | 43
Onyx | 44
Onyx | 45
Onyx | 46
Onyx | 47
Onyx | 48
Onyx | 49
Onyx | 50
Onyx | 51
Onyx | 52
Onyx | 53
Onyx | 54
Onyx | 55
Onyx | 56
Onyx | 57
Onyx | 58
Onyx | 59
Onyx | 60
Onyx | 61
Onyx | 62
Onyx | 63
Onyx | 64
Onyx | 65
Onyx | 66
Onyx | 67
Onyx | 68
Onyx | 69
Onyx | 70
Onyx | 71
Onyx | 72
Onyx | 73
Onyx | 74
Onyx | 75
Onyx | 76
Onyx | 77
Onyx | 78
Onyx | 79
Onyx | 80
Onyx | 81
Onyx | 82
Onyx | 83
Onyx | 84
Onyx | 85
Onyx | 86
Onyx | 87
Onyx | 88
Onyx | 89
Onyx | 90
Onyx | 91
Onyx | 92
Onyx | 93
Onyx | 94
Onyx | 95
Onyx | 96
Onyx | 97
Onyx | 98
Onyx | 99
Onyx | 100
Onyx | 101
Onyx | 102
Onyx | 103
Onyx | 104
Onyx | 105
Onyx | 106
Onyx | 107
Onyx | 108
Onyx | 109
Onyx | 110
Onyx | 111
Onyx | 112
Onyx | 113
Onyx | 114
Onyx | 115
Onyx | 116
Onyx | 117
Onyx | 118
Onyx | 119
Onyx | 120
Onyx | 121
Onyx | 122
Onyx | 123
Onyx | 124
Onyx | 125
Onyx | 126
Onyx | 127
Onyx | 128
Onyx | 129
Onyx | 130
Onyx | 131
Onyx | 132
Onyx | 133
Onyx | 134
Onyx | 135
Onyx | 136
Onyx | 137
Onyx | 138
Onyx | 139
Onyx | 140
Onyx | 141
Onyx | 142
Onyx | 143
Onyx | 144
Onyx | 145
Onyx | 146
Onyx | 147
Onyx | 148
Onyx | 149
Onyx | 150
Onyx | 151
Onyx | 152
Onyx | 153
Onyx | 154
Onyx | 155
Onyx | 156
Onyx | 157
Onyx | 158
Onyx | 159
Onyx | 160
Onyx | 161
Onyx | 162
Onyx | 163
Onyx | 164
Onyx | 165
Onyx | 166
Onyx | 167
Onyx | 168
Onyx | 169
Onyx | 170
Onyx | 171
Onyx | 172
Onyx | 173
Onyx | 174
Onyx | 175
Onyx | 176
Onyx | 177
Onyx | 178
Onyx | 179
Onyx | 180
Onyx | 181
Onyx | 182
Onyx | 183
Onyx | 184
Onyx | 185
Onyx | 186
Onyx | 187
Onyx | 188
Onyx | 189
Onyx | 190
Onyx | 191
Onyx | 192
Onyx | 193
Onyx | 194
Onyx | 195
Onyx | 196
Onyx | 197
Onyx | 198
Onyx | 199
Onyx | 200
Onyx | 201
Onyx | 202
Onyx | 203
Onyx | 204
Onyx | 205
Onyx | 206
Onyx | 207
Onyx | 208
Onyx | 209
Onyx | 210
Onyx | 211
Onyx | 212
Onyx | 213
Onyx | 214
Onyx | 215
Onyx | 216
Onyx | 217
Onyx | 218
Onyx | 219
Onyx | 220
Onyx | 221
Onyx | 222
Onyx | 223
Onyx | 224
Onyx | 225
Onyx | 226
Onyx | 227
Onyx | 228
Onyx | 229
Onyx | 230
Onyx | 231
Onyx | 232
Onyx | 233
Onyx | 234
Onyx | 235
Onyx | 236
Onyx | 237
Onyx | 238
Onyx | 239
Onyx | 240
Onyx | 241
Onyx | 242
Onyx | 243
Onyx | 244
Onyx | 245
Onyx | 246
Onyx | 247
Onyx | 248
Onyx | 249
Onyx | 250
Onyx | 251
Onyx | 252
Onyx | 253
Onyx | 254
Onyx | 255
Onyx | 256
Onyx | 257
Onyx | 258
Onyx | 259
Onyx | 260
Onyx | 261
Onyx | 262
Onyx | 263
Onyx | 264
Onyx | 265
Onyx | 266
Onyx | 267
Onyx | 268
Onyx | 269
Onyx | 270
Onyx | 271
Onyx | 272
Onyx | 273
Onyx | 274
Onyx | 275
Onyx | 276
Onyx | 277
Onyx | 278
Onyx | 279
Onyx | 280
Onyx | 281
Onyx | 282
Onyx | 283
Onyx | 284
Onyx | 285
Onyx | 286
Onyx | 287
Onyx | 288
Onyx | 289
Onyx | 290
Onyx | 291
Onyx | 292
Onyx | 293
Onyx | 294
Onyx | 295
Onyx | 296
Onyx | 297
Onyx | 298
Onyx | 299
Onyx | 300
Onyx | 301
Onyx | 302
Onyx | 303
Onyx | 304
Onyx | 305
Onyx | 306
Onyx | 307
Onyx | 308
Onyx | 309
Onyx | 310
Onyx | 311
Onyx | 312
Onyx | 313
Onyx | 314
Onyx | 315
Onyx | 316
Onyx | 317
Onyx | 318
Onyx | 319
Onyx | 320
Onyx | 321
Onyx | 322
Onyx | 323
Onyx | 324
Onyx | 325
Onyx | 326
Onyx | 327
Onyx | 328
Onyx | 329
Onyx | 330
Onyx | 331
Onyx | 332
Onyx | 333
Onyx | 334
Onyx | 335
Onyx | 336
Onyx | 337
Onyx | 338
Onyx | 339
Onyx | 340
Onyx | 341
Onyx | 342
Onyx | 343
Onyx | 344
Onyx | 345
Onyx | 346
Onyx | 347
Onyx | 348
Onyx | 349
Onyx | 350
Onyx | 351
Onyx | 352
Onyx | 353
Onyx | 354
Onyx | 355
Onyx | 356
Onyx | 357
Onyx | 358
Onyx | 359
Onyx | 360
Onyx | 361

## Hawk
TOPS & Flops
Hawk
|  |  | Tops | First deliveries of B1+ parts in AAL and KLF
Pre environmental test started for B1+
|  |  | Flops | Currently a delay of about 6 working days of project activities related to mechanical parts due to problems at tool maker with the upper case tool.
Significant tool improvements required after B1+
Turning camera lid not working satisfactory. Noisy and too hard to turn for the first about 3.500 turns.
Action Items
Blue marked comments: changes/updates from last protocol.
Project | N° | date | raised by | description | owner | target date | status | report / comments
Onyx | 1
Onyx | 2
Onyx | 3
Onyx | 4
Onyx | 5
Onyx | 6
Onyx | 7
Onyx | 8
Onyx | 9
Onyx | 10
Onyx | 11
Onyx | 12
Onyx | 13
Onyx | 14
Onyx | 15
Onyx | 16
Onyx | 18
Onyx | 19
Onyx | 20
Onyx | 21
Onyx | 22
Onyx | 23
Onyx | 24
Onyx | 25
Onyx | 26
Onyx | 27
Onyx | 28
Onyx | 29
Onyx | 30
Onyx | 31
Onyx | 32
Onyx | 33
Onyx | 34
Onyx | 35
Onyx | 36
Onyx | 37
Onyx | 38
Onyx | 39
Onyx | 40
Onyx | 41
Onyx | 42
Onyx | 43
Onyx | 44
Onyx | 45
Onyx | 46
Onyx | 47
Onyx | 48
Onyx | 49
Onyx | 50
Onyx | 51
Onyx | 52
Onyx | 53
Onyx | 54
Onyx | 55
Onyx | 56
Onyx | 57
Onyx | 58
Onyx | 59
Onyx | 60
Onyx | 61
Onyx | 62
Onyx | 63
Onyx | 64
Onyx | 65
Onyx | 66
Onyx | 67
Onyx | 68
Onyx | 69
Onyx | 70
Onyx | 71
Onyx | 72
Onyx | 73
Onyx | 74
Onyx | 75
Onyx | 76
Onyx | 77
Onyx | 78
Onyx | 79
Onyx | 80
Onyx | 81
Onyx | 82
Onyx | 83
Onyx | 84
Onyx | 85
Onyx | 86
Onyx | 87
Onyx | 88
Onyx | 89
Onyx | 90
Onyx | 91
Onyx | 92
Onyx | 93
Onyx | 94
Onyx | 95
Onyx | 96
Onyx | 97
Onyx | 98
Onyx | 99
Onyx | 100
Onyx | 101
Onyx | 102
Onyx | 103
Onyx | 104
Onyx | 105
Onyx | 106
Onyx | 107
Onyx | 108
Onyx | 109
Onyx | 110
Onyx | 111
Onyx | 112
Onyx | 113
Onyx | 114
Onyx | 115
Onyx | 116
Onyx | 117
Onyx | 118
Onyx | 119
Onyx | 120
Onyx | 121
Onyx | 122
Onyx | 123
Onyx | 124
Onyx | 125
Onyx | 126
Onyx | 127
Onyx | 128
Onyx | 129
Onyx | 130
Onyx | 131
Onyx | 132
Onyx | 133
Onyx | 134
Onyx | 135
Onyx | 136
Onyx | 137
Onyx | 138
Onyx | 139
Onyx | 140
Onyx | 141
Onyx | 142
Onyx | 143
Onyx | 144
Onyx | 145
Onyx | 146
Onyx | 147
Onyx | 148
Onyx | 149
Onyx | 150
Onyx | 151
Onyx | 152
Onyx | 153
Onyx | 154
Onyx | 155
Onyx | 156
Onyx | 157
Onyx | 158
Onyx | 159
Onyx | 160
Onyx | 161
Onyx | 162
Onyx | 163
Onyx | 164
Onyx | 165
Onyx | 166
Onyx | 167
Onyx | 168
Onyx | 169
Onyx | 170
Onyx | 171
Onyx | 172
Onyx | 173
Onyx | 174
Onyx | 175
Onyx | 176
Onyx | 177
Onyx | 178
Onyx | 179
Onyx | 180
Onyx | 181
Onyx | 182
Onyx | 183
Onyx | 184
Onyx | 185
Onyx | 186
Onyx | 187
Onyx | 188
Onyx | 189
Onyx | 190
Onyx | 191
Onyx | 192
Onyx | 193
Onyx | 194
Onyx | 195
Onyx | 196
Onyx | 197
Onyx | 198
Onyx | 199
Onyx | 200
Onyx | 201
Onyx | 202
Onyx | 203
Onyx | 204
Onyx | 205
Onyx | 206
Onyx | 207
Onyx | 208
Onyx | 209
Onyx | 210
Onyx | 211
Onyx | 212
Onyx | 213
Onyx | 214
Onyx | 215
Onyx | 216
Onyx | 217
Onyx | 218
Onyx | 219
Onyx | 220
Onyx | 221
Onyx | 222
Onyx | 223
Onyx | 224
Onyx | 225
Onyx | 226
Onyx | 227
Onyx | 228
Onyx | 229
Onyx | 230
Onyx | 231
Onyx | 232
Onyx | 233
Onyx | 234
Onyx | 235
Onyx | 236
Onyx | 237
Onyx | 238
Onyx | 239
Onyx | 240
Onyx | 241
Onyx | 242
Onyx | 243
Onyx | 244
Onyx | 245
Onyx | 246
Onyx | 247
Onyx | 248
Onyx | 249
Onyx | 250
Onyx | 251
Onyx | 252
Onyx | 253
Onyx | 254
Onyx | 255
Onyx | 256
Onyx | 257
Onyx | 258
Onyx | 259
Onyx | 260
Onyx | 261
Onyx | 262
Onyx | 263
Onyx | 264
Onyx | 265
Onyx | 266
Onyx | 267
Onyx | 268
Onyx | 269
Onyx | 270
Onyx | 271
Onyx | 272
Onyx | 273
Onyx | 274
Onyx | 275
Onyx | 276
Onyx | 277
Onyx | 278
Onyx | 279
Onyx | 280
Onyx | 281
Onyx | 282
Onyx | 283
Onyx | 284
Onyx | 285
Onyx | 286
Onyx | 287
Onyx | 288
Onyx | 289
Onyx | 290
Onyx | 291
Onyx | 292
Onyx | 293
Onyx | 294
Onyx | 295
Onyx | 296
Onyx | 297
Onyx | 298
Onyx | 299
Onyx | 300
Onyx | 301
Onyx | 302
Onyx | 303
Onyx | 304
Onyx | 305
Onyx | 306
Onyx | 307
Onyx | 308
Onyx | 309
Onyx | 310
Onyx | 311
Onyx | 312
Onyx | 313
Onyx | 314
Onyx | 315
Onyx | 316
Onyx | 317
Onyx | 318
Onyx | 319
Onyx | 320
Onyx | 321
Onyx | 322
Onyx | 323
Onyx | 324
Onyx | 325
Onyx | 326
Onyx | 327
Onyx | 328
Onyx | 329
Onyx | 330
Onyx | 331
Onyx | 332
Onyx | 333
Onyx | 334
Onyx | 335
Onyx | 336
Onyx | 337
Onyx | 338
Onyx | 339
Onyx | 340
Onyx | 341
Onyx | 342
Onyx | 343
Onyx | 344
Onyx | 345
Onyx | 346
Onyx | 347
Onyx | 348
Onyx | 349
Onyx | 350
Onyx | 351
Onyx | 352
Onyx | 353
Onyx | 354
Onyx | 355
Onyx | 356
Onyx | 357
Onyx | 358
Onyx | 359
Onyx | 360
Onyx | 361

## Hydra
TOPS & Flops
Hydra
|  |  | Tops | S4 on track
|  |  | Flops | Still unclarified whether streaming will be in SL75
Action Items
Blue marked comments: changes/updates from last protocol.
Project | N° | date | raised by | description | owner | target date | status | report / comments
Onyx | 1
Onyx | 2
Onyx | 3
Onyx | 4
Onyx | 5
Onyx | 6
Onyx | 7
Onyx | 8
Onyx | 9
Onyx | 10
Onyx | 11
Onyx | 12
Onyx | 13
Onyx | 14
Onyx | 15
Onyx | 16
Onyx | 18
Onyx | 19
Onyx | 20
Onyx | 21
Onyx | 22
Onyx | 23
Onyx | 24
Onyx | 25
Onyx | 26
Onyx | 27
Onyx | 28
Onyx | 29
Onyx | 30
Onyx | 31
Onyx | 32
Onyx | 33
Onyx | 34
Onyx | 35
Onyx | 36
Onyx | 37
Onyx | 38
Onyx | 39
Onyx | 40
Onyx | 41
Onyx | 42
Onyx | 43
Onyx | 44
Onyx | 45
Onyx | 46
Onyx | 47
Onyx | 48
Onyx | 49
Onyx | 50
Onyx | 51
Onyx | 52
Onyx | 53
Onyx | 54
Onyx | 55
Onyx | 56
Onyx | 57
Onyx | 58
Onyx | 59
Onyx | 60
Onyx | 61
Onyx | 62
Onyx | 63
Onyx | 64
Onyx | 65
Onyx | 66
Onyx | 67
Onyx | 68
Onyx | 69
Onyx | 70
Onyx | 71
Onyx | 72
Onyx | 73
Onyx | 74
Onyx | 75
Onyx | 76
Onyx | 77
Onyx | 78
Onyx | 79
Onyx | 80
Onyx | 81
Onyx | 82
Onyx | 83
Onyx | 84
Onyx | 85
Onyx | 86
Onyx | 87
Onyx | 88
Onyx | 89
Onyx | 90
Onyx | 91
Onyx | 92
Onyx | 93
Onyx | 94
Onyx | 95
Onyx | 96
Onyx | 97
Onyx | 98
Onyx | 99
Onyx | 100
Onyx | 101
Onyx | 102
Onyx | 103
Onyx | 104
Onyx | 105
Onyx | 106
Onyx | 107
Onyx | 108
Onyx | 109
Onyx | 110
Onyx | 111
Onyx | 112
Onyx | 113
Onyx | 114
Onyx | 115
Onyx | 116
Onyx | 117
Onyx | 118
Onyx | 119
Onyx | 120
Onyx | 121
Onyx | 122
Onyx | 123
Onyx | 124
Onyx | 125
Onyx | 126
Onyx | 127
Onyx | 128
Onyx | 129
Onyx | 130
Onyx | 131
Onyx | 132
Onyx | 133
Onyx | 134
Onyx | 135
Onyx | 136
Onyx | 137
Onyx | 138
Onyx | 139
Onyx | 140
Onyx | 141
Onyx | 142
Onyx | 143
Onyx | 144
Onyx | 145
Onyx | 146
Onyx | 147
Onyx | 148
Onyx | 149
Onyx | 150
Onyx | 151
Onyx | 152
Onyx | 153
Onyx | 154
Onyx | 155
Onyx | 156
Onyx | 157
Onyx | 158
Onyx | 159
Onyx | 160
Onyx | 161
Onyx | 162
Onyx | 163
Onyx | 164
Onyx | 165
Onyx | 166
Onyx | 167
Onyx | 168
Onyx | 169
Onyx | 170
Onyx | 171
Onyx | 172
Onyx | 173
Onyx | 174
Onyx | 175
Onyx | 176
Onyx | 177
Onyx | 178
Onyx | 179
Onyx | 180
Onyx | 181
Onyx | 182
Onyx | 183
Onyx | 184
Onyx | 185
Onyx | 186
Onyx | 187
Onyx | 188
Onyx | 189
Onyx | 190
Onyx | 191
Onyx | 192
Onyx | 193
Onyx | 194
Onyx | 195
Onyx | 196
Onyx | 197
Onyx | 198
Onyx | 199
Onyx | 200
Onyx | 201
Onyx | 202
Onyx | 203
Onyx | 204
Onyx | 205
Onyx | 206
Onyx | 207
Onyx | 208
Onyx | 209
Onyx | 210
Onyx | 211
Onyx | 212
Onyx | 213
Onyx | 214
Onyx | 215
Onyx | 216
Onyx | 217
Onyx | 218
Onyx | 219
Onyx | 220
Onyx | 221
Onyx | 222
Onyx | 223
Onyx | 224
Onyx | 225
Onyx | 226
Onyx | 227
Onyx | 228
Onyx | 229
Onyx | 230
Onyx | 231
Onyx | 232
Onyx | 233
Onyx | 234
Onyx | 235
Onyx | 236
Onyx | 237
Onyx | 238
Onyx | 239
Onyx | 240
Onyx | 241
Onyx | 242
Onyx | 243
Onyx | 244
Onyx | 245
Onyx | 246
Onyx | 247
Onyx | 248
Onyx | 249
Onyx | 250
Onyx | 251
Onyx | 252
Onyx | 253
Onyx | 254
Onyx | 255
Onyx | 256
Onyx | 257
Onyx | 258
Onyx | 259
Onyx | 260
Onyx | 261
Onyx | 262
Onyx | 263
Onyx | 264
Onyx | 265
Onyx | 266
Onyx | 267
Onyx | 268
Onyx | 269
Onyx | 270
Onyx | 271
Onyx | 272
Onyx | 273
Onyx | 274
Onyx | 275
Onyx | 276
Onyx | 277
Onyx | 278
Onyx | 279
Onyx | 280
Onyx | 281
Onyx | 282
Onyx | 283
Onyx | 284
Onyx | 285
Onyx | 286
Onyx | 287
Onyx | 288
Onyx | 289
Onyx | 290
Onyx | 291
Onyx | 292
Onyx | 293
Onyx | 294
Onyx | 295
Onyx | 296
Onyx | 297
Onyx | 298
Onyx | 299
Onyx | 300
Onyx | 301
Onyx | 302
Onyx | 303
Onyx | 304
Onyx | 305
Onyx | 306
Onyx | 307
Onyx | 308
Onyx | 309
Onyx | 310
Onyx | 311
Onyx | 312
Onyx | 313
Onyx | 314
Onyx | 315
Onyx | 316
Onyx | 317
Onyx | 318
Onyx | 319
Onyx | 320
Onyx | 321
Onyx | 322
Onyx | 323
Onyx | 324
Onyx | 325
Onyx | 326
Onyx | 327
Onyx | 328
Onyx | 329
Onyx | 330
Onyx | 331
Onyx | 332
Onyx | 333
Onyx | 334
Onyx | 335
Onyx | 336
Onyx | 337
Onyx | 338
Onyx | 339
Onyx | 340
Onyx | 341
Onyx | 342
Onyx | 343
Onyx | 344
Onyx | 345
Onyx | 346
Onyx | 347
Onyx | 348
Onyx | 349
Onyx | 350
Onyx | 351
Onyx | 352
Onyx | 353
Onyx | 354
Onyx | 355
Onyx | 356
Onyx | 357
Onyx | 358
Onyx | 359
Onyx | 360
Onyx | 361

## Minos
TOPS & Flops
Minos
Tops
Flops
Action Items
Blue marked comments: changes/updates from last protocol.
Project | N° | date | raised by | description | owner | target date | status | report / comments
Onyx | 1
Onyx | 2
Onyx | 3
Onyx | 4
Onyx | 5
Onyx | 6
Onyx | 7
Onyx | 8
Onyx | 9
Onyx | 10
Onyx | 11
Onyx | 12
Onyx | 13
Onyx | 14
Onyx | 15
Onyx | 16
Onyx | 18
Onyx | 19
Onyx | 20
Onyx | 21
Onyx | 22
Onyx | 23
Onyx | 24
Onyx | 25
Onyx | 26
Onyx | 27
Onyx | 28
Onyx | 29
Onyx | 30
Onyx | 31
Onyx | 32
Onyx | 33
Onyx | 34
Onyx | 35
Onyx | 36
Onyx | 37
Onyx | 38
Onyx | 39
Onyx | 40
Onyx | 41
Onyx | 42
Onyx | 43
Onyx | 44
Onyx | 45
Onyx | 46
Onyx | 47
Onyx | 48
Onyx | 49
Onyx | 50
Onyx | 51
Onyx | 52
Onyx | 53
Onyx | 54
Onyx | 55
Onyx | 56
Onyx | 57
Onyx | 58
Onyx | 59
Onyx | 60
Onyx | 61
Onyx | 62
Onyx | 63
Onyx | 64
Onyx | 65
Onyx | 66
Onyx | 67
Onyx | 68
Onyx | 69
Onyx | 70
Onyx | 71
Onyx | 72
Onyx | 73
Onyx | 74
Onyx | 75
Onyx | 76
Onyx | 77
Onyx | 78
Onyx | 79
Onyx | 80
Onyx | 81
Onyx | 82
Onyx | 83
Onyx | 84
Onyx | 85
Onyx | 86
Onyx | 87
Onyx | 88
Onyx | 89
Onyx | 90
Onyx | 91
Onyx | 92
Onyx | 93
Onyx | 94
Onyx | 95
Onyx | 96
Onyx | 97
Onyx | 98
Onyx | 99
Onyx | 100
Onyx | 101
Onyx | 102
Onyx | 103
Onyx | 104
Onyx | 105
Onyx | 106
Onyx | 107
Onyx | 108
Onyx | 109
Onyx | 110
Onyx | 111
Onyx | 112
Onyx | 113
Onyx | 114
Onyx | 115
Onyx | 116
Onyx | 117
Onyx | 118
Onyx | 119
Onyx | 120
Onyx | 121
Onyx | 122
Onyx | 123
Onyx | 124
Onyx | 125
Onyx | 126
Onyx | 127
Onyx | 128
Onyx | 129
Onyx | 130
Onyx | 131
Onyx | 132
Onyx | 133
Onyx | 134
Onyx | 135
Onyx | 136
Onyx | 137
Onyx | 138
Onyx | 139
Onyx | 140
Onyx | 141
Onyx | 142
Onyx | 143
Onyx | 144
Onyx | 145
Onyx | 146
Onyx | 147
Onyx | 148
Onyx | 149
Onyx | 150
Onyx | 151
Onyx | 152
Onyx | 153
Onyx | 154
Onyx | 155
Onyx | 156
Onyx | 157
Onyx | 158
Onyx | 159
Onyx | 160
Onyx | 161
Onyx | 162
Onyx | 163
Onyx | 164
Onyx | 165
Onyx | 166
Onyx | 167
Onyx | 168
Onyx | 169
Onyx | 170
Onyx | 171
Onyx | 172
Onyx | 173
Onyx | 174
Onyx | 175
Onyx | 176
Onyx | 177
Onyx | 178
Onyx | 179
Onyx | 180
Onyx | 181
Onyx | 182
Onyx | 183
Onyx | 184
Onyx | 185
Onyx | 186
Onyx | 187
Onyx | 188
Onyx | 189
Onyx | 190
Onyx | 191
Onyx | 192
Onyx | 193
Onyx | 194
Onyx | 195
Onyx | 196
Onyx | 197
Onyx | 198
Onyx | 199
Onyx | 200
Onyx | 201
Onyx | 202
Onyx | 203
Onyx | 204
Onyx | 205
Onyx | 206
Onyx | 207
Onyx | 208
Onyx | 209
Onyx | 210
Onyx | 211
Onyx | 212
Onyx | 213
Onyx | 214
Onyx | 215
Onyx | 216
Onyx | 217
Onyx | 218
Onyx | 219
Onyx | 220
Onyx | 221
Onyx | 222
Onyx | 223
Onyx | 224
Onyx | 225
Onyx | 226
Onyx | 227
Onyx | 228
Onyx | 229
Onyx | 230
Onyx | 231
Onyx | 232
Onyx | 233
Onyx | 234
Onyx | 235
Onyx | 236
Onyx | 237
Onyx | 238
Onyx | 239
Onyx | 240
Onyx | 241
Onyx | 242
Onyx | 243
Onyx | 244
Onyx | 245
Onyx | 246
Onyx | 247
Onyx | 248
Onyx | 249
Onyx | 250
Onyx | 251
Onyx | 252
Onyx | 253
Onyx | 254
Onyx | 255
Onyx | 256
Onyx | 257
Onyx | 258
Onyx | 259
Onyx | 260
Onyx | 261
Onyx | 262
Onyx | 263
Onyx | 264
Onyx | 265
Onyx | 266
Onyx | 267
Onyx | 268
Onyx | 269
Onyx | 270
Onyx | 271
Onyx | 272
Onyx | 273
Onyx | 274
Onyx | 275
Onyx | 276
Onyx | 277
Onyx | 278
Onyx | 279
Onyx | 280
Onyx | 281
Onyx | 282
Onyx | 283
Onyx | 284
Onyx | 285
Onyx | 286
Onyx | 287
Onyx | 288
Onyx | 289
Onyx | 290
Onyx | 291
Onyx | 292
Onyx | 293
Onyx | 294
Onyx | 295
Onyx | 296
Onyx | 297
Onyx | 298
Onyx | 299
Onyx | 300
Onyx | 301
Onyx | 302
Onyx | 303
Onyx | 304
Onyx | 305
Onyx | 306
Onyx | 307
Onyx | 308
Onyx | 309
Onyx | 310
Onyx | 311
Onyx | 312
Onyx | 313
Onyx | 314
Onyx | 315
Onyx | 316
Onyx | 317
Onyx | 318
Onyx | 319
Onyx | 320
Onyx | 321
Onyx | 322
Onyx | 323
Onyx | 324
Onyx | 325
Onyx | 326
Onyx | 327
Onyx | 328
Onyx | 329
Onyx | 330
Onyx | 331
Onyx | 332
Onyx | 333
Onyx | 334
Onyx | 335
Onyx | 336
Onyx | 337
Onyx | 338
Onyx | 339
Onyx | 340
Onyx | 341
Onyx | 342
Onyx | 343
Onyx | 344
Onyx | 345
Onyx | 346
Onyx | 347
Onyx | 348
Onyx | 349
Onyx | 350
Onyx | 351
Onyx | 352
Onyx | 353
Onyx | 354
Onyx | 355
Onyx | 356
Onyx | 357
Onyx | 358
Onyx | 359
Onyx | 360
Onyx | 361

## Obsidian
TOPS & Flops
Obsidian
|  |  | Tops | - B1+ Mechanical data shipped 11th May according to schedule
- B1+ PCB data ready for shipment 17th May according to schedule
- Settled new PVD share 75% including supplier commitment
- Settled that Obsidian always includes FM radio (simplifies SW variants + tests) due to missing volume on version without FM radio (BOM and Business case upgraded)
|  |  | Flops | - Obsidian S2 (18.05.06) & Obsidian LAM 850 M1, (target 10.05.06); Both delayed due to missing supplier commitment (SCM/ SQM) – Received and signatures expected today (23rd); Missing signature from AD (reason unknown)
Action Items
Blue marked comments: changes/updates from last protocol.
Project | N° | date | raised by | description | owner | target date | status | report / comments
Onyx | 1
Onyx | 2
Onyx | 3
Onyx | 4
Onyx | 5
Onyx | 6
Onyx | 7
Onyx | 8
Onyx | 9
Onyx | 10
Onyx | 11
Onyx | 12
Onyx | 13
Onyx | 14
Onyx | 15
Onyx | 16
Onyx | 18
Onyx | 19
Onyx | 20
Onyx | 21
Onyx | 22
Onyx | 23
Onyx | 24
Onyx | 25
Onyx | 26
Onyx | 27
Onyx | 28
Onyx | 29
Onyx | 30
Onyx | 31
Onyx | 32
Onyx | 33
Onyx | 34
Onyx | 35
Onyx | 36
Onyx | 37
Onyx | 38
Onyx | 39
Onyx | 40
Onyx | 41
Onyx | 42
Onyx | 43
Onyx | 44
Onyx | 45
Onyx | 46
Onyx | 47
Onyx | 48
Onyx | 49
Onyx | 50
Onyx | 51
Onyx | 52
Onyx | 53
Onyx | 54
Onyx | 55
Onyx | 56
Onyx | 57
Onyx | 58
Onyx | 59
Onyx | 60
Onyx | 61
Onyx | 62
Onyx | 63
Onyx | 64
Onyx | 65
Onyx | 66
Onyx | 67
Onyx | 68
Onyx | 69
Onyx | 70
Onyx | 71
Onyx | 72
Onyx | 73
Onyx | 74
Onyx | 75
Onyx | 76
Onyx | 77
Onyx | 78
Onyx | 79
Onyx | 80
Onyx | 81
Onyx | 82
Onyx | 83
Onyx | 84
Onyx | 85
Onyx | 86
Onyx | 87
Onyx | 88
Onyx | 89
Onyx | 90
Onyx | 91
Onyx | 92
Onyx | 93
Onyx | 94
Onyx | 95
Onyx | 96
Onyx | 97
Onyx | 98
Onyx | 99
Onyx | 100
Onyx | 101
Onyx | 102
Onyx | 103
Onyx | 104
Onyx | 105
Onyx | 106
Onyx | 107
Onyx | 108
Onyx | 109
Onyx | 110
Onyx | 111
Onyx | 112
Onyx | 113
Onyx | 114
Onyx | 115
Onyx | 116
Onyx | 117
Onyx | 118
Onyx | 119
Onyx | 120
Onyx | 121
Onyx | 122
Onyx | 123
Onyx | 124
Onyx | 125
Onyx | 126
Onyx | 127
Onyx | 128
Onyx | 129
Onyx | 130
Onyx | 131
Onyx | 132
Onyx | 133
Onyx | 134
Onyx | 135
Onyx | 136
Onyx | 137
Onyx | 138
Onyx | 139
Onyx | 140
Onyx | 141
Onyx | 142
Onyx | 143
Onyx | 144
Onyx | 145
Onyx | 146
Onyx | 147
Onyx | 148
Onyx | 149
Onyx | 150
Onyx | 151
Onyx | 152
Onyx | 153
Onyx | 154
Onyx | 155
Onyx | 156
Onyx | 157
Onyx | 158
Onyx | 159
Onyx | 160
Onyx | 161
Onyx | 162
Onyx | 163
Onyx | 164
Onyx | 165
Onyx | 166
Onyx | 167
Onyx | 168
Onyx | 169
Onyx | 170
Onyx | 171
Onyx | 172
Onyx | 173
Onyx | 174
Onyx | 175
Onyx | 176
Onyx | 177
Onyx | 178
Onyx | 179
Onyx | 180
Onyx | 181
Onyx | 182
Onyx | 183
Onyx | 184
Onyx | 185
Onyx | 186
Onyx | 187
Onyx | 188
Onyx | 189
Onyx | 190
Onyx | 191
Onyx | 192
Onyx | 193
Onyx | 194
Onyx | 195
Onyx | 196
Onyx | 197
Onyx | 198
Onyx | 199
Onyx | 200
Onyx | 201
Onyx | 202
Onyx | 203
Onyx | 204
Onyx | 205
Onyx | 206
Onyx | 207
Onyx | 208
Onyx | 209
Onyx | 210
Onyx | 211
Onyx | 212
Onyx | 213
Onyx | 214
Onyx | 215
Onyx | 216
Onyx | 217
Onyx | 218
Onyx | 219
Onyx | 220
Onyx | 221
Onyx | 222
Onyx | 223
Onyx | 224
Onyx | 225
Onyx | 226
Onyx | 227
Onyx | 228
Onyx | 229
Onyx | 230
Onyx | 231
Onyx | 232
Onyx | 233
Onyx | 234
Onyx | 235
Onyx | 236
Onyx | 237
Onyx | 238
Onyx | 239
Onyx | 240
Onyx | 241
Onyx | 242
Onyx | 243
Onyx | 244
Onyx | 245
Onyx | 246
Onyx | 247
Onyx | 248
Onyx | 249
Onyx | 250
Onyx | 251
Onyx | 252
Onyx | 253
Onyx | 254
Onyx | 255
Onyx | 256
Onyx | 257
Onyx | 258
Onyx | 259
Onyx | 260
Onyx | 261
Onyx | 262
Onyx | 263
Onyx | 264
Onyx | 265
Onyx | 266
Onyx | 267
Onyx | 268
Onyx | 269
Onyx | 270
Onyx | 271
Onyx | 272
Onyx | 273
Onyx | 274
Onyx | 275
Onyx | 276
Onyx | 277
Onyx | 278
Onyx | 279
Onyx | 280
Onyx | 281
Onyx | 282
Onyx | 283
Onyx | 284
Onyx | 285
Onyx | 286
Onyx | 287
Onyx | 288
Onyx | 289
Onyx | 290
Onyx | 291
Onyx | 292
Onyx | 293
Onyx | 294
Onyx | 295
Onyx | 296
Onyx | 297
Onyx | 298
Onyx | 299
Onyx | 300
Onyx | 301
Onyx | 302
Onyx | 303
Onyx | 304
Onyx | 305
Onyx | 306
Onyx | 307
Onyx | 308
Onyx | 309
Onyx | 310
Onyx | 311
Onyx | 312
Onyx | 313
Onyx | 314
Onyx | 315
Onyx | 316
Onyx | 317
Onyx | 318
Onyx | 319
Onyx | 320
Onyx | 321
Onyx | 322
Onyx | 323
Onyx | 324
Onyx | 325
Onyx | 326
Onyx | 327
Onyx | 328
Onyx | 329
Onyx | 330
Onyx | 331
Onyx | 332
Onyx | 333
Onyx | 334
Onyx | 335
Onyx | 336
Onyx | 337
Onyx | 338
Onyx | 339
Onyx | 340
Onyx | 341
Onyx | 342
Onyx | 343
Onyx | 344
Onyx | 345
Onyx | 346
Onyx | 347
Onyx | 348
Onyx | 349
Onyx | 350
Onyx | 351
Onyx | 352
Onyx | 353
Onyx | 354
Onyx | 355
Onyx | 356
Onyx | 357
Onyx | 358
Onyx | 359
Onyx | 360
Onyx | 361

## Philippe
TOPS & Flops
Philippe
|  |  | Tops | DS declared in PBR 19.05.06 (scheduled for 29.05.06)
First shipments send out today (23.05.06)
|  |  | Flops | Mechanical corrections necessary after DS due to gap at side key and failures in butter test.
Action Items
Blue marked comments: changes/updates from last protocol.
Project | N° | date | raised by | description | owner | target date | status | report / comments
Onyx | 1
Onyx | 2
Onyx | 3
Onyx | 4
Onyx | 5
Onyx | 6
Onyx | 7
Onyx | 8
Onyx | 9
Onyx | 10
Onyx | 11
Onyx | 12
Onyx | 13
Onyx | 14
Onyx | 15
Onyx | 16
Onyx | 18
Onyx | 19
Onyx | 20
Onyx | 21
Onyx | 22
Onyx | 23
Onyx | 24
Onyx | 25
Onyx | 26
Onyx | 27
Onyx | 28
Onyx | 29
Onyx | 30
Onyx | 31
Onyx | 32
Onyx | 33
Onyx | 34
Onyx | 35
Onyx | 36
Onyx | 37
Onyx | 38
Onyx | 39
Onyx | 40
Onyx | 41
Onyx | 42
Onyx | 43
Onyx | 44
Onyx | 45
Onyx | 46
Onyx | 47
Onyx | 48
Onyx | 49
Onyx | 50
Onyx | 51
Onyx | 52
Onyx | 53
Onyx | 54
Onyx | 55
Onyx | 56
Onyx | 57
Onyx | 58
Onyx | 59
Onyx | 60
Onyx | 61
Onyx | 62
Onyx | 63
Onyx | 64
Onyx | 65
Onyx | 66
Onyx | 67
Onyx | 68
Onyx | 69
Onyx | 70
Onyx | 71
Onyx | 72
Onyx | 73
Onyx | 74
Onyx | 75
Onyx | 76
Onyx | 77
Onyx | 78
Onyx | 79
Onyx | 80
Onyx | 81
Onyx | 82
Onyx | 83
Onyx | 84
Onyx | 85
Onyx | 86
Onyx | 87
Onyx | 88
Onyx | 89
Onyx | 90
Onyx | 91
Onyx | 92
Onyx | 93
Onyx | 94
Onyx | 95
Onyx | 96
Onyx | 97
Onyx | 98
Onyx | 99
Onyx | 100
Onyx | 101
Onyx | 102
Onyx | 103
Onyx | 104
Onyx | 105
Onyx | 106
Onyx | 107
Onyx | 108
Onyx | 109
Onyx | 110
Onyx | 111
Onyx | 112
Onyx | 113
Onyx | 114
Onyx | 115
Onyx | 116
Onyx | 117
Onyx | 118
Onyx | 119
Onyx | 120
Onyx | 121
Onyx | 122
Onyx | 123
Onyx | 124
Onyx | 125
Onyx | 126
Onyx | 127
Onyx | 128
Onyx | 129
Onyx | 130
Onyx | 131
Onyx | 132
Onyx | 133
Onyx | 134
Onyx | 135
Onyx | 136
Onyx | 137
Onyx | 138
Onyx | 139
Onyx | 140
Onyx | 141
Onyx | 142
Onyx | 143
Onyx | 144
Onyx | 145
Onyx | 146
Onyx | 147
Onyx | 148
Onyx | 149
Onyx | 150
Onyx | 151
Onyx | 152
Onyx | 153
Onyx | 154
Onyx | 155
Onyx | 156
Onyx | 157
Onyx | 158
Onyx | 159
Onyx | 160
Onyx | 161
Onyx | 162
Onyx | 163
Onyx | 164
Onyx | 165
Onyx | 166
Onyx | 167
Onyx | 168
Onyx | 169
Onyx | 170
Onyx | 171
Onyx | 172
Onyx | 173
Onyx | 174
Onyx | 175
Onyx | 176
Onyx | 177
Onyx | 178
Onyx | 179
Onyx | 180
Onyx | 181
Onyx | 182
Onyx | 183
Onyx | 184
Onyx | 185
Onyx | 186
Onyx | 187
Onyx | 188
Onyx | 189
Onyx | 190
Onyx | 191
Onyx | 192
Onyx | 193
Onyx | 194
Onyx | 195
Onyx | 196
Onyx | 197
Onyx | 198
Onyx | 199
Onyx | 200
Onyx | 201
Onyx | 202
Onyx | 203
Onyx | 204
Onyx | 205
Onyx | 206
Onyx | 207
Onyx | 208
Onyx | 209
Onyx | 210
Onyx | 211
Onyx | 212
Onyx | 213
Onyx | 214
Onyx | 215
Onyx | 216
Onyx | 217
Onyx | 218
Onyx | 219
Onyx | 220
Onyx | 221
Onyx | 222
Onyx | 223
Onyx | 224
Onyx | 225
Onyx | 226
Onyx | 227
Onyx | 228
Onyx | 229
Onyx | 230
Onyx | 231
Onyx | 232
Onyx | 233
Onyx | 234
Onyx | 235
Onyx | 236
Onyx | 237
Onyx | 238
Onyx | 239
Onyx | 240
Onyx | 241
Onyx | 242
Onyx | 243
Onyx | 244
Onyx | 245
Onyx | 246
Onyx | 247
Onyx | 248
Onyx | 249
Onyx | 250
Onyx | 251
Onyx | 252
Onyx | 253
Onyx | 254
Onyx | 255
Onyx | 256
Onyx | 257
Onyx | 258
Onyx | 259
Onyx | 260
Onyx | 261
Onyx | 262
Onyx | 263
Onyx | 264
Onyx | 265
Onyx | 266
Onyx | 267
Onyx | 268
Onyx | 269
Onyx | 270
Onyx | 271
Onyx | 272
Onyx | 273
Onyx | 274
Onyx | 275
Onyx | 276
Onyx | 277
Onyx | 278
Onyx | 279
Onyx | 280
Onyx | 281
Onyx | 282
Onyx | 283
Onyx | 284
Onyx | 285
Onyx | 286
Onyx | 287
Onyx | 288
Onyx | 289
Onyx | 290
Onyx | 291
Onyx | 292
Onyx | 293
Onyx | 294
Onyx | 295
Onyx | 296
Onyx | 297
Onyx | 298
Onyx | 299
Onyx | 300
Onyx | 301
Onyx | 302
Onyx | 303
Onyx | 304
Onyx | 305
Onyx | 306
Onyx | 307
Onyx | 308
Onyx | 309
Onyx | 310
Onyx | 311
Onyx | 312
Onyx | 313
Onyx | 314
Onyx | 315
Onyx | 316
Onyx | 317
Onyx | 318
Onyx | 319
Onyx | 320
Onyx | 321
Onyx | 322
Onyx | 323
Onyx | 324
Onyx | 325
Onyx | 326
Onyx | 327
Onyx | 328
Onyx | 329
Onyx | 330
Onyx | 331
Onyx | 332
Onyx | 333
Onyx | 334
Onyx | 335
Onyx | 336
Onyx | 337
Onyx | 338
Onyx | 339
Onyx | 340
Onyx | 341
Onyx | 342
Onyx | 343
Onyx | 344
Onyx | 345
Onyx | 346
Onyx | 347
Onyx | 348
Onyx | 349
Onyx | 350
Onyx | 351
Onyx | 352
Onyx | 353
Onyx | 354
Onyx | 355
Onyx | 356
Onyx | 357
Onyx | 358
Onyx | 359
Onyx | 360
Onyx | 361

## Polaris
TOPS & Flops
Polaris
Tops
|  |  | Flops | 100% manual inspection at Factory due to bad tactile feeling of Navi Key
S4(31.5) endangered due to: Navi Key; Bonding of FC; Unlimited Approvals (19 pending)
Display falls off during assambly
Sales Forecast decraesed, Fillrate pretty poor
Action Items
Blue marked comments: changes/updates from last protocol.
Project | N° | date | raised by | description | owner | target date | status | report / comments
Onyx | 1
Onyx | 2
Onyx | 3
Onyx | 4
Onyx | 5
Onyx | 6
Onyx | 7
Onyx | 8
Onyx | 9
Onyx | 10
Onyx | 11
Onyx | 12
Onyx | 13
Onyx | 14
Onyx | 15
Onyx | 16
Onyx | 18
Onyx | 19
Onyx | 20
Onyx | 21
Onyx | 22
Onyx | 23
Onyx | 24
Onyx | 25
Onyx | 26
Onyx | 27
Onyx | 28
Onyx | 29
Onyx | 30
Onyx | 31
Onyx | 32
Onyx | 33
Onyx | 34
Onyx | 35
Onyx | 36
Onyx | 37
Onyx | 38
Onyx | 39
Onyx | 40
Onyx | 41
Onyx | 42
Onyx | 43
Onyx | 44
Onyx | 45
Onyx | 46
Onyx | 47
Onyx | 48
Onyx | 49
Onyx | 50
Onyx | 51
Onyx | 52
Onyx | 53
Onyx | 54
Onyx | 55
Onyx | 56
Onyx | 57
Onyx | 58
Onyx | 59
Onyx | 60
Onyx | 61
Onyx | 62
Onyx | 63
Onyx | 64
Onyx | 65
Onyx | 66
Onyx | 67
Onyx | 68
Onyx | 69
Onyx | 70
Onyx | 71
Onyx | 72
Onyx | 73
Onyx | 74
Onyx | 75
Onyx | 76
Onyx | 77
Onyx | 78
Onyx | 79
Onyx | 80
Onyx | 81
Onyx | 82
Onyx | 83
Onyx | 84
Onyx | 85
Onyx | 86
Onyx | 87
Onyx | 88
Onyx | 89
Onyx | 90
Onyx | 91
Onyx | 92
Onyx | 93
Onyx | 94
Onyx | 95
Onyx | 96
Onyx | 97
Onyx | 98
Onyx | 99
Onyx | 100
Onyx | 101
Onyx | 102
Onyx | 103
Onyx | 104
Onyx | 105
Onyx | 106
Onyx | 107
Onyx | 108
Onyx | 109
Onyx | 110
Onyx | 111
Onyx | 112
Onyx | 113
Onyx | 114
Onyx | 115
Onyx | 116
Onyx | 117
Onyx | 118
Onyx | 119
Onyx | 120
Onyx | 121
Onyx | 122
Onyx | 123
Onyx | 124
Onyx | 125
Onyx | 126
Onyx | 127
Onyx | 128
Onyx | 129
Onyx | 130
Onyx | 131
Onyx | 132
Onyx | 133
Onyx | 134
Onyx | 135
Onyx | 136
Onyx | 137
Onyx | 138
Onyx | 139
Onyx | 140
Onyx | 141
Onyx | 142
Onyx | 143
Onyx | 144
Onyx | 145
Onyx | 146
Onyx | 147
Onyx | 148
Onyx | 149
Onyx | 150
Onyx | 151
Onyx | 152
Onyx | 153
Onyx | 154
Onyx | 155
Onyx | 156
Onyx | 157
Onyx | 158
Onyx | 159
Onyx | 160
Onyx | 161
Onyx | 162
Onyx | 163
Onyx | 164
Onyx | 165
Onyx | 166
Onyx | 167
Onyx | 168
Onyx | 169
Onyx | 170
Onyx | 171
Onyx | 172
Onyx | 173
Onyx | 174
Onyx | 175
Onyx | 176
Onyx | 177
Onyx | 178
Onyx | 179
Onyx | 180
Onyx | 181
Onyx | 182
Onyx | 183
Onyx | 184
Onyx | 185
Onyx | 186
Onyx | 187
Onyx | 188
Onyx | 189
Onyx | 190
Onyx | 191
Onyx | 192
Onyx | 193
Onyx | 194
Onyx | 195
Onyx | 196
Onyx | 197
Onyx | 198
Onyx | 199
Onyx | 200
Onyx | 201
Onyx | 202
Onyx | 203
Onyx | 204
Onyx | 205
Onyx | 206
Onyx | 207
Onyx | 208
Onyx | 209
Onyx | 210
Onyx | 211
Onyx | 212
Onyx | 213
Onyx | 214
Onyx | 215
Onyx | 216
Onyx | 217
Onyx | 218
Onyx | 219
Onyx | 220
Onyx | 221
Onyx | 222
Onyx | 223
Onyx | 224
Onyx | 225
Onyx | 226
Onyx | 227
Onyx | 228
Onyx | 229
Onyx | 230
Onyx | 231
Onyx | 232
Onyx | 233
Onyx | 234
Onyx | 235
Onyx | 236
Onyx | 237
Onyx | 238
Onyx | 239
Onyx | 240
Onyx | 241
Onyx | 242
Onyx | 243
Onyx | 244
Onyx | 245
Onyx | 246
Onyx | 247
Onyx | 248
Onyx | 249
Onyx | 250
Onyx | 251
Onyx | 252
Onyx | 253
Onyx | 254
Onyx | 255
Onyx | 256
Onyx | 257
Onyx | 258
Onyx | 259
Onyx | 260
Onyx | 261
Onyx | 262
Onyx | 263
Onyx | 264
Onyx | 265
Onyx | 266
Onyx | 267
Onyx | 268
Onyx | 269
Onyx | 270
Onyx | 271
Onyx | 272
Onyx | 273
Onyx | 274
Onyx | 275
Onyx | 276
Onyx | 277
Onyx | 278
Onyx | 279
Onyx | 280
Onyx | 281
Onyx | 282
Onyx | 283
Onyx | 284
Onyx | 285
Onyx | 286
Onyx | 287
Onyx | 288
Onyx | 289
Onyx | 290
Onyx | 291
Onyx | 292
Onyx | 293
Onyx | 294
Onyx | 295
Onyx | 296
Onyx | 297
Onyx | 298
Onyx | 299
Onyx | 300
Onyx | 301
Onyx | 302
Onyx | 303
Onyx | 304
Onyx | 305
Onyx | 306
Onyx | 307
Onyx | 308
Onyx | 309
Onyx | 310
Onyx | 311
Onyx | 312
Onyx | 313
Onyx | 314
Onyx | 315
Onyx | 316
Onyx | 317
Onyx | 318
Onyx | 319
Onyx | 320
Onyx | 321
Onyx | 322
Onyx | 323
Onyx | 324
Onyx | 325
Onyx | 326
Onyx | 327
Onyx | 328
Onyx | 329
Onyx | 330
Onyx | 331
Onyx | 332
Onyx | 333
Onyx | 334
Onyx | 335
Onyx | 336
Onyx | 337
Onyx | 338
Onyx | 339
Onyx | 340
Onyx | 341
Onyx | 342
Onyx | 343
Onyx | 344
Onyx | 345
Onyx | 346
Onyx | 347
Onyx | 348
Onyx | 349
Onyx | 350
Onyx | 351
Onyx | 352
Onyx | 353
Onyx | 354
Onyx | 355
Onyx | 356
Onyx | 357
Onyx | 358
Onyx | 359
Onyx | 360
Onyx | 361

## Silverstone
TOPS & Flops
Silverstone
|  |  | Tops | M_alpha is accepted by the Silverstone PD-Team on time (19.05.2006), the further product development is feasible
CRs are raised against SW-Platform for adaption of Featurelist for Silverstone (SW distributed new featurelist V2.0.1)
|  |  | Flops | Two stackup concepts are currently possible: 1. Platform Main PCB approach 2. Silverstone specific Main PCB (Pros: Length 2mm shorter, metal for front cover & keypad, battery in the south -> better handling, more flexibility for keypad design / Cons: antenna performance may be decreased copmared to concept 1, BB chamber must be split into BB- & PMU-part)
Action Items
Blue marked comments: changes/updates from last protocol.
Project | N° | date | raised by | description | owner | target date | status | report / comments
Onyx | 1 | 2006-05-22 | Kern | Provide design feedback on stackup concepts - if concept 2 (Silverstone Main PCB) decision must be considered by PD 1 step: Provide design feedback and initial alignement with MD, LPD, DigHW, EA on 23.05. (Kern) | Kern | 2006-06-24
Onyx | 2
Onyx | 3
Onyx | 4
Onyx | 5
Onyx | 6
Onyx | 7
Onyx | 8
Onyx | 9
Onyx | 10
Onyx | 11
Onyx | 12
Onyx | 13
Onyx | 14
Onyx | 15
Onyx | 16
Onyx | 18
Onyx | 19
Onyx | 20
Onyx | 21
Onyx | 22
Onyx | 23
Onyx | 24
Onyx | 25
Onyx | 26
Onyx | 27
Onyx | 28
Onyx | 29
Onyx | 30
Onyx | 31
Onyx | 32
Onyx | 33
Onyx | 34
Onyx | 35
Onyx | 36
Onyx | 37
Onyx | 38
Onyx | 39
Onyx | 40
Onyx | 41
Onyx | 42
Onyx | 43
Onyx | 44
Onyx | 45
Onyx | 46
Onyx | 47
Onyx | 48
Onyx | 49
Onyx | 50
Onyx | 51
Onyx | 52
Onyx | 53
Onyx | 54
Onyx | 55
Onyx | 56
Onyx | 57
Onyx | 58
Onyx | 59
Onyx | 60
Onyx | 61
Onyx | 62
Onyx | 63
Onyx | 64
Onyx | 65
Onyx | 66
Onyx | 67
Onyx | 68
Onyx | 69
Onyx | 70
Onyx | 71
Onyx | 72
Onyx | 73
Onyx | 74
Onyx | 75
Onyx | 76
Onyx | 77
Onyx | 78
Onyx | 79
Onyx | 80
Onyx | 81
Onyx | 82
Onyx | 83
Onyx | 84
Onyx | 85
Onyx | 86
Onyx | 87
Onyx | 88
Onyx | 89
Onyx | 90
Onyx | 91
Onyx | 92
Onyx | 93
Onyx | 94
Onyx | 95
Onyx | 96
Onyx | 97
Onyx | 98
Onyx | 99
Onyx | 100
Onyx | 101
Onyx | 102
Onyx | 103
Onyx | 104
Onyx | 105
Onyx | 106
Onyx | 107
Onyx | 108
Onyx | 109
Onyx | 110
Onyx | 111
Onyx | 112
Onyx | 113
Onyx | 114
Onyx | 115
Onyx | 116
Onyx | 117
Onyx | 118
Onyx | 119
Onyx | 120
Onyx | 121
Onyx | 122
Onyx | 123
Onyx | 124
Onyx | 125
Onyx | 126
Onyx | 127
Onyx | 128
Onyx | 129
Onyx | 130
Onyx | 131
Onyx | 132
Onyx | 133
Onyx | 134
Onyx | 135
Onyx | 136
Onyx | 137
Onyx | 138
Onyx | 139
Onyx | 140
Onyx | 141
Onyx | 142
Onyx | 143
Onyx | 144
Onyx | 145
Onyx | 146
Onyx | 147
Onyx | 148
Onyx | 149
Onyx | 150
Onyx | 151
Onyx | 152
Onyx | 153
Onyx | 154
Onyx | 155
Onyx | 156
Onyx | 157
Onyx | 158
Onyx | 159
Onyx | 160
Onyx | 161
Onyx | 162
Onyx | 163
Onyx | 164
Onyx | 165
Onyx | 166
Onyx | 167
Onyx | 168
Onyx | 169
Onyx | 170
Onyx | 171
Onyx | 172
Onyx | 173
Onyx | 174
Onyx | 175
Onyx | 176
Onyx | 177
Onyx | 178
Onyx | 179
Onyx | 180
Onyx | 181
Onyx | 182
Onyx | 183
Onyx | 184
Onyx | 185
Onyx | 186
Onyx | 187
Onyx | 188
Onyx | 189
Onyx | 190
Onyx | 191
Onyx | 192
Onyx | 193
Onyx | 194
Onyx | 195
Onyx | 196
Onyx | 197
Onyx | 198
Onyx | 199
Onyx | 200
Onyx | 201
Onyx | 202
Onyx | 203
Onyx | 204
Onyx | 205
Onyx | 206
Onyx | 207
Onyx | 208
Onyx | 209
Onyx | 210
Onyx | 211
Onyx | 212
Onyx | 213
Onyx | 214
Onyx | 215
Onyx | 216
Onyx | 217
Onyx | 218
Onyx | 219
Onyx | 220
Onyx | 221
Onyx | 222
Onyx | 223
Onyx | 224
Onyx | 225
Onyx | 226
Onyx | 227
Onyx | 228
Onyx | 229
Onyx | 230
Onyx | 231
Onyx | 232
Onyx | 233
Onyx | 234
Onyx | 235
Onyx | 236
Onyx | 237
Onyx | 238
Onyx | 239
Onyx | 240
Onyx | 241
Onyx | 242
Onyx | 243
Onyx | 244
Onyx | 245
Onyx | 246
Onyx | 247
Onyx | 248
Onyx | 249
Onyx | 250
Onyx | 251
Onyx | 252
Onyx | 253
Onyx | 254
Onyx | 255
Onyx | 256
Onyx | 257
Onyx | 258
Onyx | 259
Onyx | 260
Onyx | 261
Onyx | 262
Onyx | 263
Onyx | 264
Onyx | 265
Onyx | 266
Onyx | 267
Onyx | 268
Onyx | 269
Onyx | 270
Onyx | 271
Onyx | 272
Onyx | 273
Onyx | 274
Onyx | 275
Onyx | 276
Onyx | 277
Onyx | 278
Onyx | 279
Onyx | 280
Onyx | 281
Onyx | 282
Onyx | 283
Onyx | 284
Onyx | 285
Onyx | 286
Onyx | 287
Onyx | 288
Onyx | 289
Onyx | 290
Onyx | 291
Onyx | 292
Onyx | 293
Onyx | 294
Onyx | 295
Onyx | 296
Onyx | 297
Onyx | 298
Onyx | 299
Onyx | 300
Onyx | 301
Onyx | 302
Onyx | 303
Onyx | 304
Onyx | 305
Onyx | 306
Onyx | 307
Onyx | 308
Onyx | 309
Onyx | 310
Onyx | 311
Onyx | 312
Onyx | 313
Onyx | 314
Onyx | 315
Onyx | 316
Onyx | 317
Onyx | 318
Onyx | 319
Onyx | 320
Onyx | 321
Onyx | 322
Onyx | 323
Onyx | 324
Onyx | 325
Onyx | 326
Onyx | 327
Onyx | 328
Onyx | 329
Onyx | 330
Onyx | 331
Onyx | 332
Onyx | 333
Onyx | 334
Onyx | 335
Onyx | 336
Onyx | 337
Onyx | 338
Onyx | 339
Onyx | 340
Onyx | 341
Onyx | 342
Onyx | 343
Onyx | 344
Onyx | 345
Onyx | 346
Onyx | 347
Onyx | 348
Onyx | 349
Onyx | 350
Onyx | 351
Onyx | 352
Onyx | 353
Onyx | 354
Onyx | 355
Onyx | 356
Onyx | 357
Onyx | 358
Onyx | 359
Onyx | 360
Onyx | 361

## Swift
TOPS & Flops
Swift
Tops
Flops
Action Items
Blue marked comments: changes/updates from last protocol.
Project | N° | date | raised by | description | owner | target date | status | report / comments
Onyx | 1
Onyx | 2
Onyx | 3
Onyx | 4
Onyx | 5
Onyx | 6
Onyx | 7
Onyx | 8
Onyx | 9
Onyx | 10
Onyx | 11
Onyx | 12
Onyx | 13
Onyx | 14
Onyx | 15
Onyx | 16
Onyx | 18
Onyx | 19
Onyx | 20
Onyx | 21
Onyx | 22
Onyx | 23
Onyx | 24
Onyx | 25
Onyx | 26
Onyx | 27
Onyx | 28
Onyx | 29
Onyx | 30
Onyx | 31
Onyx | 32
Onyx | 33
Onyx | 34
Onyx | 35
Onyx | 36
Onyx | 37
Onyx | 38
Onyx | 39
Onyx | 40
Onyx | 41
Onyx | 42
Onyx | 43
Onyx | 44
Onyx | 45
Onyx | 46
Onyx | 47
Onyx | 48
Onyx | 49
Onyx | 50
Onyx | 51
Onyx | 52
Onyx | 53
Onyx | 54
Onyx | 55
Onyx | 56
Onyx | 57
Onyx | 58
Onyx | 59
Onyx | 60
Onyx | 61
Onyx | 62
Onyx | 63
Onyx | 64
Onyx | 65
Onyx | 66
Onyx | 67
Onyx | 68
Onyx | 69
Onyx | 70
Onyx | 71
Onyx | 72
Onyx | 73
Onyx | 74
Onyx | 75
Onyx | 76
Onyx | 77
Onyx | 78
Onyx | 79
Onyx | 80
Onyx | 81
Onyx | 82
Onyx | 83
Onyx | 84
Onyx | 85
Onyx | 86
Onyx | 87
Onyx | 88
Onyx | 89
Onyx | 90
Onyx | 91
Onyx | 92
Onyx | 93
Onyx | 94
Onyx | 95
Onyx | 96
Onyx | 97
Onyx | 98
Onyx | 99
Onyx | 100
Onyx | 101
Onyx | 102
Onyx | 103
Onyx | 104
Onyx | 105
Onyx | 106
Onyx | 107
Onyx | 108
Onyx | 109
Onyx | 110
Onyx | 111
Onyx | 112
Onyx | 113
Onyx | 114
Onyx | 115
Onyx | 116
Onyx | 117
Onyx | 118
Onyx | 119
Onyx | 120
Onyx | 121
Onyx | 122
Onyx | 123
Onyx | 124
Onyx | 125
Onyx | 126
Onyx | 127
Onyx | 128
Onyx | 129
Onyx | 130
Onyx | 131
Onyx | 132
Onyx | 133
Onyx | 134
Onyx | 135
Onyx | 136
Onyx | 137
Onyx | 138
Onyx | 139
Onyx | 140
Onyx | 141
Onyx | 142
Onyx | 143
Onyx | 144
Onyx | 145
Onyx | 146
Onyx | 147
Onyx | 148
Onyx | 149
Onyx | 150
Onyx | 151
Onyx | 152
Onyx | 153
Onyx | 154
Onyx | 155
Onyx | 156
Onyx | 157
Onyx | 158
Onyx | 159
Onyx | 160
Onyx | 161
Onyx | 162
Onyx | 163
Onyx | 164
Onyx | 165
Onyx | 166
Onyx | 167
Onyx | 168
Onyx | 169
Onyx | 170
Onyx | 171
Onyx | 172
Onyx | 173
Onyx | 174
Onyx | 175
Onyx | 176
Onyx | 177
Onyx | 178
Onyx | 179
Onyx | 180
Onyx | 181
Onyx | 182
Onyx | 183
Onyx | 184
Onyx | 185
Onyx | 186
Onyx | 187
Onyx | 188
Onyx | 189
Onyx | 190
Onyx | 191
Onyx | 192
Onyx | 193
Onyx | 194
Onyx | 195
Onyx | 196
Onyx | 197
Onyx | 198
Onyx | 199
Onyx | 200
Onyx | 201
Onyx | 202
Onyx | 203
Onyx | 204
Onyx | 205
Onyx | 206
Onyx | 207
Onyx | 208
Onyx | 209
Onyx | 210
Onyx | 211
Onyx | 212
Onyx | 213
Onyx | 214
Onyx | 215
Onyx | 216
Onyx | 217
Onyx | 218
Onyx | 219
Onyx | 220
Onyx | 221
Onyx | 222
Onyx | 223
Onyx | 224
Onyx | 225
Onyx | 226
Onyx | 227
Onyx | 228
Onyx | 229
Onyx | 230
Onyx | 231
Onyx | 232
Onyx | 233
Onyx | 234
Onyx | 235
Onyx | 236
Onyx | 237
Onyx | 238
Onyx | 239
Onyx | 240
Onyx | 241
Onyx | 242
Onyx | 243
Onyx | 244
Onyx | 245
Onyx | 246
Onyx | 247
Onyx | 248
Onyx | 249
Onyx | 250
Onyx | 251
Onyx | 252
Onyx | 253
Onyx | 254
Onyx | 255
Onyx | 256
Onyx | 257
Onyx | 258
Onyx | 259
Onyx | 260
Onyx | 261
Onyx | 262
Onyx | 263
Onyx | 264
Onyx | 265
Onyx | 266
Onyx | 267
Onyx | 268
Onyx | 269
Onyx | 270
Onyx | 271
Onyx | 272
Onyx | 273
Onyx | 274
Onyx | 275
Onyx | 276
Onyx | 277
Onyx | 278
Onyx | 279
Onyx | 280
Onyx | 281
Onyx | 282
Onyx | 283
Onyx | 284
Onyx | 285
Onyx | 286
Onyx | 287
Onyx | 288
Onyx | 289
Onyx | 290
Onyx | 291
Onyx | 292
Onyx | 293
Onyx | 294
Onyx | 295
Onyx | 296
Onyx | 297
Onyx | 298
Onyx | 299
Onyx | 300
Onyx | 301
Onyx | 302
Onyx | 303
Onyx | 304
Onyx | 305
Onyx | 306
Onyx | 307
Onyx | 308
Onyx | 309
Onyx | 310
Onyx | 311
Onyx | 312
Onyx | 313
Onyx | 314
Onyx | 315
Onyx | 316
Onyx | 317
Onyx | 318
Onyx | 319
Onyx | 320
Onyx | 321
Onyx | 322
Onyx | 323
Onyx | 324
Onyx | 325
Onyx | 326
Onyx | 327
Onyx | 328
Onyx | 329
Onyx | 330
Onyx | 331
Onyx | 332
Onyx | 333
Onyx | 334
Onyx | 335
Onyx | 336
Onyx | 337
Onyx | 338
Onyx | 339
Onyx | 340
Onyx | 341
Onyx | 342
Onyx | 343
Onyx | 344
Onyx | 345
Onyx | 346
Onyx | 347
Onyx | 348
Onyx | 349
Onyx | 350
Onyx | 351
Onyx | 352
Onyx | 353
Onyx | 354
Onyx | 355
Onyx | 356
Onyx | 357
Onyx | 358
Onyx | 359
Onyx | 360
Onyx | 361

## ALL
| Action Items | [6 empty] | Blue marked comments: changes/updates from last protocol.
Project | N° | date | raised by | desciption | owner | target date | status | report / comments
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!