## Projects fron A -> Z
TPM 2 weekly (CW even 04.04.06)
Tops | Flops
Products
Chameleon
M1 is delayed by two weeks due to new LC Volume and KHVatec
Diamond
Hawk (2nd presenter CDa)
- S0 declared | - LC volume drop (30% since M0)
- Fast MD prototypes received today | - M1 shift 31.03 to 06.04 tbc (LC volume drop; new quotes required; BOM and BC update required; MD issues)
Hydra
APAC DS signed by ST | Request for Hydra refresh (by only changing the Camera)
Jerry
A1+ PCB taped out 31.03.2006 | ASP status of Aries base SW still an open issue
Sprint 1 SW demo being presented to VF today | M1 not declared
Minos
Obsidian
FOT 23rd on all mechanical parts 3 days ahead of schedule. Generally all parts are looking good with exception of volume key and screw poles. Work is on-going | Ramp-up plan: September volume shifted: 213->209k (Sales request 225k) - Work ongoing for adapted RU plan for 850MHz and improvements
B1 PCB mounting in Klf 3rd April after delay due to strike. B1 Final assembly in Klf CW15
Great Sales-feedback from LAM and 850MHz version is therefore requested by CPM
Philippe (2nd presenter CDa)
- Type approval started | - LC volume drop (about 50% since M1)
- Tool updates for mass production parts ongoing. Approval of parts and tools for in CW14. | - BOM increase compared to M1 (about 10%; new exchange rates; increased prices for MD parts and tools; reduced LC volume)
Polaris (1st presenter TNe)
Informel TMO Approval received (Official paper still pending) | No Further orders received, Production Qty. Likely to be reduced
Approval Orange Poland and Amena expected 7-Apr | E+ Approval still pending, 2 bugs reported depending on E+ Test Enviroment
All but on O2 Bugs fixed, Approval expected 7-Apr. | PTC Poland Approval atill pending, Bug reported likely to depend on SAT Application
Swift
Swift Production will start on 03.04.2006 with following limitations: - rework of soldering in KLF - rework of ALU front cover at Perlos | S3 not declared because of: - too many high prio SW bugs - soldering problems of SIM &SD card reader - overlapping ALU front cover - delayed BOM update
Missing KHVatec deliveries endangers TTV - Selection and qualification of second source for KHVatec parts
HW Program Manager
Topic 1
Topic 2
Topic 3
Wireless Connectivity Program Manager
Bluetooth
CR 2022 for Orange / Polaris( Swift and Philippe) : yesterday "Implement Popup before receive objects via Bluetooth" regardless of our argumentation send out. Is it lost or is it promised to Orange?
Bluetooth Spec Version 1.1: - V1.1 deprecated for 9. Aug. 07, QCT Projects mandatory to support min. V1.2.
IFX Bluetooth Second Chipset/SW supplier support: - What time is Management Meeting, Preparation?
DVB-H
New timeline for Ameythis: - necessary for supplier selection and to complete development concept definition.
Wireless LAN
Company Sykepe not motivated to support: - expects a product story for Thin Phone Client before they support us.
SW Program Manager
SG2 Release Minos / Hydra
SG2 Release Swift
S3 delayed in a range of 1 week
Difficult clarification with QA about DS criterias, progress expected tonight
Gemstone Apoxi Platform
Tim Hagemann started as PL SW | Seamless cooperation with all suppliers after timeout not successfull.
1st sprint planning ongoing
TPM Platform
Topic 1
Topic 2
Topic 3
For line break within a cell pls. press 'Alt' + 'Enter'