## Projects fron Z -> A
TPM2 weekly (CW 15 11.04.06) - 2.5G/3G IFX
Tops | Flops
TPM Platform
Topic 1
Topic 2
Topic 3
TPM SW
SG2 Release Minos / Hydra
SG2 Release Swift
Gemstone Apoxi Platform
TPM Wireless Connectivity
Bluetooth
CR 2022 for Orange / Swift and Philippe : - Our argumentation and VDF specific solution proposed to Orange for "Implement Popup before receive objects via Bluetooth" waiting for Orange feedback.
Bluetooth FM Radio : - Due to the 0.4 pitch support first in 2008 in production, prefered supplier TI will be requested today to offer BRF6350 BGA 0.5 mm (only WSP 0.4).
Apoxi Requirements : - Requirement Engineering need to be improved, no aggrement to the requirement spec format and change tracking, uncoordinated TPS and R&D interfaces
DVB-H
Wireless LAN
TPM HW
Topic 1
Topic 2
Topic 3
Products
Swift (1st presentation)
S3-SW declared last Friday | Re-oldering process and material availability limitting production in KW15 to 3k Re-soldering process will limit production in KW16 (current plan is 9,5k)
Material status - Phone and Battery safety documentation complete - STM qualification: risk releases can be done - Avago PA: no volume limitation any more regarding Ramp-Up plan | No offer from Catcher to produce Base Upper Case as second source to KHVatec (statement: part is too complex), BYD now asked to make quote
No-ID Production ongoing, several problems solved (Vibra blocking, Flex cutting, screwing process) and counter measures already implemented | Streaming Feature not yet committed by SW before Step2, impact on TTV
Fast-Track implementation timeline endangered, technical feasability questioned
Polaris
TMO Approval granted | Problem with Cover Front occured again; CF Frame released after drop test; Analysis ongoing; RR estimation of QM: 8% Worst Case
Amena (Orange ESP) Approval granted | SCM FTR posponed due to Problems with pys. Dimension of Cover Front
O2 Approval granted
Orange Poland Approval granted
E+ Final Approval granted
Overall Order Situation increasing
Philippe
- MD part tool updates for mass production ongoing and all tools are expected to be ready 18.04.06 | - Type approval time line endangered. ST-MO strategy not aligned with SW. Bug reports in CQ have not been processed. SW platform request CR to bring SW in compliance with the valid GCF version (3.21).
- Mechanical corrections not finally tested until after start of ramp-up. Risk assesment will be made based on current knowledge and maintained as new results become available.
Obsidian
B1.1 assembly ongoing with good results. No major difficulties or surprises. | The Swift team have been ordered not to correct SW bugs in Shadow files. Mening no re-use of SW in shodow files and all debugging and corrections must be done over again. Does not make sense not to follow the platform approach.
Review of FOT-status conducted with CPM.
GPM / TMO approval have been agreed to be made within 8 weeks and within the current Obsidian schedule, sample availabillity and SW plans. Further planning ongoing for the remaining approvals.
850 planning OK except for RU
Minos
Jerry
M1 declared on PBR 07.04.06
VF very happy with current performance. VF quote: "... greatly increased the confidence of myself and the team that we are on track in the Jerry SW development ..."
Agreement regarding 2nd keypad supplier reached
A1+ production on schedule for tomorrow and Thursday in KLF
Hydra
E-Plus approved SVN31
Hawk
- Tooling ongoing for B1+ parts | - M1 still open (BOM update missing due to severe issues in SP regarding price updates and system problems)
- Trade-off between rotating camera lid and flash light has compromised performance of flash light. In agreement with CPM.
Diamond
* M0-Target on 21th April (OPC preparation till when?) | * SW Featurelist (APOXI) preparation still ongoing
* New DS Date in 04/2007 | * SW Scheudle (APOXI) vs. Mapping on Project schedule still under evaluation
* Fixation of Endcaps still under evaluation - find alternative soluitons (screwing solution critical for factory)
Chameleon
B1 TO done | M1 delayed by two weeks, due to the decision KHVatec to backup with a second supplier! (DynaCast negotiation must be finished at 14.04.2006, to reduce the delay for B1+ by one week!)
For line break within a cell pls. press 'Alt' + 'Enter'