## Projects fron A -> Z
TPM weekly (CW 16 18.04.06) - 2.5G/3G IFX
Tops | Flops
Products
Chameleon
TO done on 10.04.2006 (two day earlier as planed). | SP & LCM1 ( QM PRO ) have not signed the M1 declaration up to now! ( SP: New BOM calculation is under implementation? / QM PRO has not all tooling plans received from DynaCast)
B1 First Shot will start tomorrow
Diamond
* SW: sprint-content-description needs to be fixed * SW: sprint planning needs to be adapted to Diamond schedule * fixation of end-caps needs to be solved w/o Design-Changes
Hawk (1st presenter)
- Outstanding issues on BOM clarified for M1 declaration.
Hydra
Environmental test looks good for Golden variant. | Still no RR estimated for SVN30. Blocking QA for signing APAC DS
New CR for re-branding SL75 due to low sales figures.
Jerry
Fixtures for A1+ testing in KLF arrived late, only 22 manually rebooted PCB's sent to AAL before Easter. The rest will be sent today or tomorrow.
Minos
Obsidian
‘- B1 prototype series with 380 units. Remaining in CW16. LCM have reported that the mechanics is great and very mature compared to normal B1 samples | ‘- Customer test problems due to failures on fixtures - Volume key is not working due to incorrect spec / wiring on PCB
- The Swift team have been ordered not to correct SW bugs in Shadow files. Mening no re-use of SW in shadow files and all debugging and corrections must be done over again. Does not make sense not to follow the platform approach
Philippe (1st presenter)
- Agreement on support from SW platform for solving type approval (GCF) bugs. | - Housing tools send later than scheduled from tool maker in Hong Kong to Nolato in Sweden. Nolato has provide plan to catch up for ramp-up deliveries. Impact: Later verification of tool changes in quality/environmental test.
- Mechanical corrections not finally tested until after start of ramp-up. Risk assesment will be made based on current knowledge and maintained as new results become available.
Polaris
Automatic Assembly Line up and running (optimization ongoing) | Screw Boss Problem still pending
Silverstone
PD-Team Kickoff done succesfully | M_alpha was declared by CM, but Malpha-status not reached -> New Malpha-date planned 19.05.2006
Very first DS-indication: 15.05.07 Basis: Alignment with MD on basis of standard-plan for Class3-products | No concept at all available to get speaker and microphone sealed. Taskforce with MD and BB to be established
Nano IO can't be sealed => Complete new IO-concept needed, Taskforce to be established
700h Standby-time as goal, currently no battery with enough capacity available
MD and BB on holiday this week => no progress on stackup/mechanics
PL-SW not yet nominated
Swift
Soldering problem understood now | 10 of the 14 DS Blocker are in the same area (OBSV), freeze period deadline is today
material problem of SIM card and SD card reader, SIM card reader bending under temperature
Production started again after Thursday stop | kepady glueing environmental tests - B2 tests have been better than test of pilot parts
HW Program Manager
Topic 1
Topic 2
Topic 3
Wireless Connectivity Program Manager
Bluetooth
DVB-H
Wireless LAN
SW Program Manager
SG2 Release Minos / Hydra
SG2 Release Swift
Gemstone Apoxi Platform
For line break within a cell pls. press 'Alt' + 'Enter'