## Projects fron Z -> A
TPM2 weekly (CW 17 25.04.06) - 2.5G/3G IFX
Tops | Flops
SW Program Manager
SG2 Release Minos / Hydra
SVN 34 delivered with TMO Bug Fixes, Driver for STM and Spansion Flash | New bugs from Phillipe caused by new connectivity component (Nano IO)
nCCPI is going down as expected to acchieve S4 by end of May
SG2 Release Swift
(see report Swift)
Gemstone Apoxi Platform
M0 Diamond achieved by 21.4. in time | IFX canceled their participation in Annex R&D review on 26.4.
Teleca TLA signed, 1st code delivery by today | Only rough codesize estimates available. In worst case calculation Silverstone and Kaolin need additional Flash memory.
Wireless Connectivity Program Manager
Bluetooth
Bluetooth FM Radio: - 4th May decision go/no from prefered solution TI BRF6350 in BGA 0.5 mm (now only WSP 0.4mm). - 8th May decision IFX to support third party BT / BT FMR in Apoxi.
DVB-H
Due to shift of Amethyst from 6/07 to 2/08 adjustment in DVB-H 95: Processing to re-consider solutions
Wireless LAN
HW Program Manager
Topic 1
Topic 2
Topic 3
Products
1'st presenter Swift
"Video Streaming" SW bug solution worked out, DS SW will be provided on Thursday | Agreement regarding keypad glueing for DS to be made between LCM, MD and QM-HW; first test result from plasma activation and re-pressing in operator logo assembly available
ALU cover overlap solution verified and accepted today by MD and SCM QM at Peros side in Hungary | Open B2B connectors found in APP (Auspackprüfung); reason is reduced thickness of Flex stiffener; counter measure in implementation is additional tape on B2B connector
Lastest drop tests of non re-soldered PCBs showed 0% return rate, verification of these "good" test results requested by TPM by doing second run of drop test with non re-soldered PCBs, final results available tomorrow | Current Ramp Up volume endangered because of shortage of Härter ALU cover; implementation of additional milling tooling not in time; impact on ramp-up volume to be worked out with Perlos until Thursday; escalation ongoing together with SCM-QM and SP
Silverstone
New Malpha-date planned 19.05.2006 (main open issues: water proofed acoustic, IO & 700h Stand By)
Polaris
Front Cover bonding insufficient: potential causes have not been confirmed by supplier. Latest drop tests showed no improvement. Expert team (MD, SD QM, 3M gluing experts, Lumberg, 6Sigma expert) installed at CCC to find root cause and stabilise/ improve process.
Navi ring tactility problem: keypad apparently out of spec. -> 100% inspection at line installed. Short-term measures are being analysed.
Philippe
All molding tools are at Nolato in Sweden and molding for ramp-up has started. | - Notice received about delay of lower case delivery due to lack of vibra. Estimated delay of 4 working days. Impact on early DS. Supply chain has been requested to push vibra supplier.
- Potential delay of GCF approval due to open SW bugs. Bugs expected to be fixed in SW release SVN37 on 4th May. Impact on early DS. Corrective actions to be clarified.
- Mechanical corrections not finally tested until after start of ramp-up. Risk assesment will be made based on current knowledge and maintained as new results become available.
Obsidian
Second half of the B1 test series in Klf. is running after 4 days of problem solving. Comnion delivered SW update for Bright 6PL RF this morning, 25th April | Obsidian LAM 850 resulting budget in PMC is 935k, which is almost 400k above original budget Hereof, 50k reduction on material. Total amount of hours is 6329k, Hereof HW 685hours, SW 1366hours, QM including Field test 1340hours and ST including Operator approval 2038hours. Serious improvements necessary
Platform approach and re-use of SW requested, including that Platform CR’s are corrected on the (9) shadow files. Separate product CR’s should of-course be handled separately for each project. Same problem on GCF, etc. Again the platform approach should be used for products like Obsidian and Cameleon -> Keep topic for next meeting!
Minos
+ Vodafone gave unlimited release for SVN31
Jerry
Sprint 2 SW coming in from SISL on schedule, demo to VF next week
A1+ HW test on-going. RF performance equal to or better than Aries. Audio idle noise seen on A1 solved with latest Twigo PMU - Old firmware version used in A1.
Hydra
QM signed APAC DS | Demand for China market "0"
SL78 target for SOP mid of July planned and reachable
VF approved SVN31 (many variants will be upgraded)
Price reduction of Pluto display 14% (with effect from July 06)
Environmental test of GOLD passed.
Hawk
- Environmental tests ongoing on early prototypes.
Diamond
* M0-declaration done on 21th April on time | * SW: Memory estimation for M0 described not to fit into 64MB as planned. Needs to be re-checked (support needed from U.Geiger)
* BB/SW: Check needed flash-configurations in the context of 128 MB needed for APOXI; plan appropriate driver develpoment for Gemstone APOXI (support needed by Hänsel/Geiger)
* Design: Info Area (virtual Display) needs to be re-designed - Info from Design Mo 24th April
* Design: Assumption of B2B (70pin) not confirmed from supplier - evaluation of Design consequences running (support needed from K. Krösen)
* EA: confidence-level for closed-mode-telephony is 70% influenced by SAR value (support needed from J. Bauregger)
Chameleon
First Shot started on 19.04.2006. PCB is working in Service mode. RFT working | M1 declared by PD but refused in PBR due to BOM to high
FSP and Inline Adapter are delayed by 5 days. B1 Main run SMT should start Thursday
- potential SW Problem: AFC adjustement not working in Obsidian. New SW tommorow
For line break within a cell pls. press 'Alt' + 'Enter'