## Projects fron A -> Z
TPM weekly (CW 18 02.05.06) - 2.5G/3G IFX
Tops | Flops
Products
Chameleon
RF adjustement (SW) now working; FKT, AS working. Phone is switching on in Service and normal mode | Inline Testadapter for FBCs are delayed until 03.05.2006;MDF Stencil sticks still in custom; Tool for Antenna Carrier is delayed FOT Parts at Nolato until 03.05.2006; All Mechanic Parts here in KLF on 04.05.06,
PBR on Friday will decide on the further ongoing from Marketing point of view
Diamond
* antenna performance could be influenced by necessary mechanical changes (radius of flex and additional way to snap-in the slider); new samples ordered; EA will re-measure then
* SW S0 shifted to 02.06.2006 (due to many feasibility studies have to be performed)
* two release-buttons currently in mechanical concept but only one button requested by CPM
Hawk
- Hard tools for housing parts nearly ready for B1+ production
Hydra
Slpash screen (for SL78) will be in from SVN37. | SEID now suddently admitted that they have image sticking on their display :-(. Leadtime for new display is 7month.
Planning in PMC for SL78 will be done today. | BOM's for Gold variant not uploaded for supplier safe.
Jerry
A1+ testing on-going. No issues found. Only very minor corrections for B1. B1 tape-out on schedule for 08.05.06. | Production test issue with Spansion flash still open. Not sure that it is the same problem as seen on other products using the Spansion flash.
Hand-over to BEJ in progress in all functional areas. Management hand-over in CW19.
Sprint 2 on schedule. Demo to VF end of this wek.
100% mech. data on schedule last week.
Minos
* S4 prepared for 26.05.2006 (only platform SW, ST, PQA missing)
Obsidian (1st presenter)
Ramp-up planning workshop undertaken with Draft result where most requirements from CPM / Sales on MAN, LAM, SSMC, Mex. DS can be fulfilled. (To be Confirmed.!) | Continuous struggle on getting second half of the B1 test series through Klf. Several SW and test problems have been slowing down progress. Expect to have this running 2nd May
Most environmental tests run on Obsidian with only limited number of fails (one critical)
Platform approach and re-use of SW requested, including that Platform CR’s are corrected on the (9) shadow files. Separate product CR’s should of-course be handled separately for each project. Same problem on GCF, etc. Again the platform approach should be used for products like Obsidian and Cameleon -> Topic from last meeting. AI: UGe to clarify for reason why the process doesn't work correct.
Philippe
- Pre-pilot series of 500 NO-ID phones based on B2 parts performed in factory with success. | - Verification of mechanical changes not finalised until after start of ramp-up. Assesment for risk release of parts will be done.
- All housing tools in place at Nolato. | - Failed quality test (150cm drop test, 30cm drop test, necklace hook test)
- 12.000 parts for pilot- and ramp-up molded and painted and ready for preassembly | - S3 delayed
- Two SW DS blockers under investigation. To be fixed until 3rd of May
- Q-department might not declare DS due to open mechanical issues.
Polaris
Screw Bosses release: - There is a bonding problem, which is acceptable for a limited time but no production stop neccessary. Additional 3% RR estimated. - Visit at supplier showed process issues, which have been turned off. Verification in progress.
Silverstone (2nd presenter)
Not mature Malpha leads to higher efforts in mechanical design -> resource situation currrently not sufficient, clarification with MD dept. Krösen/Schrage ongoing RISK: late availablity of mature stack up leads to delay for principle design decision and design acceptance test >> M0 delay
Swift
DS declared by SW and ST for SW SR4 (SVN06); QM-SW expected for today latest tomorrow | Limitation of Härter ALU cover in ramp up -> milling tools too late and yield rates lower than expected; Härter presented new ramp up volumes which are trusted now by SCM QM
SW released by customer for several retail variants in CW 18 (Bulgaria, Greece, Ukraine, Russia) | May volume reduced to 80k (with risk of 25% -> 60k)
Project has declared S3 | SW SR5 (incl. Orange and TMO) -> still 16 open CQ; OTC planned for tomorrow
HW Program Manager
Topic 1
Topic 2
Topic 3
Wireless Connectivity Program Manager
Bluetooth
DVB-H
Wireless LAN
SW Program Manager
SG2 Release Minos / Hydra
SG2 Release Swift
Gemstone Apoxi Platform
For line break within a cell pls. press 'Alt' + 'Enter'