## Projects fron Z -> A
TPM weekly (CW 19 09.05.06) - 2.5G/3G IFX
Tops | Flops
SW Program Manager
SG2 Release Minos / Hydra
SG2 Release Swift
Gemstone Apoxi Platform
Wireless Connectivity Program Manager
Bluetooth
DVB-H
Wireless LAN
HW Program Manager
Topic 1
Topic 2
Topic 3
Products
Swift
DS declared on 03.05.2006 by OPC and confirmed by CPM (Phil Mulholland) | May volume limitted to 78k (with risk of 25%) due to material shortage of ALU cover (Härter)
SW realeses for several retail variants, E-Plus and most likely TMO | Orange SW approval delayed because of remaining blocking bugs; SW release shifted to SR6 which means 2 weeks delay compared to planning
Step2 SW shifted by 4 weeks to 07.07.2006
Silverstone
First planning workshop done with most parties (Pre M0 status) -> DS planned on 23.05.2007 | High load in MD department, new resources late announced (on 09.05. - TBC) => higher risk on M_alpha finalization
Polaris
SW S4 Maturity reached (nCCPI 35k) | 100% manual inspection at Factory due to bad tactile feeling of Navi Key
Bonding Problem: Most recent Parts show much better performance than before (RR 1,5%). Two further improvments pending, exp. CW20
Philippe (1st presenter)
- Potentials for early DS under clarification. Opportunity for CW20 / CW21. | - Failed butter test. Blocking from PL QM point of view for S3 and hence DS
- S3 delayed due to failures in environmental test (butter test)
- Current available SW SVN37 not GCF compliant. Currently no countries has confirmed to take deliveries w/o GCF compliance. Solutions expected with SVN38 scheduled for 10.05.06
Obsidian
B1 run completed and all samples distributed. | Delay on environmental test on HW configuration with 2. source components, meaning late qualification of these components.
Environmental test on B1 concluded with good result. No critical problems detected. Mechanical adjustments are defined and tool modification will be initiated this week. | 850 MHz SW support delaid from Comnion. RF test can not be completed in time and may impact S2 for Obsidian LAM.
FM radio is running in HW and in SW.
Minos
Jerry
B1 tape-out 08.05.2006 - 2 days ahead of schedule | Discussion still on-going if B1 plastic parts will be producted at Perlos or at toolmaker.
Hand-over to BEJ wil be finished end of this week
Hydra
Finally the TTD is signed from EPSON side. | KHVatec claims higher prices for slider of the GOLD variant (may endanger the PS)
As soon as the signed document is in our position BB signs the S4. | So far no specific demands on SL78 (China declined, rest of APAC awaiting)
Hawk (1st presenter)
- Problems at toolmaker to get the tools for upper case and lower case up and running. Currently delay of 4 days. Options for recovery being clarified
Diamond
* MD: release-button(s): two currently in mechanical concept but only one button requested by CPM plus geometry and visibility of release part on slider not accepted by Design - currently no solution - critical for S0 - support K.Krösen needed
* MD: New: Removable Displaylense above "Info-Schlitz / partial Display" requested by Design - currently no solution - critical for S0 - support from K.Krösen needed
* SW: transparency in SW missing: documentations (feature incl. Usecases) , Maintainance of Featurelist updates missing, no overview of crititcal components, no content description of sprints, high level plannen till M1 missing…… support form G. Fässler needed
Chameleon
First Call done | PBR stopped today Chameleon : Reasons: low profits shown in business case (combination of costs, volumes, etc.)
First drop tests in MD shows a good behaviour
For line break within a cell pls. press 'Alt' + 'Enter'