## Projects fron A -> Z
TPM weekly (CW 20 16.05.06) - 2.5G/3G IFX
Tops | Flops
Products
Diamond (A.Betting)
* SW high level planning from now till M1 still under evaluation(incl. All necessarc documentations, feasibility studys and plannings) - answer promside 17th May (Fässler)
* SW Feature-Documentation (e.g. Featurelist or/and Feature Break Down list, ) still under evaluation - QM does not accept to remove Featurelist and go for FBS only - answer promised till 18th May (Geiger)
* MD: Release Button solution still under evaluation - fully MD support available - Design/CPM/MD/TPM Meeting on 16th May - target agreement on final solution (critical for S0-Milestone)
Hawk (C. Dalmose / J. Schmitz)
- Delay of 1 week (6 working days) by tool maker due to technical problems in the preparations of the tools for the upper case. Ready 15.06.06. Activities to recover time ongoing. Potential risk on DS due to the tight time schedule. Assesment to be done when quality of the first molded parts is known.
Hydra (K. Christiansen)
S4 declared for dHW, LCM3 ......... | SL78 stopped because of negative market feed-back. Would assume that marketing would perform such things before starting activities (waste of money)
SG2 problem from UMCi not an issue for Hydra. Stay with devices from ALTIS. | All activities (sales / production) stopped in China.
Jerry (L. Bonde)
Handover finished. Full resposibility for driving the project now in BEJ.
Minos (U. Barner)
Obsidian (T. Stokholm)
B1+ Mechanical data shipped 11th May according to schedule | Obsidian LAM 850, M1 target date 10th May missed due SCM (missing confirmation from suppliers ) and ST (missing operator requirements) – New target date is 18th May
B1+ PCB data ready for shipment 17th May according to schedule
SW expect to be able to declare S25 ahead of schedule
Philippe (C. Dalmose / J. Schmitz)
- S3 declared (delayed from 20.04.06 due to failure in butter test (Quality test)) | - Verification of mechanical changes not finalised until after start of ramp-up. Assesment for risk release of parts will be done.
- Opportunity for early delivery of phones with SW SVN37 to countries (Czech, Ukraine) that does not need GCF approval. (Full GCF and Java compliance not fulfilled until SVN38) | - Correction for butter test failure implemented as running change. Q-department assess an added return rate of 2% until solution is implemented.
- Opportunity for DS on 24th May (original 29th May)
- R&TTE approval achieved
- Java compliance confirmed by ST-SW BEJ (self-certification)
Polaris (T. Neumann)
SW S4 Maturity reached (nCCPI 27k) | 100% manual inspection at Factory due to bad tactile feeling of Navi Key
Bonding Problem: Most recent Parts show much better performance than before (RR 1,5%). Two further improvments pending, exp. CW20 | S4(31.5) endangered due to: Navi Key; Bonding of FC; Unlimited Approvals (19 pending)
Silverstone (1st presenter) (R. Kern)
M_alpha finalization on 19.05.06 at risk: > Selection of acoustic concept to reach GSM-spec AND min. IPx7 not finalized / impact on device size to be considered !!! > No final sealing & screwing concept available / impact on device size to be considered !!! > Risk that platform concept can not be used due to necessity for internal Nano I/O
Swift (J. Kockmann)
SW approvals for E- Plus and several retail variants (Germany, Greece, Russia, Bulgaria, Ukraine) | May volume reduced again by 14k to 39k due to missing LEDs and ALU cover @ Perlos; this issue will be escalated by P. Mulholland in Sales-Delivery meeting tomorrow
Step2 DS on 07.07.2006 not accepted by extended management board; C. Joos will clarify in a telco with R&D SW
TMO global and Orange global expected with SVN11 now; SVN11 to be provided tomorrow
HW Program Manager (D. Hänsel)
Topic 1
Topic 2
Topic 3
Wireless Connectivity Program Manager (H. Karacelik)
Bluetooth
BT/FMR SW porting in QCT Platform started yesterday, Monolithic BT/FMR Implemantation in Koala as lead project planed. | Necessary BT FMR Measurement equipment not available: e.g. Audio-Analyzer UPL, EDR Tester CBT
DVB-H
Necassary DVB-H Measurement equipment not available, Gap between necessary efforts and current planning.
Wireless LAN
SW Program Manager (U. Geiger)
SG2 Release Minos / Hydra
SG2 Release Swift
Gemstone Apoxi Platform
For line break within a cell pls. press 'Alt' + 'Enter'