## CA M0
Conformance assessment milestone M0 |  | Jerry |  |  |  | Major
Additional risks, miscellaneous |  | Name of PPL |  |  |  | Major
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
Very tight time schedule, specially for mechanics. High risk that problems caused by mechanical solutions will delay DS | # Perform system and design FMEAs in order to identify potential failures and define reasonable corrective actions # perform basic tests in Beijing lab in order to get test results at very short notice | MD/QM | ongoing |  | Delay on DS | 2
SW team setup with several sites involved | Spent special effort to coordinate activities | PLT/SW PL | ongoing |  |  | 2
PV planning showing dedicated ressources on department level is missing | To be updated | All PPLs | S0 |  |  | 2
M0 document is missing | M1 draft version will be updated from all PPLs | PPLs | 03/16/2006 |  |  | 1
Radio | M.Brammer |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
1
EMC antenna | Arne Bisgaard Kristensen |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
Antenna mockup 2 is depending on FDM parts to be delivered by end of March |  | Christian P. Nielsen |  |  |  | 1
Digital and mixed signal HW | Flemming Bach Kristensen |  |  |  |  | Major
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
Potential acoustical leakage on speaker/back volume | see MD | Christian P. Nielsen |  |  |  | 2
Software | Yang Yong Qiang |  |  |  |  | Major
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
SW requirements from VF difficult to get closed. Replanning might be necessary | To clarify SW requirements with VF. For those requirements, which cannot be clarified finally yet the timeline for implementation (what sprint ?) and possible impact on other sprints or SW features must be identyfied and communicated in the M1 declaration | A.Broeze | 3/27 (for M1 declaration planned on 3/31) |  | Ressource and time line risk for unknown workpackages | 2
Signal Processing | Allan Hansen |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
1
Mechanics | Christian P. Nielsen/Fu Ling Pin |  |  |  |  | Major
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
On/off key possible problems: # Microswitch for on/off key might be damaged during drops (shear off) # Button will not switch on/off the phone due to tolerances | # Perform design FMEA to identify reasonable measures # Tolerance analysis | Christian P. Nielsen/Fu Lin Ping | 3/27 (for M1 declaration planned on 3/31) |  | Product quality injured | 2
Potential acoustical leakage on speaker/back volume | # Perform design FMEA to identify reasonable measures # to finalize concept | Christian P. Nielsen/Fu Lin Ping | 3/27 (for M1 declaration planned on 3/31) |  | Product quality injured | 2
Slighter key (keypad lock) possible problems: # slider breakage during drop test # un-intended activation due to external magnetic force # activated in pocket due to low activation force # unstable function due to magnetic tolerance | Perform design FMEA to identify reasonable measures | Christian P. Nielsen/Fu Lin Ping | 3/27 (for M1 declaration planned on 3/31) |  | Product quality injured | 2
Function keys possible problems: # poor tactile feeling # light leakage around the decoration part | Perform design FMEA to identify reasonable measures | Christian P. Nielsen/Fu Lin Ping | 3/27 (for M1 declaration planned on 3/31) |  | Product quality injured | 2
Possible problem with MDF due to limited glueing surface area in upper part | to be checked during environmental tests | Christian P. Nielsen/Fu Lin Ping/T.Bartel | B1 |  | Product quality injured | 2
Keypad suppliers not yet choosen |  | Dong Xia (SP) | week 11 |  |  | 2
Uneven light illumination/distribution on simply keys | # Not clarified whether a SW simulation is possible at Perlos on time # To provide an additional LED in simply key area --> decision is needed | Christian P. Nielsen/Fu Lin Ping | M1 |  | Product quality injured | 2
Possible rattling on soft keys and function keys | # extend rubber keypad in order to apply pre-tension | Christian P.Nielsen/Fu Lin Ping | M1 |  | Product quality injured | 2
Layout/Production Data | Randi Bak, Dorte Nielsen |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
1
Procurement Engineering | Mariann Svendsen |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
There isn't a correct full part list in SAP PLM. BOM is calculated on partlist made by SP/PE | MD & dHW has to create and release an updated full part list | Poul Erik Rask/Christian P. Nielsen | 03/14/2006 |  |  | 1
SCM Production technology | Katharina Hilker |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
Broken receiver snap hooks | Check if BMS will use the semi-automatic assembly device because the manual assembly leads to broken snap-hooks | Bonde/Broeze/Song | M1 |  |  | 1
Round VF label has to be glued on battery cover | Make-Or-Buy-Decision open | Bonde/Broeze/Song | M1 |  |  | 1
Display rotation by 180 degree: tape on earpiece needed; in-house assembly because earpiece is also used in other projects | Tolerance calculation initiated: If possible avoid tape to save money | Christian P. Nielsen/Fu Lin Ping | 3/27 (for M1 declaration planned on 3/31) |  |  | 1
Material availability/SDQM | Thomas Limbach |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
1
Quality Management | Thomas Bartel |  |  |  |  | Major
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
Possible problem with MDF due to limited glueing surface area in upper part --> see MD | to be checked during environmental tests | Christian P. Nielsen/Fu Lin Ping/T.Bartel | B1 |  |  | 2
System Test | Yang Li (ST1), Wie Xue Kai (ST2) |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
1
Service | Heinz-Gerd Voelker |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
SWUOTA implementation is not clarified |  | Bonde/Broeze/Song | 3/27 (for M1 declaration planned on 3/31) |  |  | 1
Accessories | Thorsten Lange |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
1
1)e.g.: Time to Market delay; Returnrate rise; Additional R&D effort
2): Milestone assessment: Issues are ranked as follows:
Prohibitive |  | Milestone declaration not signed by COM MD QM. Milestone declaration blocked. State of emergency. Most strictly follow-up.
Major |  | Major deviation according to conformance assessment of COM MD QM.
None/Minor |  | Milestone declaration recom-mended or at least possible Action items in case of deviations o be tracked by SPM.
The Conformance Assessment will be issued by the responsible Quality Project Manager (QM Product Lifecycle). It is binding to the project team.
The final Round Table meeting in the project team has to take place one week prior to envisaged Milestone declaration at the latest.
The Product Generation Manager (PGM) or the PM / ODM Board members can overrule the milestone decision due to strategic reasons. In this case the decision maker takes all responsibility undivided. The decision maker has the responsibility to inform the MP