## Termine
Milestone Schedules TPM Mch, KLf
Project Name | Cat. | CPM | TPM | TPM-R&D | TPM-BO | Site |  | M-Alpha | M0 | S0 | M1 | S2 | S25 | S3 | DS | S4/M3 | M4 | EOL | ~dir.R&D cost LC
Condor [ME75] | BSi | Lasprilla | Lasprilla | Betting |  | KLf | Plan | - | 2005-06-17 | 2005-06-17 | 2005-07-08 | 2005-09-16 | 2005-10-14 | 2005-11-04 | 2005-11-25 | 2006-01-13 |  |  | 9800000
|  | Miguel |  |  |  |  | Is | - | 2005-06-17 | 2005-06-17 | 2005-07-13 | 2005-09-16 | 2005-10-14 | 2005-11-04 | 2005-11-14 | 2006-01-20 |  |  | 8500000
Minos [S75] | HJG | Hombeck | Hombeck | Barner |  | KLf | Plan | 2003-10-03 | 2004-06-30 | 2004-09-15 | 2004-11-30 | 2005-03-02 | 2005-06-24 | 2005-08-26 | 2005-09-15 | 2006-01-27 |  |  | 21392695
|  | Jan | Jan | Ulrich |  |  | Is | 2003-10-03 | 2004-08-20 | 2004-12-02 | 2004-12-02 | 2005-03-02 | 2005-12-16 | 2006-02-14 | 2006-02-17 | 2006-05-26 |  |  | 19391106
Hydra [SL75] | BSi | Mues-Hane | Mues-Hane | Christiansen |  | Aal | Plan | 2003-12-03 | 2004-07-07 | 2004-11-30 | 2004-11-30 | 2005-03-02 |  | 2005-08-26 | 2005-09-22 | 2006-01-27 |  |  | 17691970
|  | Hans-Martin | Hans-Martin | Keld |  |  | Is | 2003-12-03 | 2004-07-07 | 2004-12-02 | 2004-12-02 | 2005-03-02 | 2006-01-20 | 2006-02-14 | 2006-02-17 | 2006-05-26 | 2006-09-15 | 2006-12-31 | 17686000
Polaris [S68] | HJG | Hachmann | Neumann | Dr.Lang | Normann | Ulm | Plan |  | 2005-07-01 | 2005-09-23 | 2005-09-23 | 2005-10-21 | 2005-11-18 | 2006-01-24 | 2006-02-24 | 2006-05-31 |  |  | 10384938
|  | Eric | Thomas | Andreas | Kristina-Pia |  | Is | 2005-02-15 | 2005-07-01 | 2005-09-23 | 2005-09-23 | 2005-10-21 | 2005-12-06 | 2006-03-10 | 2006-02-23 |  |  |  | 10160913.14
Swift [EL71] | BSi | Evangelista | Kockmann | Hohenleitner | Klaus | Mch G | Plan |  | 2005-07-01 | 2005-09-23 | 2005-10-10 | 2005-10-28 | 2006-02-03 | 2006-03-31 | 2006-04-28 | 2006-08-04 |  |  | 15,7 Mio
|  | Heike | Jürgen | Markus | Annette |  | Is |  | 2005-07-01 | 2005-09-23 | 2005-10-11 | 2005-10-28 | 2006-02-10 | [5 empty] | 14,9 Mio
Swift Step 2 [EL71] | BSi | Evangelista | Kockmann | Hohenleitner | Klaus | Mch G | Plan |  | 2006-02-03: 2006-03-10; 2006-03-31: 2006-05-05; 2006-04-28: 2006-06-09
|  | Heike | Jürgen | Markus | Annette |  | Is |  | 2006-02-03: 2006-03-16
Philippe [C81] | HJG | Weidner | Dalmose | Byrdal | Shen | Aal | Plan | 2005-10-25 | 2005-11-18 | 2005-11-18 | 2005-12-08 | 2006-03-10 | 2006-03-10 | 2006-04-26 | 2006-05-29 | 2006-06-30 |  | 2007-01-31 | 4686000
|  | Claudia | Claus | Ole | Bojing |  | Is | 2005-10-25 | 2005-11-20 | 2005-11-21 | 2005-12-15 | 2006-03-10 | 2006-03-10 | (26-4-06) | 2006-05-29 | 2006-06-30 |  | 2007-01-31 | 4223000
Hawk [M81] | HJG | Heinen | Dalmose | Byrdal | Christoph | Aal | Plan |  | 2006-03-08 | 2006-03-08 | 2006-03-31 | 2006-06-12 | 2006-06-12 | 2006-07-31 | 2006-08-11 | 2006-09-15 |  | 2007-06-30 | 3042000
|  | Antje | Claus | Ole | Link |  | Is | 2006-02-03 | 2006-03-08: 2006-03-08; 2006-03-08: 2006-03-14; 2006-03-31: 2006-04-20 |  | 2007-06-30 | 3042000
Obsidian [E71] | BSi | Greger | Stokholm | Ole Rasmussen |  | Aal | Plan |  | 2005-12-07 | 2005-12-23 | 2006-03-08 | 2006-05-18 | 2006-07-17 | 2006-08-18 | 2006-09-08 | 2006-10-19 |  | 2007-07-31 | 7,7Mio
|  | Vinzenz |  |  |  |  | Is | 2005-10-27 | 2005-12-07: 2005-12-07; 2005-12-23: 2006-02-03; 2006-03-08: 2006-03-17 |  |  | 6,8Mio
Chameleon [CL61] | BSi | Greger | Zimmer | Gallos | Link | KLf | Plan | 2005-10-01 | 2006-03-17 | 2006-03-17 | 2006-03-31 | 2006-07-10 | 2006-08-07 | 2006-10-16 | 2006-11-10 | 2006-12-22 |  |  | 6500000
|  | Vinzenz | Alois | Reinhard | Christoph |  | Is |  | 2005-12-07: 2006-03-20; 2005-12-23: 2006-03-20; 2006-03-08: 2006-04-20; 2006-09-08: 2006-11-08
Jerry [] | KBr | Koh Kheng Wah | Shuai Zhang | XinJuan Song |  | Aal | Plan |  | 2006-03-17 | 2006-03-31 | 2006-03-31 | 2006-07-31 | 2006-07-31 | 2006-08-23 | 2006-10-06 | 2006-11-30 | 2007-10-06 | 2007-10-06 | 7200000
|  |  |  | Arjen Broeze |  |  | Is | 2006-01-17 | 2005-12-07: 2006-03-17; 2005-12-23: 2006-04-07; 2006-03-08: 2006-04-07
Diamond | BSi | Lohbrunner | Betting | Barner |  | KLf | Plan | 2006-01-19 | 2006-04-21 | 2006-05-19 | 2006-06-23 | 2006-10-12 | 2006-12-13 | 2007-02-07 | 2007-04-20 | 2007-05-30 |  |  | 12200000
|  | Ulrike | Andreas | Ulrich |  |  | Is | 2006-01-19 | 2005-12-07: 2006-04-21
Silverstone | SRe | Brück | Kern | Röhrig |  | Klf | Plan | 2006-05-19 | 2006-06-30 | 2006-08-04 | 2006-09-01 | 2006-12-22 | 2007-03-02 | 2007-04-20 | 2007-05-23 | 2007-06-29 | 2007-07-30
-> Basis: First rough plan |  | Klaus-Peter | Ralf | Daniel |  |  | Is
Kaolin | BSi | Corniou | NN | NN |  | KLf | Plan | 2006-05-30 | 2006-06-21 | 2006-07-19 | 2006-08-23 | 2006-12-12 |  | 2007-04-06 | 17.06.07 30.06.07 | 2007-07-22 | 2008-08-30 | 2008-08-30
|  | Frederic |  |  |  |  | Is |  | 2006-09-08: 2007-06-30
Galena | BSi |  | NN | NN |  | KLf | Plan |  | 2006-10-30 | 2006-11-30 | 2006-12-30 | 2007-04-30 |  | 2007-07-30 | 30.08.07 31.08.07 | 30.10.07 30.11.07 | 2008-11-30 | 2008-11-30
[7 empty] | Is |  | 2006-09-08: 2007-08-31
Kunzite | KBr |  | NN | NN |  | KLf | Plan |  | 2007-01-31 | 2007-02-28 | 2007-03-30 | 2007-05-31 |  | 2007-08-31 | 28.09.07 30.09.07 | 24.10.07 31.10.07 | 2008-10-31 | 2008-10-31
[7 empty] | Is |  | 2006-09-08: 2007-09-30
Wolf 5 [SXG75] | BSi | Plitzner | Watzke | Engelhardt |  | KLf | Plan |  | 2004-03-24 | 2004-08-12 | 2004-09-23 | 2005-04-08 | 2005-04-20 | 2005-07-21 | 2005-09-22 | 2005-10-07 |  |  | 36500000
|  | Ralf | Jörn | Thomas |  |  | Is | 2004-01-21 | 2004-07-02 | 2004-08-19 | 2004-10-22 | 2005-06-03 | 2005-09-05 | 2005-12-29 | 2005-12-29 | 2006-03-17 |  |  | 36200000
Onyx | BSi | Jerbi | Feldhoff | Alkämper | Klaus | KLf | Plan |  | 2006-01-09 | 2006-02-16 | 2006-03-17 | 2006-06-08 | 2006-07-21 | 2006-08-25 | 2006-10-20 | 2006-12-21 |  |  | 13054000
|  |  | Markus | Thomas | Annette |  | Is |  | 2004-03-24: 2005-12-23; 2004-08-12: 2006-02-16; 2004-09-23: 2006-03-17
Kestrel [EF81] | HJG | Palandoeken | Petersen | Schreiber |  | Mch | Plan |  | 2005-04-14 |  | 2005-07-08 |  | 2005-11-18 |  | 2006-03-03 | 2006-05-14 |  |  | 7000000
|  | Hasan | Holger |  |  |  | Is |  | 2005-04-14 |  | 2005-07-08 |  | 2005-12-16 |  | 2006-04-07 | 2006-05-12 |  |  | 6100000
Kestrel Refresh | HJG | Palandoeken | Petersen | Schreiber |  | Mch | Plan |  | 2004-09-23: 2006-04-28; 2005-04-20: 2006-07-04; 2005-09-22: 2006-10-20; 2005-10-07: 2006-12-22
|  | Hasan | Holger | Thorsten |  |  | Is
Ruby | HJG | Aschmoneit | Wiesing | Schwarz |  | Mch | Plan |  | 2006-03-03 | 2006-04-12 | 2006-05-17 | 2006-08-02 | 2006-10-04 | 2006-12-20 | 2007-02-28 | 2007-04-11
|  | Christoph | Detlef | Manfred |  |  | Is | 2006-01-17 | 2006-03-03: 2006-03-03; 2006-04-12: 2006-04-26; 2007-02-28: 2007-02-28
Koala | HJG | Hantschel | Watzke | Engelhardt |  | Mch | Plan | 2006-03-30 | 2006-05-30 | 2006-06-30 | 2006-07-30 | 2006-09-30 | 2006-12-15 | 2007-03-20 | 2007-04-30
[7 empty] | Is | 2006-03-22 | 2007-02-28: 2007-04-30
Titanium | HJG |  | Neumann | Lang |  | Mch | Plan |  | 2006-06-30 | 2006-07-30 | 2006-09-30 | 2007-01-30 |  | 2007-06-30 | 30.07.07 31.07.07 | 30.09.08 30.10.07 | 2008-10-30 | 2008-10-30
[7 empty] | Is |  | 2007-02-28: 2007-07-31
Garnet | BSi |  | NN | NN |  | Mch | Plan |  | 2006-09-30 | 2006-11-30 | 2006-12-30 | 2007-03-30 |  | 2007-06-30 | 30.07.07 31.07.07 | 30.08.07 30.09.07 | 2008-09-30 | 2008-09-30
[7 empty] | Is |  | 2007-02-28: 2007-07-31
Mica | BSi |  | NN | NN |  | Mch | Plan | 2006-07-30 | 2006-09-30 | 2006-11-30 | 2006-12-30 | 2007-02-28 |  | 2007-07-30 | 30.08.07 31.08.07 | 30.10.07 30.11.07 | 2008-11-30 | 2008-11-30
[7 empty] | Is |  | 2007-02-28: 2007-08-31
Total | [6 empty] | Plan | [11 empty] | 149451603
[7 empty] | Is | [11 empty] | 105303019.14
Dates derived from PMC data base
Upcoming milestones
Changes compared to the original
Initial (rough) plan
Note on A28: Peter Farrenkothen: PMC data base to be adjusted to initial planned milestones!
Note on J7: Ulrich Barner: M0 HW: 30.06.2004 (on time) M0 SW: 20.08.2004
Note on J17: Peter Farrenkothen: PMC to be updated
Note on J26: Ulrich Barner: initial date 08.03.2006
Note on K7: Ulrich Barner: S0 HW: 15.09.2004 (on time) S0 SW: 02.12.2004
Note on K17: Peter Farrenkothen: PMC to be updated
Note on K26: Ulrich Barner: S0-HW 19.05.2006 S0-SW vor/mit M1
Note on K39: Peter Farrenkothen: PFa: S0 HW 19.01.06 PMC
Note on L5: Peter Farrenkothen: PFa: No backwards correction in PMC (08.07.05) 13.07.05 is the correct date
Note on L7: Ulrich Barner: M1 plan: 30.11.2004 but S0 SW + M1 declared: 02.12.2004
Note on L17: Peter Farrenkothen: PMC to be updated
Note on L23: Peter Farrenkothen: PMC to be updated 31.03.06 -> 20.04.06
Note on N7: Ulrich Barner: S25 basic 28.09.2005 (CW39) DONE (without 'progressive' and 'streaming')
Note on T5: bettinga: stand FC 12/2005
Note on T7: Keld Christiansen: Actual + FC
Note on T9: Keld Christiansen: Actual + FC
Note on T11: Thomas Neumann: Actual+FC
Note on T26: bettinga: status: M0
Note on T38: Markus Feldhoff: Status M1: zusätzlich muss noch ein neues Display qualifiziert werden, welches additive Kosten verursacht, die derzeit in der PMC noch nicht geplant sind

## Timing
Projekt | DS | 04.06 | 05.06 | 06.06 | 07.06 | 08.06 | 09.06 | 10.06 | 11.06 | 12.06 | 01.07 | 02.07 | 03.07 | 04.07 | 05.07 | 06.07 | 07.07 | 08.07 | 09.07 | 10.07 | 11.07 | 12.07
Minos | 01.06
Hydra | 01.06
Polaris | 02.06
Swift | 04.06
Chameleon | 10.11.06
Onyx | 10.06
Diamond | 04.07
Silverstone | 05.07
Kalolin | 06.07
Galena | 08.07
Kunzite | 09.07
Philippe | 05.06
Hawk | 08.06
Obsidian | 08.06
Kestrel | 04.06
Kestrel Refr. | 10.06
Ruby | 02.07
Koala | 04.07
Titanium | 07.07
Garnet | 07.07
Mica | 08.06
Projekt | DS | 04.06 | 05.06 | 06.06 | 07.06 | 08.06 | 09.06 | 10.06 | 11.06 | 12.06 | 01.07 | 02.07 | 03.07 | 04.07 | 05.07 | 06.07 | 07.07 | 08.07 | 09.07 | 10.07 | 11.07 | 12.07

## aktuell
FF | Projektname | Kurzbeschreibung | Vol | CM | L8 | H | S | T | M | DS | Display | Size | Camera | Batt. | Chipset | Bemerkung
2.5G BMK, BMM
S | Swift [EL71] | Slim-Line seitl. | 2'0 | BS |  | M | M | M | M | 28.04.06 | 240 x 320 256k TFT | 2"0 | 1'3Mpx | 560 | SG2 ATI B5PL µSD | 45x87x14.5 B6PL
B | Philippe [C81] | Minos II | 0'62 | JG |  | A | A | A | A | 05.06 | 132 x 176 256k TFT | 1"8 | 1'3Mpx |  | SG2 B5PL BRF6150
B | Hawk [M81] | ME85 |  | JG |  | A | A | A | M | 11.08.06 | 132 x 176 256k TFT | 1"8 | 1'3Mpx |  | SG2 B5PL BRF6150
B | Obsidian [E71] | Aries Nachf. | 3'8 | BS |  | A | A | A | A | 08.09.06 | 240 x 320 256k TFT | 2"0 | 1'3Mpx |  | SG2 BT B6PLA µSD FM | 15mm
B | Dolomite | Polaris Refresh |  | JG |  | M | M | M | M | 10.06 | 132 x 176 256k TFT | 1"8 | - | 660 | SG2 B6E BT MP3 µSD | 13.2mm
S | Chameleon [CL61] |  | 0'32 | BS | x | K | K | K | K | 08.11.06 | 240 x 320 256k TFT | 2"0 | 1'3Mpx | 750 | SG2, IFX RF & BT | 87x47x20.2 mit Side-Keys
Z | Diamond | Zippo (tbc) | 0'85 | BS |  | K | K | K | K | 04.07 | 240 x 320 256k TFT | 1"8 | 1'3 FF |  | SG2, BT
B | Silverstone | 100% Waterproof | 0'63 | SR |  | K | K | K | K | 05.07 | 176 x 220 256k TFT | 2"0 | 1'3Mpx |  | SG2 FM BT | Nightvision
C | Kaolin |  | 1'4 | BS |  | K | K | K | K | 06.07 | 176 x 220 256k TFT 96 x 64 4k CSTN | 2"0 1"0 | 1'3Mpx |  | SG2 BT FM
Z | Galena |  | 2'2 | BS |  | K | K | K | K | 08.07 | 240 x 320 256k TFT | 1"8 | 1'3 | 570 | SG2 BT | 84x48x15,3mm
C | Kunzite |  | 2'9 | KB |  | K | K | K | K | 09.07 | 176 x 220 256k TFT 96 x 64 4k CSTN | 2"0 1"0 | 1'3 |  | SG2 Apoxi BT | OP Phone
3G BMK, BMM
CS | Kestrel [EF81] | TFT, Imaging | 1'6 | JG |  | M | M | M | M | 17.03.06 | 240 x 320 256k TFT 160 x 120 265k TFT | 2"2 1"3 | 2'0Mpx | 910 | 6250A | Semco Camera FF Micro SD Card
CS | Kestrel Refresh [EF?] |  | 1'7 | JG |  | M | M | M | M | 10.06 | 240 x 320 256k TFT 160 x 120 265k TFT | 2"4 1"5 | 3'2Mpx | 910 | 6250A BT FM Stereo | Semco Camera FF Micro SD Card
S | Onyx | FSR | 1'29 | BS |  | K | K | K | K | 20.10.06 | 240 x 320 16,7Mio TFT | 2"0 | 3'2 AF |  | 6250A BT FM VGA | LxBxD= 89x47x23,8mm
B | Ruby |  | 0'37 | JG |  | M | M | M | M | 28.02.07 | 240 x 560 256k TFT | 3"4 | 3'0 AF |  | 6280 3.6 FM | HDD 50x110x18
CS | Koala [ ] | Video | 0'85 | JG |  | M | M | M | M | 04.07 | 240 x 320 256k TFT 160 x 120 256k TFT | 2"4 1"3 | 3'0 AF |  | 6280 | Micro SD Card
B | Mallow | small W5 outdoor | 0'39 | SR |  | M | M | M | M | 04.07 | 320 x 240 256k TFT | 2"0 | 3MpxAF | 1000 | 6255, BT, FM
B | Garnet [] | The Sculpture | 0'22 | BS |  | M | M | M | M | 07.07 | 240 x 320 256k TFT | 2"0 | 2'0 AF |  | 6250A BT FM | 11,5mm
B | Titanium |  | 2'6 | JG |  | M | M | M | M | 06.07 | 176 x 220 256k TFT | 1"8 | 1'3 | 1000 | 6245 VGA BT µSD
S | Mica [ ] |  |  | BS |  | M | M | M | M | 08.07 | 240 x 440 256k TFT | 2"53 | 3'2 AF |  | 6255 | Micro SD Card
BMB
B | Goldfinch [A58] | Finch BT | 1'1 | KB |  | B | B | B | B | 08.08.06 | 128 x 128 64k CSTN | 1"5 | - | 820 | EGR Apoxi based | MMI PCB
C | Jade - | Brambling Clam |  |  | x | B | B | B | B | 03.07 | 176 x 220 256k TFT 96 x 64 4k CSTN | 2"0 1"0 | 1'3 |  | SG3 LED Fl BT µSD | OP phone
B | Jerry | Vodafone Simply | 0'4 | KB |  | A | B | B | K | 06.10.06 | 132 x 176 65k TFT | 1"8 | - | 820 | SGL B6E | 111.5 x 45 x 16.5
B | Amber [C31] | Nachf. Goldfinch | 8'8 | KB |  | B | B | B | B | 20.10.06 | 128 x 160 64k CSTN | 1'8 | VGA | 820 | EGR BT | Apoxi 104x45x15.5
B | Marten |  | 3'0 | KB |  | B | B | B | B | 02.07 | 128 x 160 65k CSTN | 1"8 | - | 820 | EGR µSD BT
S | Pearl |  | 3'5 | KB | x | B | B | B | B | 03.07 | 128 x 160 65k CSTN | 1"8 | VGA | 580 | EGR µSD FM BT
C | Sunstone |  | 4'3 | KB | x | B | B | B | B | 07.07 | 128 x 160 64k CSTN 96 x 64 4k CSTN | 2"0 1"0 | VGA | 580 | Locosto+ µSD BTFM LEDFlash AIT | OMA DRM 2.0, MS DRM, DRM 1.0
2.5G BQT
S | Cupid S1 [CL71] | Asia only | 0'05 | BS |  | T | T | T | T | 23.03.06 | 176 x 220 256 TFT | 2"0 | 1'3Mpx | 750 | CalypsoG2 AIT715 B6E µSD
B | Hermes B1 [E61] |  | 1'2 | KB |  | T | T | T | T | 06.04.06 | 128 x 160 64k TFT | 1"8 | VGA | 920 | CalypsoG2 Renesas J2S B6E µSD
C | Hermes C5, C6 [CF61] C6 [CF61a] |  | 0'29 | BS |  | T | T | T | T | 25.04.06 | 128 x 160 256k TFT 96 x 32 MSTN | 1"8 | 1'3 | 920 | CalypsoG2 Lite SLAero1+ AIT715 µSD | Dick-Mann
B | Pandora B2 [EF51] |  | 0'11 | JG |  | T | T | T | T | 30.05.06 | 128 x 128 256k TFT | 1"6 | 1'3Mpx | 870 | CalypsoG2 Renesas J2S B6E miniSD BT | 89x49x18 49g
B | Jasper [A38] |  | 5'0 | KB |  | T | T | T | T | 11.07.06 | 96 x 64 4k CSTN | 1"4 | - | 920 | Calypso G2 Lite B6E
C | Hermes C7 [CLxx] | Poppy2 HC5 ID |  | BS |  | T | T | T | T | 20.07.06 | 128 x 160 256k TFT 96 x 32 MSTN | 1"8 | 1'3MPx | 920 | CalypsoG2 Lite SLAero1+ AIT715 µSD
C | Venus C3 [CF81] |  | 0'2 | BS |  | T | T | T | T | 28.07.06 | 176 x 220 256k TFT 128 x 64 256k OLED | 2"2 1"0 | 2'0MPx | 800 | Calypso G2 Lite RFµD AIT713 µSD
B | P51 |  | 0'04 | JG |  | T | T | T | T | 29.07.06 | 240 x 320 256k TFT | 2"83 | 1'3MPx | 1240 | PXA272 416MHz Aero1+ MS5.0 1MBFlash | 1MBSRAM µSD BTTI WLANTI LEDFlash GPS
| Agate [A21] |  | 7'8 | KB | x | T | T | T | T | 14.08.06 | 96 x 64 BW | 1"3 | - | 920 | Calypso G2 Lite B6E
B | Calcite |  |  | KB |  | T | T | T | T | 10.06 | 176 x 220 256k TFT | 2"0 | 1'3MPx | 920 | CalypsoG2 Renesas J2S B6E MiniSD
S | Coral |  |  | KB |  | T | T | T | T | 12.06 | 176 x 220 256k TFT | 2"0 | 2'0 | 750 | Calypso G2 Lite B6E AIT811 µSD
C | Morgonite | ehem. Loloite | 4'1 | KB |  | T | T | T | T | 02.07 | 176 x 220 256k TFT 96 x 64 0k OLED | 2"0 1"0 | 1'3Mpx | 735 | Locosto+ µSD BTFM LEDFlash AIT | OMA DRM 2.0, MS DRM, DRM 1.0
B | Rembrandt |  | 5'8 | KB |  | T | T | T | T | 06.07 | 176 x 220 256k TFT | 2"0 | 2'0Mpx | 920 | Locosto+ µSD BTFM | OMA 1.0 or OMA DRM2.0+MS DRM
B | Miro |  | 2'2 | KB |  | T | T | T | T | 08.07 | 240 x 540 256k TFT | 3"4 | 2'0 AF | 920 | Neptune RFMD P2RM µSD BTFM LED Flash | OMA 1.0 or OMA DRM2.0+MS DRM
C | Monet |  | 4'3 | KB |  | T | T | T | T | 11.07 | 176 x 220 256k TFT 96 x 64 0k OLED | 2"0 1"0 | 1'3Mpx | 735 | Locosto+ µSD BTFM LEDFlash AIT | OMA 1.0 or OMA DRM2.0+MS DRM
3G BQT
B | Ulysses B1 [S81] |  |  | JG |  | T | T | T | T | 25.04.06 | 176 x 220 256k TFT | 2"0 | 1'3VGA | 920 | 6250A BT µSD | 109x48x13 99g
C | Macross C1A [EF91] |  | 0'19 | JG |  | T | T | T | T | 11.07.06 | 320 x 240 256k LTPS 64 x 96 OLED | 2"0 | 3'2Mpx VGA | 1000 | 6275 µSD RFR6250 RTR6250D | HSDPA Cl.12 1.8 8PSK 92x47x23.5 100g
B | Merlin [E81] | Low-Cost | 1'5 | JG |  | T | T | T | T | 01.09.06 | 176 x 220 256k TFT | 1"8 | 1'3MPx | 920 | 6250A BT FL µSD | OpV7.2.5 16mm
C | Caesar Ulysses C3A [SF71] |  | 0'43 | JG |  | T | T | T | T | 27.09.06 | 240 x 320 256k TFT 96 x 96 64k OLED | 2"0 | 2'0Mpx | 920 | 6250A BT FL VGA µSD | OpV7.2.5 18.8mm
B | Dali |  |  | JG |  | T | T | T | T | 02.07 | 240 x 320 256k TFT | 2"0 | 2'0MPx | 1500 | 6275 BT FL µSD VGA
B | Flint |  | 1'2 | JG |  | T | T | T | T | 03.07 | 240 x 320 256k TFT | 1"8 | 2'0MPx | 920 | 6250A BT FL µSD VGA FM | Nightvision
S | P61 | ehem. Saphire |  | JG |  | T | T | T | T | 03.07 | 240 x 320 256k TFT | 2"83 | 3'0 AF | 1240 | Hermon Bulverde 416Mc RFµDPolaris2 Max2391/ 2395 | 256/128 MByte µSD BTTI WLANTI LEDFlash TVout FM
B | Platinum |  | 1'9 | JG |  | T | T | T | T | 04.07 | 240 x 320 256k TFT | 2"0 | 3'0 AF | 1170 | 6280 GPS BT µSD
S | Goldstone |  | 0'15 | SR |  | T | T | T | T | 07.07 | 240 x 320 256k TFT | 3"0 | 3'0 AF | 1500 | iTavor 624Mc B6PLD S3G 256/128MByte 30GBHDD | µSD BTTI WLANTI LEDFlash TVout
C | Alumen | ehem.Aquamarine | 2'3 | JG |  | T | T | T | T | 07.07 | 240 x 320 256k TFT 96 x 96 64k OLED | 2"0 | 3'0 AF | 910 | 6255A µSD FM
S | Chrystal |  | 0'75 | BS |  | T | T | T | T | 09.07 | 240 x 320 256k TFT | 2"0 | 3'0Mpx | 910 | 6255A µSD FM
B | Da Vinci |  | 0'8 | JG |  | T | T | T | T | 10.07 | 240 x 320 256k TFT | 2"0 | 2'0 AF | 1170 | 6280 BT FL µSD VGA
ODM
B | Zirkon | ODM | 6'7 | KB |  | T | T | T | T | 01.07 | 96 x 64 4k CSTN | 1"4 |  |  | ODM
| I-Plattform |  | Scn |  |  | M | M | K | K | tbd |  |  |  |  | Hermon Boulverde
| Produkt I-Plattform |  | Scn |  |  | K | K | K | K | 07.06 |  |  |  |  | Hermon Boulverde
B | Canary PPM [Dodo] | Flextronix,CCI | Pln |  | x |  | A | A | A | 17.01.06 | 101 x 64 STN | 1"3 |  |  |  | Low End/Basic DS 11.05 ?
CS | Electra PPM | Cellon | App |  |  |  | U | U |  | 01.05 | 128 x 160 |  | 1'3Mpx |  | Philips 5110

## alt
FF | Projektname | Kurzbeschreibung | Vol | CM | L8 | E | F | B | M | DS | Display | Size | Camera | Batt. | Chipset | Bemerkung
2.5G BMK, BMM
B | Aries [C75] | Ulysses DTC |  |  |  | A | K | K | K | 22.08.05 | 132 x 176 TFT | 1"8 | VGA |  | SGL + 716 B6E
B | S65 w/o camera [SP65]
B | Condor [ME75] | Aries Outdoor ID | 1'4 |  |  | A | K | K | K | 25.11.05 | 132 x 176 TFT | 1"8 | VGA | 1000 | SGL + 716 B6E | Gallos
B | Cormorant [C72] | Hera VGA |  |  |  | A | A | A | A | 10.05 | 130 x 130 CSTN | 1"5 | VGA |  | SGL
B | Minos [S75] |  |  | JG |  | K | K | K | K | 12.12.05 | 132 x 176 256k TFT | 1"8 | 1'3Mpx |  | SG2 B5PL BRF6150
S | Hydra [SL75] |  | 1'1 | BS |  | A | A | A | A | 12.12.05 | 132 x 176 256k TFT | 1"8 | 1'3Mpx |  | SG2 B5PL BRF6150 | d=23.5mm
B | Polaris [S68] |  | 1'1 | JG |  | U | U | U | U | 24.02.06 | 132 x 176 256k TFT | 1"8 | - | 660 | SG2 B6E BRF6150 | 13.2mm
3G BMK, BMM
S | W4 [SG75] |  |  |  |  | R | R | M | K | 11.05 | 176 x 220 | 2"0 | 1'3Mpx | 950 | 6250
B | W5 [SXG75] |  |  | JG |  | R | R | R | K | 12.05 | 320 x 240 256k TFT | 2"2 | 2'0Mpx | 1000 | 6250 | FM Radio, BT
BMB
CS | Leopard EGL |  |  |  | B | B | B |  |  | 03.04 | 130 x 130 CSTN 96 x 64 STN | 1"5 | - | EGV3
B | Puma [A65] |  |  |  | B | B | B |  |  | 09.04 | 101 x 80 CSTN |  | - | EGV3 BSE, B6E ab 01.05
B | Libra [A75] | PCB wie Dorado |  |  | x | M | B | B | B | 05.05 | 101 x 80 CSTN |  | - |  | EGL B6E/SSD2 | Ant: Mch
B | Libra [A76] | PCB wie Dorado |  |  | x | M | B | B | B |  | 101 x 80 CSTN |  | - |  | EGL B6E/SSD2 | Ant: Mch
B | Pegasus [AX75] |  | 0'9 |  | x | A | B | B | B | 05.05 | 128 x 128 64k CSTN | 1"5 | - | R65Sl | EGL | 8$ Displ.Philips, modif.Hera
B | Dorado [A70] | PCB wie Libra | 10'6 |  | x | M | B | B | B | 03.06.05 | 101 x 64 STN |  | - |  | EGL B6E SD2 | Ant: Mch
B | Dorado 850 [A71] | PCB wie Libra |  |  | x | M | B | B | B |  | 101 x 64 STN |  | - |  | EGL B6E SD2 | Ant: Mch
B | Sirius [M75] |  |  |  |  | U | U | U | U | 06.05 | 132 x 176 256k TFT | 1"8 | 1'3Mpx |  | SGL + 732 B5E
B | Phoenix [CX75] |  |  |  |  | U | U | U | S | 06.05 | 132 x 176 256 T | 1"8 | 1'3Mpx |  | SGL + 732 B5E
CS | Adonis [CF75] [CF76] | BYD OSS | 2'1 | KB | x | B | B | B | B | 07.05 | 128 x 160 CSTN 96 x 64 CSTN 4k | 1"8 1"0 | VGA | R65Sl | SGL G15 716 B6E G12 komp.
S | Flamingo [CF110] |  |  |  |  | A | A | B | S | 24.10.05 | 130 x 130 64k TFT | 1"7 | - | 580 | EGL B6E SD2
B | Finch [A31] |  | 3'5 | KB | x | B | B | B | B | 08.02.06 | 128 x 128 64k CSTN | 1"5 | - | 700 | EGL SSD2 | DB? 102x46x18
CS | Quail [AF51] | BYD OSS | 1'8 | KB |  | M | M | B | B | 20.02.06 | 130 x 130 CSTN 96 x 64 CSTN | 1"5 | - | 660 | EGL B6E SD2 | 79x41x19.2 80g BYD Batt.2nd zu Polaris
S | Pelicane [AL21] | Flamingo DTC | 1'7 | KB | x | A | B | B | S | 23.03.06 | 130 x 130 64k TFT | 1"7 | - | 580 | EGL | 87x46x19 78g
2.5G BQT
B | P50 |  | 0'05 | JG |  | T | T | T | T | 12.05 | 240 x 320 256k TFT | 2"83 | 1'3MPx | 1240 | PXA272 416MHz Aero1+ MS3.0 512kBFlash | 512kBSRAM µSD BTTI WLANTI LEDFlash
B | Hyperion B1 [S88] |  | 0'3 | JG |  | T | T | T | T | 27.03.06 | 176 x 220 256k OLED | 2"0 | 2'0 AF | 920 | CalypsoG2 Renesas J2S B6E µSD BT | LEDFlash
3G BQT
CS | Siskin | Adonis new ID |  |  |  | B | B | B | B | 12.05 | 128 x 160 TFT 96 x 64 CSTN 4k | 1"8 1"0 | 1'3Mpx | 750 | SGL + 758 | OV9650
CS | S80 [SFG75] |  | 0'07 |  |  | T | T | T | T | 11.05 | 176 x 220 256k TFT 96 x 96 64k CSTN | 2"0 1"2 | 1'3MPx CIF |  | 6250 MMIK MiniSD LEDFlash MurataBT | IrDa
ODM
CS | Electra PPM [SF65] | Cellon |  |  |  |  | U | U |  | 01.05 | 128 x 160 |  | 1'3Mpx |  | Philips 5110
CS | Wega PPM [CL75] | Quanta |  |  |  |  | U A | K | A | 12.08.05 | 128 x 160 256k TFT 96 x 64 64k CSTN | 1"7 1"1 | VGA |  | ADI
B | Mars PPM [CC75] | Elcoteq/EDC |  |  |  |  | U | U | U | 27.10.05 | 128 x 160 64k TFT | 1"66 |  | 820 | Motorola | PS:Freescale
Note on G3: HAs: PPL Aal,
Note on G11: HAs: PPL KLf
Note on G12: HAs: PPL KLf
Note on H11: HAs: PPL Mch
Note on I3: HAs: Galos
Note on I11: HAs: PPL Mch
Note on J26: HAs: BYD ?