## Tabelle2
Supply Chain Management
Available rules for D2C applied; deviations are listed | DONE
General concept for realization of customer variants defined (placing of customer logo, operator key, SW modifications etc…) | DONE
External assemblies have been defined. | open | no assembly concept available, has to be done until S0
Life cycle volumes, peak volumes and sales split and regions available | DONE
Production sites and RU factories are defined (according to SD overall stategy driven by CM) | DONE
Team sensitized concerning restriction of production sites | DONE
Potential production sites are considered within supplier selection (e.g. assemblies) | DONE
Ramp Up Plan available on weekly basis (including ramp up locations and configuration /rebooting scenario) | DONE
Draft Logistics concept available concerning production site, configuration sites | DONE
Number of HW / Design variants (IDs) defined | DONE
Product related second solutions and second sources agreed with Procurement | DONE
Maximum monthly capacity has been defined (incl.needed upside flexibility) | DONE
Conversion cost re-evaluated be SD BA | open | F1 planning has to be done when assembly concept is available
Part declaration OFE PP available | DONE | production site SSMC
Part declaration SD QM available | blocking | pending
Quality Management: Material Quality and Technical Capability
Detailed Primavera project plan from M0 to M1 showing dedicated resources by name is available | DONE
Rough Primavera project plan from M1 to M3/S4 showing dedicated resources on department level is available | DONE
Production process Quality Manager QM CI is assigned | DONE
Quality Management: Production Technology
Detailed Primavera project plan from M0 to M1 showing dedicated resources by name is available | pending
Rough Primavera project plan from M1 to M3/S4 showing dedicated resources on department level is available | pending
Product related second solutions and second sources agreed with Procurement | pending
Parts list (Populated PCB) is available in SAP PLM | DONE
Production Technology
Detailed Primavera project plan from M0 to M1 showing dedicated resources by name is available | DONE
Rough Primavera project plan from M1 to M3/S4 showing dedicated resources on department level is available | open | Draft status – will be updated until M1
New product technologies with specifications and status are available | DONE
New production technologies with specifications and status are available | DONE
Draft calculation for process times, special tooling cost and F1 hours are available | open | No assembly concept – has to be done until S0
Draft SD Production process flow layout is available | open | No assembly concept – has to be done until S0
Part declaration PT is available
Project account is available | open | Project account not available
Connection technique defined (e.g.: RF, connectors, B2B, battery connector) | DONE | DONE
Fall-back solution (e.g. second solution, added resources, …) for not finished pre-development projects defined | DONE | DONE
Customizing concept with focus on NO ID available | DONE | VF exclusive
Prototype shop planning is available | open | first draft - update until S0 necessary