## M1
Jerry M1 Milestone. Items critical or blocking for milestone declaration
Blocking |  | Blocking issue for declaring the specific milestone
Critical |  | Problem to be solved later- solution and timeframe must however be known and agreed
Milestone can be/is approved
Line | M1 | Blocking or critical issue | Status | Comment | Risk assesment | Actions | Who | When
BB - F. B. Kristensen |  | Declaration paper will be uploaded by Mar 31th
|  | S0 blocking point: board outline and stackup concept finalized | Has declared S0 | Expected to be finished on Mar. 25
No big risk and blocks for M1 except the timeline
| Blocking | ASP requirment should use the latest version. | Open | Has to escalate to top management |  | Escalate to top management | Wolfgang | Mar 29th
RF - M. Brammer |  | Declaration paper will be uploaded at Mar 29th
|  | S0 blocking point: board outline and stackup concept finalized | S0 has been declared | Expected to be finished on Mar. 25
No big risk and blocks for M1 except the timeline
complete project primavera detail plan is reviewed and agreed
EA - A. B. Krisensen | Declared |  |  | Expect to declare on Mar. 20
MD - C. P. Nielsen |  | Declaration paper will be uploaded Mar 29th
|  | Design FMEAs | scheduled | Will be done on 21-22/3
|  | TTDs | ongoing | Draft versions need to be done before M1
|  | MAP plan | ongoing
|  | Kick off meeting with PM and LPD about variants | will be planned by PM
|  | Primavera plan | Finshed by Mar 29th | Telco with Christian, Katharina, Randi and Bjarne
|  | Update the performance description regarding soft touch |  | Expected to finish by today
SW - Y. Y. Qiang | Declared | Open issue has been uploaded Declaration paper will be uploaded Mar 29th |  | Planning: - 2 SISL CIT member to be onsite from mid May to end Sept., maybe earlier, depending on number of bugs - 2 enployees onsite from beginning of June. |  | SW director/line manager should provide proper resources. | Juergen Bonfert, Yang Yong Qiang | by end of March.
| Critical | No modified wingboard in SISL so far, which might endanger SW Sprint 1 | active | Will be partially handcarried by Juergen Schmitz |  |  | Allan Hensan, Yang Yong Qiang | by 21.03.06
| blocking | Some requirements still open and to be clarified with VF. | active | Some features required by VF must be compromised due to high effort, e.g. T9 tutorial |  | Get VF to compromise or plan additional effort. Most features clarified already. Remaining open items should be closed on Mar. 25 | Arjen Broeze, Shen Yu Kai | by 21.03.06
|  | There is no direct connection between RIDB Beijing and CDB SISL, and no auto sync therefore, which impacts integration cycle. | active | Need agreement bwtween ITS BenQ and Siemens SBS. |  | Get a timeline to get this fixed or additional resources for doing manual sync. Will be automated before the end of March. Current manual solution is ok until then. | Arjen Broeze | by 21.03.06
| blocking | Primavera planning | ongoing | Will be completed by Mar 24
| Critical | Improve timeline, otherwise no contract |  | Will be discussed in last week of March
|  | CIT colleague from AAL could only stay till end of May. SW team need official commitment from AAL for CIT people staying in BEJ for the whole lifecycle | Open |  |  | Find a solution to stablize the CIT resources | Juergen Bonfert | By 31 of May
SW-QM - B. M. Mortensen |  | Check later
| critical | ASP corporate instruction has to be agreed on by SW team | Will be reviewed by SW team 2006-03-23: Will get agreed today, after which SW team needs to agree on requirement
| critical | Featurelist shall be closed |  | Check actual status
QM - T. Bartel | Blocking | All PPLs have declared M1 milestones with attached reasonable MEP checklists showing restrictions, planned corrective actions, timeline for implementation | ongoing |  |  |  |  | 2006-03-24
| Blocking | M1 document (performance description) | ongoing | The current the document has still lots of "?" Please take care that new GQR (1.1.1) are taken into account in the Performance Description |  | All PPLs have to implement their requirements into M1 document | Arjen Broeze Poul Erik Rask | 2006-03-20
|  | Design FMEAs performed and reviewed from QM | Done |  |  |  | MD/QM | 2006-03-24
| Blocking | Risk analysis for product safety filled out from relevant PPL and signed by PLT,PM & QM | in progress | Should be finished at Mar 29th |  | PPLs to fill out risk and safety analysis document and PLT/PM/QM sign | PLT/PM/QM | Due by March 22
| Blocking | M1 Q-Gate has been perfomed | not started | Scheduled at Mar 31th |  |  |  | week 12
| Blocking | RMEA available for PS/DS | need to be reviewed |  |  | Still needs to be done. | PLT/PM | 2006-03-24
|  | Quality Planning is available | Close |  |  | Create Quality plan | T.Bartel | week 11
| Blocking | PSQA plans available from RF, EA, dHW, MD, SW | HW and RF PSQA plan are missing. EA and MD PSQA plan should be reworked |  |  | Create PSQA plans | PPLs for RF, EA, dHW, MD | week 12
| Blocking | ASP concept is complete and agreed by ASP team | in escalating |  |  | ASP concept was already received by Claus Nielsen and looks ok | dHW, ASP team, QM | week 12
AD - T. Lange |  | Check later
ST MO - F. Kokholm | Declared
ST SW - Yang Li | Declared | Declaration paper will be uploaded Mar 29
|  | Finalized featurelist needed | Close | Will be available before March 17
|  | Finalized number of SW variants for VF |  | Currently looks like max 25, customization will be very limited |  | Decided: max 19 | Sean,Monika | 2006-03-25
| critical | Primavera plan needs Bjarne support
ST TA - Wei Xue Kai | Declared | Declaration paper will be uploaded Mar 29
Documents like peformance description needed
|  | Primavera detailed planning |  | Will be checked by planner before Mar. 25
CC - H. Boll |  | Declaration paper will be uploaded at Mar 29th
VPM - K. Falkenberger |  | No blocking point. Declaration paper should be followed |  |  |  | Ask for the declaration papter | Zhang Shuai | Mar 29th
|  | Hardware variant is not fixed (logo on battery cover) | closed |  |  |  | Monika,VF
| Critical | Software variants not fixed |  |  |  |  | Monika,VF
GPM - Frans Billich |  | Same status as VPM
PE - M. Svendsen |  | Declaration paper will be uploaded at Mar 29th
BA - Jie gao |  | Waiting for business case. Declaration paper may come at Mar 30th |  |  |  | Ask Gao Jie for declaration paper. Suppose declaration paper coming Mar 30th | Koh KhengWah | Mar 29th
|  | Current R&D budget |  | PMC data. Jerry PMC has been closed for M1
| Critical | Contract status with VF (volume, price, penalties, etc) | Open | Original target was end of March. Now VF insists on timeline improval | Contract preparations are already done. Signature may come after M1 |  | Koh Kheng Wah
Volumn is still 150k for the first 3 months
VF payment for 630 samples is not in contract at the moment
PL-T - Broeze, Song, Bonde
| Blocking | complete project primavera details plan should show the DS within Sep
|  | Put the operator approval into primavera plan |  |  |  | Add a extra activity into the primavera | Lars Bonde | Mar 30th
CPM - K. W. Koh
| Critical | Contract with VF is not finalized |  |  |  |  | Koh Kheng Wah, Gary Vincent | ?
| Blocking | Commited project plan from PD team with fixed DS date | Open
Planning - B. L. Thomsen
| Blocking | Current DS date is still Oct 11th by Mar 29th
| Critical | PPLs need to update the primavera plan especialy for the hours and missing expected finish date, data date and so on
LCM1 - Jens Riedel |  | Declaration paper will follow SDQM
|  | dispo variant should be in place | Done |  |  | Should be available latest middle/end of april | Poul Erik | 2006.03.28
|  | does VF accept delivery out of SSMC? | Done |  |  | Koh Kheng Wah will check | Koh Kheng Wah | 2006.03.20
15k may be configured in KLF may after M1 for rebooting and box. Curent assumption is SSMC will do the mass production
LCM3 - K. Hilker | Declared | Commited result out of production and test workshop is available | ongoing | assembly - DONE board-level-test DONE phone-level-test - planned for CW11 | commited result for device-level-test expected by end of CW11 |  |  | 2006-03-20
| Critical | Detailed Primavera project plan up to M3/S4 is available, showing dedicated resources by name and/or on department level for external consultants | ongoing | not all resources in BMS are available in Primavera
| Critical | Packaging concept is fixed and ensures a manual and automatic packaging, a hint is placed in the performance list (PM) | ongoing | decision about package box needed
|  | The assembly concept ensures a manual and automatic assembling of the Components; a hint is placed in the performance list (PM) | Closed | we agreed in the assembly WS that all trays have to fulfill the requirements described in GTTD61119 |  | hint has to be placed in the performance list | Lars Bonde | M1
|  | 70% 3D Data in supplier safe available | Done | at least 50% data must be available in supplier safe |  |  | Christian P. Nielsen | M1
|  | Prototype volumes and dates are agreed | Done | mainly volume is missing |  | TPM has to provide prototype volumes | Poul Erik Rask | 2006-03-17
|  | Budget plan is agreed | Done | has to be done after volumes are fixed |  | TPM has to provide prototype volumes | Poul Erik Rask | 2006-03-17
|  | Prototype shop sites and volume split is defined | Done | prototype shop is BMK until A1+ and BMS effective from B1 - volumes still missing |  | TPM has to provide prototype volumes | Poul Erik Rask | 2006-03-17
|  | Milestone planning is in accordance with prototype runs, PTR, FRT, ramp up plan and ramp up volume | Done | ramp up plan will be updated for M1 and PTR and FRT need to be checked, duration of prototype runs to be checked after volumes are fixed |  | TPM has to provide prototype volumes | Poul Erik Rask | 2006-03-17
| Critical | Make-or-Buy decision for VF logo on battery cover needed | open |  | because of the shape a misalignment of the logo on the battery cover is critical | TPM have to find out the expected variance of the battery cover. Needs to be finalized until S15 | Lars Bonde | 2006-03-17
| Critical | Decision if tape on earpiece is really needed | open |  |  | Tolerance calculation has to be done | Christian P. Nielsen | M1
|  | Evaluate feasibility to use a standard SW for production in Jerry | open | a stable version of the mobile SW will be used in production - phones are re-booted in CI with new SW versions SMT/board-test/device-test will use stable SW and are not influenced by SW changes |  | check expected SW for re-booting and decide if a standard SW for production makes sense | Allan Hansen, Katharina Hilker, Lars Bonde | M1
|  | Quality targets for production have to be added to performance description | open
SD QM - Thomas Limbach
| Blocking | Second source for keypad is missing | Open |  |  | Talk with Mr. Amann since Jerry only have 450k volumn in total | Arjen Broeze …. | Mar 29th
| Critical | Perlos and M-Tech fasibility study is open | Open |  |  | Talk with Perlos and M-tech | Thomas Limbach | Mar 29th
TPM - Shuai Zhang