## CA S0_M1
Conformance assessment milestone S0/M1 |  | Jerry |  |  |  | Major
Additional risks, miscellaneous |  | Name of PPL |  |  |  | Major
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
It has been agreed to pass all relevant current ASP test cases, which is not yet clear whether they all can pass Risk not all test cases can be passed | Check programmer resources for bug fixing and implementation of possible needed ASP requirements | PLT/SW PL | ongoing |  |  | 2
Very tight time schedule, specially for mechanics. High risk that problems caused by mechanical solutions will delay DS. | Strong monitoring of all tests and test reports. Initiate immediate corrective actions as soon as any problems occur | MD/QM | ongoing |  | Delay on DS | 2
There is a risk that Jerry will not pass all relevant current GCF test cases version 3.21.1 (or latest) Test cases for version 3.21.1 not yet tested with C75 and SP65 | Check programmer resources for bug fixing | PLT/SW PL/ST | ongoing |  |  | 2
Radio | M.Brammer |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
No risk | [5 empty] | 1
EMC antenna | Arne Bisgaard Kristensen |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
No risk | [5 empty] | 1
Digital and mixed signal HW | Flemming Bach Kristensen |  |  |  |  | Major
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
Design for the keypad lock is on the limit, i.e. no tolerances for locked/unlocked detection | Check on B1 samples and during B1 tests | Christian P. Nielsen | B1 |  |  | 2
Software | Yang Yong Qiang |  |  |  |  | Major
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
SW requirements from VF difficult to get closed. Replanning might be necessary --> Some requirements are still open | Measures to be defined until S15 | A.Broeze | S15 |  | Ressource and time line risk for unknown workpackages | 2
Resources provided by department up tp M3 --> Resources/effort for bugfixing are not covered yet | Measures to be defined until S15 | A.Broeze | S15 |  |  | 2
Test Plan WBIT (White Box Integration) available --> Feature driven test plan available. Not for WBIT | Measures to be defined until S15 | A.Broeze | S15 |  |  | 2
SW Variants: Operator specific MMI, MMI languages, SIM-Lock, Initialization, applications --> VF ODM product. Language group not yet finalized due to memory consumption | Measures to be defined until S15 | A.Broeze | S15 |  |  | 2
Resources provided by department up tp M3 --> Resources/effort for bugfixing are not covered yet --> CM and BM from AAL will leave Jerry end of May. New colleagues on BJ site not nominated yet | Measures to be defined until S15 | A.Broeze | S15 |  |  | 2
Automatically syncronisation between BJ and SISL database endangered due to firm policy. Exeption have to be given by top management. Manually syncronisation not sufficient due to timeline | Measures to be defined until S15 | A.Broeze | S15 |  |  | 2
Defect on Aries regarding protocol stack bug. (DT100135438). If valid for Jerry --> code cannot be corrected because it's owned by Comneon | Measures to be defined until S15 | A.Broeze | S15 |  |  | 2
13 Core Integration Team nominated (appointed specialists form CA, L1, PS and SP) --> -2 CIT members in BenQ are required, but only one candidate available. The other one is open. -PS support not yet finalized -No SP changes | Measures to be defined until S15 | A.Broeze | S15 |  |  | 2
Signal Processing | Allan Hansen |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
No risk | [5 empty] | 1
Mechanics | Christian P. Nielsen/Fu Ling Pin |  |  |  |  | Major
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
On/off key possible problems: # Microswitch for on/off key might be damaged during drops (shear off) # Button will not switch on/off the phone due to tolerances | # Perform design FMEA to identify reasonable measures --> done # Tolerance analysis # --> check during B1 tests | Christian P. Nielsen/Fu Lin Ping/T.Bartel | B1 |  | Product quality injured | 2
Potential acoustical leakage on speaker/back volume | # Perform design FMEA to identify reasonable measures # to finalize concept --> done # --> check on B1 samples | Christian P. Nielsen/Fu Lin Ping/T.Bartel | B1 |  | Product quality injured | 2
Slighter key (keypad lock) possible problems: # slider breakage during drop test # un-intended activation due to external magnetic force # activated in pocket due to low activation force # unstable function due to magnetic tolerance | Perform design FMEA to identify reasonable measures --> done # check during B1 tests | Christian P. Nielsen/Fu Lin Ping/T.Bartel | B1 |  | Product quality injured | 2
Function keys possible problems: # poor tactile feeling # light leakage around the decoration part | Perform design FMEA to identify reasonable measures --> done # check during B1 tests | Christian P. Nielsen/Fu Lin Ping/T.Bartel | B1 |  | Product quality injured | 2
Possible problem with MDF due to limited glueing surface area in upper part | to be checked during environmental tests | Christian P. Nielsen/Fu Lin Ping/T.Bartel | B1 |  | Product quality injured | 2
Uneven light illumination/distribution on simply keys | # Not clarified whether a SW simulation is possible at Perlos on time # To provide an additional LED in simply key area --> decision is needed --> accepted # --> Check on B1 samples | Christian P. Nielsen/Fu Lin Ping/T.Bartel | B1 |  | Product quality injured | 2
Possible rattling on soft keys and function keys | # extend rubber keypad in order to apply pre-tension # --> check on B1 samples | Christian P.Nielsen/Fu Lin Ping/T.Bartel | B1 |  | Product quality injured | 2
Layout/Production Data | Randi Bak, Dorte Nielsen |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
No risk | [5 empty] | 1
Procurement Engineering | Mariann Svendsen |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
Packing unit not finallized, VF has special requirements e.g. no UG but QSG and special box inlay | Clarify with VF and final agreement is needed | M. Reiss | 2006-04-07 |  |  | 1
SCM Production technology | Katharina Hilker |  |  |  |  | Major
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
Round VF label has to be glued on battery cover --> still not fixed for M1 need to be decided before S15 | Make-Or-Buy-Decision open | Bonde/Broeze/Song | S15 |  |  | 2
Packaging concept not fixed yet | Fix before S15 | Sara Song | S15 |  |  | 1
Number of expected variants still open, final decision until S15 needed |  | Bonde/Broeze/Song | S15 |  |  | 1
Evaluate concept for production avoiding misalignment |  | PT1 | S15 |  |  | 1
Evaluate feasibility in Jerry to use a standard SW for production |  | YongQiang Yang (SW), JingWen Gong (LCM3), Arjen Broeze, Sara Song (TPM) | S3 |  |  | 1
Display rotation by 180 degree: tape on earpiece needed; in-house assembly because earpiece is also used in other projects --> still not fixed for M1 | Tolerance calculation initiated: If possible avoid tape to save money | Christian P. Nielsen/Fu Lin Ping | S15 |  |  | 2
Material availability/SDQM | Thomas Limbach |  |  |  |  | Major
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
Detailed PV project plan up to M3/S4 is not available | Add resources from SSMC site | QM CI | S15 |  |  | 1
Only one keypad supplier chosen and fixed until M1 | Second keypad source (preferred Silitech or Topbound) must be qualified immediately after M1 | PE | S15 |  |  | 2
Material availability is not secured | Wrong supplier information and open points must be clarified from R & D | Arjen Broeze, Christian P. Nielsen | 2006-04-13 |  |  | 2
Quality Management | Thomas Bartel |  |  |  |  | Major
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
Possible problem with MDF due to limited glueing surface area in upper part --> see MD | to be checked during environmental tests | T.Bartel | B1 |  |  | 2
Potential mechanical problems due to new concepts --> see MD | to be checked during environmental tests | T.Bartel | B1 |  |  | 2
System Test | Yang Li (ST1), Wie Xue Kai (ST2) |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
No risk | [5 empty] | 1
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
Number of SW variants for the key operator received from Global Product Managementare are not finalized yet. | Provide the missing information to ST | PLT, TPM, CPM |  |  |  | 1
Service | Heinz-Gerd Voelker |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
No risk | [5 empty] | 1
Accessories | Thorsten Lange |  |  |  |  | None/Minor
Problem description | Measure | Responsible | Due date | Date completed | Risk potential 1) | Milestone assessment 2)
No risk | [5 empty] | 1
1)e.g.: Time to Market delay; Returnrate rise; Additional R&D effort
2): Milestone assessment: Issues are ranked as follows:
Prohibitive |  | Milestone declaration not signed by COM MD QM. Milestone declaration blocked. State of emergency. Most strictly follow-up.
Major |  | Major deviation according to conformance assessment of COM MD QM.
None/Minor |  | Milestone declaration recom-mended or at least possible Action items in case of deviations o be tracked by SPM.
The Conformance Assessment will be issued by the responsible Quality Project Manager (QM Product Lifecycle). It is binding to the project team.
The final Round Table meeting in the project team has to take place one week prior to envisaged Milestone declaration at the latest.
The Product Generation Manager (PGM) or the PM / ODM Board members can overrule the milestone decision due to strategic reasons. In this case the decision maker takes all responsibility undivided. The decision maker has the responsibility to inform the MP