## M0-LCM1
M0 SCM-Milestone
Product: | Jerry
LCM 1 | Lifecycle Management |  |  | Mrs. Jakob | Date:
Sign:
LCM 1 | Lifecycle Management |  |  | Mr. Riedel | Date:
| Project Manager |  |  |  | Sign:
Herewith the M0 SCM-Milestone is
declared
[6 empty] | declared with restrictions | x
is not declared
LCM | Lifecycle Management |  |  | Mr. Dörne | Date
|  |  |  | (or substitute) | Sign
Short summary / comments:
Product will be produced in PHA
BMK LCM will drive project till M1 / S15
Distribution List:
TPM |  |  |  | Mr. Zhang Shuai
BO PL |  |  |  | n.n.
BA |  |  |  | Mr. Gao Jie |  | (w/o attachments)
LCM3 |  |  |  | Mrs.Hilker
SCM QM |  |  |  | Mr. Limbach
Attachment:
General Information
Milestones
| target | reached
M0 | 2006-02-24
S0 | 2006-03-10
M1 | 2006-03-21
S15 | 2006-04-25
S2 | 2006-07-18
M2
S25 | 2006-07-18
SCM-S3 | 2006-08-17
S3 | 2006-08-17
PS | 2006-09-08
DS | 2006-09-22
SCM-S4 | 2006-10-28
S4 | 2006-11-01
SCM-M3 | tbd
M3 | 2006-12-01
Planned prototype runs
Tape out date |  | Main | MMI | FPC
A1 |  | 2006-02-23 | no MMI
A1+ |  | 2006-04-06
B1 |  | 2006-05-15
B2 |  | 2006-06-27
Pilot |  | tbd
Prototype run date |  | PCB | Phone
A1 |  | 2006-03-09
A1+ |  | 2006-04-20
B1 |  | 2006-05-30 | 2006-06-02
B2 |  | 2006-07-12 | 2006-07-18
Volumes / Sites | [5 empty] | Ramp up plan:
Site | Peak Vol. | RU Date | Config Date | Transfer Date
Klf | not planned
SSMC | 50k | 2006-09-08 | 2006-09-22
Man | not planned
Checklist acc. to MEP
[7 empty] | Yes | No
| Available rules for D2C applied; deviations are listed | [5 empty] | x
| General concept for realization of customer variants defined (placing of customer logo, operator key, SW modifications etc…) | [5 empty] | x
| External assemblies have been defined. | [6 empty] | x
| Life cycle volumes, peak volumes and sales split and regions available | [5 empty] | x
| Production sites and RU factories are defined (according to SCM overall stategy driven by CM) | [5 empty] | x
| Team sensitized concerning restriction of production sites | [5 empty] | x
| Potential production sites are considered within supplier selection (e.g. assemblies) | [6 empty] | x
| Ramp Up Plan available on weekly basis (including ramp up locations and configuration /rebooting scenario) | [5 empty] | x
| Draft Logistics concept available concerning production site, configuration sites | [5 empty] | x
| Number of HW / Design variants (IDs) defined | [6 empty] | x
| Product related second solutions and second sources agreed with Procurement | [5 empty] | x
| Maximum monthly capacity has been defined (incl.needed upside flexibility) | [5 empty] | x
| Conversion cost re-evaluated be SD BA | [5 empty] | x
| Part declaration OFE PP available | [6 empty] | x
| Part declaration SCM QM available | [5 empty] | x
Checklist internal
[7 empty] | Yes | No
| List of restrictions/ open points has been defined, AI adressed & scheduled | [5 empty] | x
| „Make or Buy” workshop held | [6 empty] | x
| Draft concept available concerning global supplier logistics | [6 empty] | x
| Ramp Up Plan and sales split communicated to CM and OP | [5 empty] | x
| Check of compatibility from Milestones with prototype runs, ramp up plan and ramp up volume done | [5 empty] | x
| SCM Team members until M1 defined and until M3 reserved | [5 empty] | x
| Project manager LCM1 has been designated by the department head | [5 empty] | x
| sub project leaders QM (project group) has been designated by the department head and resources reserved by the department up to S4 | [5 empty] | x
| M0 presentation and status report is in IMS available | [5 empty] | x
| SCM planning in PMC updated | [6 empty] | x
| SCM Team Kick Off held or scheduled | [5 empty] | x
| M0 LCM internal management review scheduled (2 weeks before declaration date) | [5 empty] | x
Action Items/ Restrictions
Action /Restriction/ Status |  |  |  | Owner |  | Date
External assemblies / make or buy not defined at M0 Will be finalized by M1 |  |  |  | PD |  | 2006-03-21
Supplier selection will be done by M1 |  |  |  | PD |  | 2006-03-21
1 design, 1 colour but variance of BC not defined yet, will be done by M1 |  |  |  | PD |  | 2006-03-21

## S0-LCM1
S0 SCM-Milestone
Product: | Jerry
LCM 1 | Lifecycle Management |  |  | Mrs. Jakob | Date:
Sign:
LCM 1 | Lifecycle Management |  |  | Mr. Riedel | Date:
| Project Manager |  |  |  | Sign:
Herewith the S0 SCM-Milestone is
declared
[6 empty] | declared with restrictions | x
is not declared
LCM | Lifecycle Management |  |  | Mr. Dörne | Date
|  |  |  | (or substitute) | Sign
Short summary / comments:
Distribution List:
TPM |  |  |  | Mr. Zhang Shuai
BO PL |  |  |  | n.n.
BA |  |  |  | Mr. Gao Jie |  | (w/o attachments)
LCM3 |  |  |  | Mrs.Hilker
SCM QM |  |  |  | Mr. Limbach
Attachment:
General Information
Milestones
| target | reached
M0 | 2006-02-24
S0 | 2006-03-10
M1 | 2006-03-21
S15 | 2006-04-25
S2 | 2006-07-18
M2
S25 | 2006-07-18
SCM-S3 | 2006-08-17
S3 | 2006-08-17
PS | 2006-09-08
DS | 2006-09-22
SCM-S4 | 2006-10-28
S4 | 2006-11-01
SCM-M3 | tbd
M3 | 2006-12-01
Planned prototype runs
Tape out date |  | Main | MMI | FPC
A1 |  | 2006-02-23 | no MMI
A1+ |  | 2006-03-21
B1 |  | 2006-05-05
B2 |  | 2006-06-21
Pilot |  | tbd
Prototype run date |  | PCB | Phone
A1 |  | 2006-03-09
A1+ |  | 2006-04-12
B1 |  | 2006-05-17 | 2006-05-22
B2 |  | 2006-07-03 | 2006-07-06
Volumes / Sites | [5 empty] | Ramp up plan:
Site | Peak Vol. | RU Date | Config Date | Transfer Date
Klf | not planned
SSMC | 50k | 2006-09-08 | 2006-09-22
Man | not planned
Checklist acc. to MEP
[7 empty] | Yes | No
| Available rules for Design to SD at S0 Phase applied; deviations are listed | [5 empty] | x
| General concept for realization of customer variants finalizied (placing of customer logo, operator key, SW modifications etc…) | [5 empty] | x
| Ramp up plan and sales split updated. | [5 empty] | x
| Conversion Costs have been re –evaluated by SCM BA | [5 empty] | x
| Production risks listed and communicated to project | [5 empty] | x
| Parts list available (delivery units) | [6 empty] | x
| Make or buy decision is available | [6 empty] | x
| Part declaration SCM QM available | [5 empty] | x
Checklist internal
[7 empty] | Yes | No
| Ramp up plan communicated to SD Team, CM and OP | [5 empty] | x
| Alignment with APE has been done | [5 empty] | x
| Alignment with factory material management has been done | [6 empty] | x
| SCM project presentation available in IMS | [5 empty] | x
| SCM-Kickoff and Design to SCM Workshop held, | [5 empty] | x
| List of restrictions/ open points has been defined, AI adressed & scheduled | [5 empty] | x
| "Make or buy" workshop results updated | [6 empty] | x
| S0 LCM internal management review held (2 weeks before declaration date) | [5 empty] | x
| BOM and lifecycle quantity communicated to MO SLL to start LSA negotiations | [5 empty] | x |  | Ansprechpartner MO- SLL: Fliege, Hardy | Redenbacher
Action Items/ Restrictions
Action /Restriction/ Status |  |  |  | Owner |  | Date
Make or buy decisions will be done by M1 |  |  |  | PD |  | 2006-03-21
Alignment with factory material management will be done 18 weeks before pilot |  |  |  | LCM1 |  | 2006-04-21
Dispo list delivery units required 18 weeks before demand / pilot |  |  |  | PD / VM |  | 2006-04-21

## M1-LCM1
M1 SCM-Milestone
Product: | Jerry
LCM 1 | Lifecycle Management |  |  | Mrs. Jakob | Date:
Sign:
LCM 1 | Lifecycle Management |  |  | Mr. Riedel | Date:
| Project Manager |  |  |  | Sign:
Herewith the M1 SCM-Milestone is
declared
[6 empty] | declared with restrictions |  | x
is not declared
LCM | Lifecycle Management |  |  | Mr. Dörne | Date
|  |  |  | (or substitute) | Sign
Short summary / comments:
LCM1 will handover to BMS by S15 (25.04.06)
Decision on limited reboot scenario (15k) in KLF open, CR required 10 weeks before rebooting
Supplier commitments will be finalized by April, 13th
Distribution List:
TPM |  |  |  | Mr. Zhang Shuai
BO PL |  |  |  | n.n.
BA |  |  |  | Mr. Gao Jie |  | (w/o attachments)
LCM3 |  |  |  | Mrs.Hilker
SCM QM |  |  |  | Mr. Limbach
Attachment:
General Information
Milestones
| target | reached
M0 | 2006-03-17 | 2006-03-17
S0 | 2006-03-17 | 2006-03-17
M1 | 2006-03-31 | 2006-04-07
S15 | 2006-04-25
S2 | 2006-07-18
M2 | 2006-06-22
S25 | 2006-06-22
SD-S3
S3 | 2006-08-17
PS | 2006-09-08
DS | 2006-09-22
SD-S4
S4 | 2006-11-01
SD-M3
M3 | 2006-12-01
Planned prototype runs
Tape out date |  | Main | MMI | FPC
A1 |  | 2006-02-23 | no MMI
A1+ |  | 2006-03-21
B1 |  | 2006-05-05
B2 |  | 2006-06-21
Pilot |  | tbd
Prototype run date |  | PCB | Phone
A1 |  | 2006-03-09
A1+ |  | 2006-04-12
B1 |  | 2006-05-17 | 2006-05-22
B2 |  | 2006-07-03 | 2006-07-06
Volumes / Sites | [5 empty] | Ramp up plan:
Site | Peak Vol. | RU Date | Config Date | Transfer Date
Klf | not planned
SSMC | 65k | 2006-09-08 | 2006-09-22
Man | not planned
Checklist acc. to MEP
[8 empty] | Yes | No
| Dispo-variants (design, colour) available in SAP KEP | [6 empty] | x
| Ramp-up planned updated in detail including dispo-variants, sales split and possible rebooting scenario available | [5 empty] | 1)2) |  | x
| Supplier concept for global production concept (planned production sites’) available | [7 empty] | x
| Schedule for variant specific Ramp up plan and/or No-ID Ramp Up plan including lead times of variants specific parts agreed in Rea Team | [6 empty] | x
| Milestone planning is in accordance with prototype runs, PTR, FRT, ramp up plan and ramp up volume | [6 empty] | x
| Conversion costs updated by SCM BA | [6 empty] | x
| Project specific lead times for components defines (i.e. upper and lower case) | [6 empty] | x
| Project specific decisions on necessity of plan variants made and lead time fixed | [6 empty] | x
| Additionally checkpoint in case of PS/DS scenario: Time schedule for milestones PS/DS available | [6 empty] | x
| Availability of qualified components is secured | [6 empty] | x
| Manufacturing capacities from the suppliers are reserved | [5 empty] | 6) |  | x
| Number of different assembled PCB variants fixed by TLM (flash memory, 2, RF solution) | [6 empty] | x
| Project list and critical component list defined/ distributed | [6 empty] | x
| Delta qualification process run for all RU site planned | [7 empty] | x
| Packaging-Concept is available and agreed with PM | [5 empty] | 5) |  | x
| Part declaration OFE PP available | [7 empty] | x
| Part declaration SD QM available | [6 empty] | x
Checklist internal
[8 empty] | Yes | No
| BSC (balanced scorecard) in IMS available | [7 empty] | x
| Ramp up plan and production locations confirmed by CM | [6 empty] | x
| Ramp up plan and production locations aligned with SD team | [6 empty] | x
| Agreed concept available concerning global supplier logistics | [6 empty] | x
| LSA for all parts and components available | [7 empty] | x
| M1 presentation and status report is in IMS available | [6 empty] | x
| M1 LCM internal management review held (2 weeks before declaration date) | [6 empty] | x
| Availability or resources LCM1 are until SD-M3 | [6 empty] | x
| List of restrictions/ open points has been defined, AI adressed & scheduled | [6 empty] | x
| Resource planning in PMC finalizied | [6 empty] | x
Action Items/ Restrictions
Action /Restriction/ Status |  |  |  | Owner |  | Date
1) Dispo planning will be started 18 weeks before Pilot run (incl. Alignment with MO) |  |  |  | LCM1 |  | 2006-04-21
2) Variant specific RU Plan will be started 10 weeks before Production |  |  |  | LCM1 |  | 2006-05-16
3) Decision on reboot scenario in KLF open CR required at least 10 weeks before rebooting |  |  |  | TPM / CPM |  | 2006-07-21
4) LCM1 handover to BMS by S15 |  |  |  | LCM1 |  | 2006-04-25
5) Packaging concept will be finalized by S15 |  |  |  | TPM |  | 2006-04-25
6) Supplier commitments to be finalized |  |  |  | PD / SCM QM |  | 2006-04-13
.
.

## S15-LCM1
S15 SCM-Milestone
Product: | Jerry
LCM 1 | Lifecycle Management |  |  | Mrs. Jakob | Date:
Sign:
LCM 1 | Lifecycle Management |  |  | Mr. | Date:
| Project Manager |  |  |  | Sign:
Herewith the S15 SCM-Milestone is
declared
declared with restrictions
is not declared
LCM | Lifecycle Management |  |  | Mr. Dörne | Date
|  |  |  | (or substitute) | Sign
Short summary / comments:
Distribution List:
SPM |  |  |  | Mr.
BO PL |  |  |  | Mr.
BA |  |  |  | Mr. |  | (w/o attachments)
LCM3 |  |  |  | Mr.
SCM QM |  |  |  | Mr.
Attachment:
General Information
Milestones
| target | reached
M0
S0
M1
S15
S2
M2
S25
SD-S3
S3
PS
DS
SD-S4
S4
SD-M3
M3
Planned prototype runs
Tape out |  | Main | MMI | FPC
A1
B1
B1+
B2
Pilot
Prototype run
A1
B1
B1+
B2
Volumes / Sites | [5 empty] | Ramp up plan:
Site | Peak Vol. | PS Date | Transfer Date
Klf
SSMC
Man
Checklist acc. to MEP
[7 empty] | Yes | No
Action items from M1 are closed or listed again
Ramp up szenario is according to M1 commitment
Part declaration SCM QM available
Checklist internal
[7 empty] | Yes | No
BSC (balanced scorecard) in IMS available
List of restrictions/ open points has been defined, AI adressed & scheduled
LCM internal management review held (2 weeks before declaration date)
Project status report is in IMS available
Action Items/ Restrictions
Action /Restriction/ Status |  |  |  | Owner |  | Date

## S2-LCM1
S2 SCM-Milestone
Product: | Jerry
LCM 1 | Lifecycle Management |  |  | Mrs. Jakob | Date:
Sign:
LCM 1 | Lifecycle Management |  |  | Mr. | Date:
| Project Manager |  |  |  | Sign:
Herewith the S2 SCM-Milestone is
declared
declared with restrictions
is not declared
LCM | Lifecycle Management |  |  | Mr. Dörne | Date
|  |  |  | (or substitute) | Sign
Short summary / comments:
Distribution List:
SPM |  |  |  | Mr.
BO PL |  |  |  | Mr.
BA |  |  |  | Mr. |  | (w/o attachments)
LCM3 |  |  |  | Mr.
SCM QM |  |  |  | Mr.
Attachment:
General Information
Milestones
| target | reached
M0
S0
M1
S15
S2
M2
S25
SD-S3
S3
PS
DS
SD-S4
S4
SD-M3
M3
Planned prototype runs
Tape out |  | Main | MMI | FPC
A1
B1
B1+
B2
Pilot
Prototype run
A1
B1
B1+
B2
Volumes / Sites | [5 empty] | Ramp up plan:
Site | Peak Vol. | PS Date | Transfer Date
Klf
SSMC
Man
Checklist acc. to MEP
[7 empty] | Yes | No
Ramp up upl including leadtime for critical components available
Customization guide from VM checked concerning impact to SD
Action items from S15 are closed or listed again
Declaration of SCM QM available
Checklist internal
[7 empty] | Yes | No
BSC (balanced scorecard) in IMS available
Alignment with factory material management has been done
Project list and critical component list updated/ distributed
List of restrictions/ open points has been defined, AI adressed & scheduled
Project status report is in IMS available
LCM internal management review held (2 weeks before declaration date)
Action Items/ Restrictions
Action /Restriction/ Status |  |  |  | Owner |  | Date

## S25-LCM1
S25 SCM-Milestone
Product: | Jerry
LCM 1 | Lifecycle Management |  |  | Mrs. Jakob | Date:
Sign:
LCM 1 | Lifecycle Management |  |  | Mr. | Date:
| Project Manager |  |  |  | Sign:
Herewith the S25 SCM-Milestone is
declared
declared with restrictions
is not declared
LCM | Lifecycle Management |  |  | Mr. Dörne | Date
|  |  |  | (or substitute) | Sign
Short summary / comments:
Distribution List:
SPM |  |  |  | Mr.
BO PL |  |  |  | Mr.
BA |  |  |  | Mr. |  | (w/o attachments)
LCM3 |  |  |  | Mr.
SCM QM |  |  |  | Mr.
Attachment:
General Information
Milestones
| target | reached
M0
S0
M1
S15
S2
M2
S25
SD-S3
S3
PS
DS
SD-S4
S4
SD-M3
M3
Planned prototype runs
Tape out |  | Main | MMI | FPC
A1
B1
B1+
B2
Pilot
Prototype run
A1
B1
B1+
B2
Volumes / Sites | [5 empty] | Ramp up plan:
Site | Peak Vol. | PS Date | Transfer Date
Klf
SSMC
Man
Checklist acc. to MEP
[7 empty] | Yes | No
Ramp up szenario is according to M1 commitment- commitment for deviations available
Ramp-up locations and quantities are confirmed and aligned SD-Team
Declaration of SD QM available
Checklist internal
[7 empty] | Yes | No
BSC (balanced scorecard) in IMS available
Project list and critical component list update distributed
List of restrictions/ open points has been defined, AI adressed & scheduled
Project status report is in IMS available
LCM internal management review held (2 weeks before declaration date)
Action Items/ Restrictions
Action /Restriction/ Status |  |  |  | Owner |  | Date

## M2-LCM1
M2 SCM-Milestone
Product: | Jerry
LCM 1 | Lifecycle Management |  |  | Mrs. Jakob | Date:
Sign:
LCM 1 | Lifecycle Management |  |  | Mr. | Date:
| Project Manager |  |  |  | Sign:
Herewith the M2 SCM-Milestone is
declared
declared with restrictions
is not declared
LCM | Lifecycle Management |  |  | Mr. Dörne | Date
|  |  |  | (or substitute) | Sign
Short summary / comments:
Distribution List:
SPM |  |  |  | Mr.
BO PL |  |  |  | Mr.
BA |  |  |  | Mr. |  | (w/o attachments)
LCM3 |  |  |  | Mr.
SCM QM |  |  |  | Mr.
Attachment:
General Information
Milestones
| target | reached
M0
S0
M1
S15
S2
M2
S25
SD-S3
S3
PS
DS
SD-S4
S4
SD-M3
M3
Planned prototype runs
Tape out |  | Main | MMI | FPC
A1
B1
B1+
B2
Pilot
Prototype run
A1
B1
B1+
B2
Volumes / Sites | [5 empty] | Ramp up plan:
Site | Peak Vol. | PS Date | Transfer Date
Klf
SSMC
Man
Checklist acc. to MEP
[7 empty] | Yes | No
Sale forcast and area split confirmed and available
Ramp-up locations and quantities are confirmed
Ramp-up quantities per variant per week to Marketing/ Sales communicated
Variant specific Ramp-up plan available and agreed in REA-team
Configuration start and DS confirmed
OFE PP prepared for order confirmation
Checklist internal
[7 empty] | Yes | No
Project list and critical component list update distributed
Ramp up plan communicated to SD Team, CM and OP
BSC in IMS available
Alignment with factory material management has been done
List of restrictions/ open points has been defined, AI adressed & scheduled
Action items from S25 are closed or listed again
LCM internal management review held (2 weeks before declaration date)
Project status report is in IMS available
Action Items/ Restrictions
Action /Restriction/ Status |  |  |  | Owner |  | Date

## S3HW-LCM1
S3HW SCM-Milestone
Product: | Jerry
LCM 1 | Lifecycle Management |  |  | Mrs. Jakob | Date:
Sign:
LCM 1 | Lifecycle Management |  |  | Mr. | Date:
| Project Manager |  |  |  | Sign:
Herewith the S3HW SCM-Milestone is
declared
declared with restrictions
is not declared
LCM | Lifecycle Management |  |  | Mr. Dörne | Date
|  |  |  | (or substitute) | Sign
Short summary / comments:
Distribution List:
SPM |  |  |  | Mr.
BO PL |  |  |  | Mr.
BA |  |  |  | Mr. |  | (w/o attachments)
LCM3 |  |  |  | Mr.
SCM QM |  |  |  | Mr.
Attachment:
General Information
Milestones
| target | reached
M0
S0
M1
S15
S2
M2
S25
SD-S3
S3
PS
DS
SD-S4
S4
SD-M3
M3
Planned prototype runs
Tape out |  | Main | MMI | FPC
A1
B1
B1+
B2
Pilot
Prototype run
A1
B1
B1+
B2
Volumes / Sites | [5 empty] | Ramp up plan:
Site | Peak Vol. | PS Date | Transfer Date
Klf
SSMC
Man
Checklist acc. to MEP
[7 empty] | Yes | No
Variants for pilot run released
Fine RU planning for pilot series available
Alignment of RU planning/ order situation with Rea Team done
Material for RU secured/ material for pilot run on stock
Part declaration SCM QM available
Checklist internal
[7 empty] | Yes | No
Project list and critical component list update distributed
BSC in IMS available
Ramp up plan communicated to SCM Team, CM and OP
Alignment with factory material management has been done
List of restrictions/ open points has been defined, AI adressed & scheduled
Action items from S25 are closed or listed again
Project status report is in IMS available
LCM internal management review held (2 weeks before declaration date)
Action Items/ Restrictions
Action /Restriction/ Status |  |  |  | Owner |  | Date

## PS-LCM1
PS SCM-Milestone
Product: | Jerry
LCM 1 | Lifecycle Management |  |  | Mrs. Jakob | Date:
Sign:
LCM 1 | Lifecycle Management |  |  | Mr. | Date:
| Project Manager |  |  |  | Sign:
Herewith the PS SCM-Milestone is
declared
declared with restrictions
is not declared
LCM | Lifecycle Management |  |  | Mr. Dörne | Date
|  |  |  | (or substitute) | Sign
Short summary / comments:
Distribution List:
SPM |  |  |  | Mr.
BO PL |  |  |  | Mr.
BA |  |  |  | Mr. |  | (w/o attachments)
LCM3 |  |  |  | Mr.
SCM QM |  |  |  | Mr.
Attachment:
General Information
Milestones
| target | reached
M0
S0
M1
S15
S2
M2
S25
SD-S3
S3
PS
DS
SD-S4
S4
SD-M3
M3
Planned prototype runs
Tape out |  | Main | MMI | FPC
A1
B1
B1+
B2
Pilot
Prototype run
A1
B1
B1+
B2
Volumes / Sites | [5 empty] | Ramp up plan:
Site | Peak Vol. | PS Date | Transfer Date
Klf
SSMC
Man
Checklist acc. to MEP
[7 empty] | Yes | No
Material for RU secured/ material on stock (at least two weeks) deviations listed
Fine RU planning with SCM and Rea-team is done
Variants for production released (Status 20 KEP) two weeks in advance
Primary disposition (status 3(2)) updated- planning >3 month
Stock/production plan, delivery preview updated
Indicate status of discontinuance
Order handling sequence tested
Pilot run for config center scheduled
Part declaration SCM QM available
Checklist internal
[7 empty] | Yes | No
BSC in IMS available
SW for production start available and released 5 working days before ps
Declaration of OFE PP available
List of restrictions/ open points has been defined, AI adressed & scheduled
Action items from S3HW are closed or listed again
Project list and critical component list update distributed
Ramp up plan communicated to SCM Team, CM and OP
Alignment with factory material management has been done
Project status report is in IMS available
LCM internal management review held (2 weeks before declaration date)
Action Items/ Restrictions
Action /Restriction/ Status |  |  |  | Owner |  | Date

## S3-LCM1
S3 SCM-Milestone
Product: | Jerry
LCM 1 | Lifecycle Management |  |  | Mrs. Jakob | Date:
Sign:
LCM 1 | Lifecycle Management |  |  | Mr. | Date:
| Project Manager |  |  |  | Sign:
Herewith the S3 SCM-Milestone is
declared
declared with restrictions
is not declared
LCM | Lifecycle Management |  |  | Mr. Dörne | Date
|  |  |  | (or substitute) | Sign
Short summary / comments:
Distribution List:
SPM |  |  |  | Mr.
BO PL |  |  |  | Mr.
BA |  |  |  | Mr. |  | (w/o attachments)
LCM3 |  |  |  | Mr.
SCM QM |  |  |  | Mr.
Attachment:
General Information
Milestones
| target | reached
M0
S0
M1
S15
S2
M2
S25
SD-S3
S3
PS
DS
SD-S4
S4
SD-M3
M3
Planned prototype runs
Tape out |  | Main | MMI | FPC
A1
B1
B1+
B2
Pilot
Prototype run
A1
B1
B1+
B2
Volumes / Sites | [5 empty] | Ramp up plan:
Site | Peak Vol. | PS Date | Transfer Date
Klf
SSMC
Man
Checklist acc. to MEP
[7 empty] | Yes | No
Alignment of RU planning with Rea Team done
Part declaration QM available
Checklist internal
[7 empty] | Yes | No
BSC in IMS available
Ramp up plan communicated to SCM Team, CM and OP
List of restrictions/ open points has been defined
Project status report is in IMS available
LCM internal management review held (2 weeks before declaration date)
Action Items/ Restrictions
Action /Restriction/ Status |  |  |  | Owner |  | Date

## DS-LCM1
DS SCM-Milestone
Product: | Jerry
LCM 1 | Lifecycle Management |  |  | Mrs. Jakob | Date:
Sign:
LCM 1 | Lifecycle Management |  |  | Mr. | Date:
| Project Manager |  |  |  | Sign:
Herewith the DS SCM-Milestone is
declared
declared with restrictions
is not declared
LCM | Lifecycle Management |  |  | Mr. Dörne | Date
|  |  |  | (or substitute) | Sign
Short summary / comments:
Distribution List:
SPM |  |  |  | Mr.
BO PL |  |  |  | Mr.
BA |  |  |  | Mr. |  | (w/o attachments)
LCM3 |  |  |  | Mr.
SCM QM |  |  |  | Mr.
Attachment:
General Information
Milestones
| target | reached
M0
S0
M1
S15
S2
M2
S25
SD-S3
S3
PS
DS
SD-S4
S4
SD-M3
M3
Planned prototype runs
Tape out |  | Main | MMI | FPC
A1
B1
B1+
B2
Pilot
Prototype run
A1
B1
B1+
B2
Volumes / Sites | [5 empty] | Ramp up plan:
Site | Peak Vol. | PS Date | Transfer Date
Klf
SSMC
Man
Checklist acc. to MEP
[7 empty] | Yes | No
Material for RU secured/ material on stock (at least two weeks) deviations listed
Fine RU planning with SCM and Rea-team is done
Variants for production released (Status 20 KEP) two weeks in advance
Release for delivering variants to customer before S4 by PM/ CCQ available
Conversion cost are updated by SCM BA
Declaration of OFE PP available
Part declaration SCM QM available
Checklist internal
[7 empty] | Yes | No
BSC in IMS available
SW for production start available and released 5 working days before DS
Production capacity for reboot szenario secured
Ramp up plan communicated to SCM Team, CM and OP
List of restrictions/ open points has been defined
Project status report is in IMS available
LCM internal management review held (2 weeks before declaration date)
Action Items/ Restrictions
Action /Restriction/ Status |  |  |  | Owner |  | Date

## S4-LCM1
S4 SCM-Milestone
Product: | Jerry
LCM 1 | Lifecycle Management |  |  | Mrs. Jakob | Date:
Sign:
LCM 1 | Lifecycle Management |  |  | Mr. | Date:
| Project Manager |  |  |  | Sign:
Herewith the S4 SCM-Milestone is
declared
declared with restrictions
is not declared
LCM | Lifecycle Management |  |  | Mr. Dörne | Date
|  |  |  | (or substitute) | Sign
Short summary / comments:
Distribution List:
SPM |  |  |  | Mr.
BO PL |  |  |  | Mr.
BA |  |  |  | Mr. |  | (w/o attachments)
LCM3 |  |  |  | Mr.
SCM QM |  |  |  | Mr.
TLM CM |  |  |  | Mr.
Attachment:
General Information
Milestones
| target | reached
M0
S0
M1
S15
S2
M2
S25
SD-S3
S3
PS
DS
SD-S4
S4
SD-M3
M3
Planned prototype runs
Tape out |  | Main | MMI | FPC
A1
B1
B1+
B2
Pilot
Prototype run
A1
B1
B1+
B2
Volumes / Sites | [5 empty] | Ramp up plan:
Site | Peak Vol. | PS Date | Transfer Date
Klf
SSMC
Man
Checklist acc. to MEP
[7 empty] | Yes | No
Conversion cost are updated by SCM BA
Handover declaration from LCM1 to FKMM/ SLO available open issues solved
Declaration of OFE PP available
End of RU defined, handover to line organisation scheduled
Review / alignment of ramp-up plan has been done
Part declaration SCM QM available
Checklist internal
[7 empty] | Yes | No
Lessons learnt workshop scheduled
Action Items/ Restrictions
Action /Restriction/ Status |  |  |  | Owner |  | Date