## CA M0
Conformance assessment milestone M0 | Obsidian |  |  | Additional risk costs | 0 | Major
Additional risks, miscellaneous | Name
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
Radio | [5 empty] | Major
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
Performance of B6PLA platform not sufficient.Change is needed. | Lind Møller Mortensen | S0 |  | Time delay |  | 2
EMC antenna | [5 empty] | None/Minor
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
No comment | Arne Bisgaard Christensen |  |  |  |  | 1
Logic | [5 empty] | Major
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
New battery 720mAh need to be implemented to get enough standby time. | Trine Bech Lendrup | S0 |  | Time delay |  | 2
Speaker deliveries for ramp up not secured | Trine Bech Lendrup | S0 |  | Time delay |  | 1
Software | [5 empty] | None/Minor
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
Independent FM radio can introduce serious ASP issues.The volume of the FM radio will be unknown to the phone. | Carsten Termansen | S0 |  | Safety risk |  | 1
Swift using 2 speakers solution.Obsidian use one speaker>introduces ASP implementations. | Carsten Termansen | S0 |  | Safety risk |  | 1
FM headset .Interaction with phone not totally specified.FM radio control not part of phone MMI | Carsten Termansen | S0 |  | Time delay |  | 1
Project plan to follow Swift as much as possible> CR accepted for Swift will also have impact on Obsidian> can have impact on Obsidian timeline, without the possibility to reject the CR | Carsten Termansen | S0 |  | Time delay |  | 1
Mechanical Design | [5 empty] | Major
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
PVD coating.No expierence with antenna transparent PVD coating , productionyield and quality level | Erik Højfeldt | S0 |  | Time delay |  | 2
Camera design robustness.Camera design is raised 2mm and sensitive to drop and static load | Erik Højfeldt | S0 |  | Higher return rate |  | 2
Nano I/O connector sensitive to mechanical forces.Not as strong as old I/O connector | Erik Højfeldt | S0 |  | Higher return rate |  | 1
T flash reader not qualified | Erik Højfeldt | S0 |  | Time delay |  | 1
Time schedule is very critical(Only 2 month for correction) | Erik Højfeldt | M1 |  | Time delay |  | 2
Layout Production Data | [5 empty] | None/Minor
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
Layout for RF shield is missing | Randi Bak | S0 |  | Time delay |  | 1
Global Sourcing | [5 empty] | None/minor
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
No standard battery can be used | Robert Mølgaard | S0 |  | Time delay |  | 1
PVD shall be use as surface on mechanical parts | Robert Mølgaard | M1 |  | Time delay and cost impact |  | 1
LCM3 Production technology | [5 empty] | None/Minor
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
No Id concept not available | Josef Schwarz | S0 |  | Time delay |  | 1
Production of MMI board at BenQ/KLF side under investigation | Josef Schwarz | S0 |  |  |  | 1
SD QM Material /process | [5 empty] | None/Minor
No comment | Juergen Krell |  |  |  |  | 1
Quality Management | [5 empty] | Major
Look at other departments | Poul Søndergaard |  |  |  |  | 2
System Test | [5 empty] | None/Minor
No comment | Steen Hansen |  |  |  |  | 1
Service
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
1)e.g.: Time to Market delay; Returnrate rise; Additional R&D effort
2): Milestone assessment: Issues are ranked as follows:
prohibitive | M | milestone declaration is blocked from QM due to severe risks, Management Decision neccesary
major (2) | K | milestone declaration possible, conditions have to be closed at due date at the latest, tracking of conditions in project team.
none (1) | J | milestone declaration recommended
The Conformance Assessment will be issued by the responsible Quality Project Manager (QM Product Lifecycle). It is binding to the project team.
The final Round Table meeting in the project team has to take place one week prior to envisaged Milestone declaration at the latest.
The Product Generation Manager (PGM) or the PM / ODM Board members can overrule the milestone decision due to strategic reasons. In this case the decision maker takes all responsibility undivided. The decision maker has the responsibility to inform the MP