M1 Milestone – Implementation Release

SCM QM Material/Process

Project: Obsidian

Material:

PD Team Project Manager (SCM QM Pro): 	Kay-Uwe Clemens; J. Krell

Process:

SD Team Project Manager (SCM QM CI): 	Harald Pressmann

The M1- SCM QM is; declared. declared with restrictions. not declared. Main restriction : Material disposition of housing & assembly parts is very risky: delivery only 5 calendar days before due date; no modification after B2 prerequisite -> Needs to be monitored frequently (every milestone)! Milestone planning is based on best case scenario Risk estimation: postpone RU one week -> ~70k less mobile phones in September 2006 #### Date of declaration: 14.03.2006 SIGNATORIES SCM QM; SCM QM Material; SCM QM CI. (Project Manager PD Team); (Project Manager SD Team). Date/signature; Date/Signature; Date/Signature.

Copies:

SD TLM LCM1

PL T

Signatories

Checklist M1- SCM QM Material Milestone

| No. | Own Milestone Requirements | Status | Owner | Ref to Restriction No |
| --- | --- | --- | --- | --- |
| 10.4.1.1 | Qualification of new components has been started | Yes | QM PRO |  |
| 10.4.1.2 | QAA initialized with supplier | Yes | QM PRO |  |
| 10.4.1.3 | Project list an critical parts list created | Yes | QM PRO |  |
| 10.4.1.4 | Specifications /Draft TTD’s are available for all new components | Yes | QM PRO |  |
| 10.4.2.1 | Detailed Primavera project plan up to M3/S4 is available, showing dedicated resources by name and on department level for external consultants | Yes | QM PRO/ CI |  |
| 10.4.28 | List of restrictions and open points has been made | Yes | QM PRO/ CI |  |
| No. | Pre- requisites from other Groups | Status | Owner | Ref to Restriction No |
| 10.4.11 | Availability of new components based on feasibility study and qualification plan is secured | Yes | SQA |  |
| 10.4.23 | Life cycle quantity has been updated | Yes | LCM1 |  |
| 10.4.24 | Maximum monthly peak of units has been updated | Yes, with restriction | LCM1 | 6 |
| 10.4.26 | External assemblies have been defined | Yes | LCM3 |  |
| 10.4.22 | Alignment with SP has been done | Yes | PE |  |
| 10.6.14 | Maximum monthly peak capacity of supplied material has been defined | Yes | PE |  |
| 10.4.14 | Different hardware variants have been defined (e.g. RF-Solutions, Flashes) | Yes | PE |  |
| 10.4.25 | Suppliers including second source and supplier share have been fixed | Yes | PE |  |
| 10.4.13 | Manufacturing capacity of new project specific components is secured | Yes | PE | for housing see 4 & 5 |

Time-Schedule

|  | target | reached |
| --- | --- | --- |
|  |  | (target) |
| M0 | 25.11.2005 | 02.12.2005 |
| S0 | 23.12.2005 | 03.02.2006 |
| M1 | 20.01.2006 | (03.03.2006) |
| S15 | 10.03.2006 |  |
| S2 | 18.05.2006 |  |
| S25 | 17.07.2006 |  |
| SD-S3 | 17.08.2006 |  |
| S3 | 18.08.2006 |  |
| PS | 01.09.2006 |  |
| DS | 08.09.2006 |  |
| SD-S4 | 19.10.2006 |  |
| S4 | 19.10.2006 |  |
| SD-M3 | 19.10.2006 |  |
| M3 | 19.10.2006 |  |

Ramp Up Plan

To change until end of CW11 by LCM

Restrictions / Open Points

| No. | Problem | Actions | Owner | Target Date | Comments |
| --- | --- | --- | --- | --- | --- |
| 1 | PVD Coating has to be non conductive | - Install test at supplier - Influence of PVD Coating (thickness of coating) regarding antenna performance has to be tested | SQA MD; EMC | done S2 | Supplier : Greenpoint / Lumberg |
| 2 | Clear responsibility regarding used lacque | - Supplier of paint has to be fixed by Nolato | MD, SQA | S4 |  |
| 3 | Material disposition of housing & assembly parts is very risky: delivery only 5 calendar days before due date | - no modification after B2 prerequisite - Needs to be monitored frequently | MD LCM | every Milestone | Milestone planning is based on best case scenario Risk estimation: postpone RU one week -> ~70k less mobile phones in September 2006 |
| 4 | “Speaker fixing not correct” notes in Lumberg commitment | Statement from MD : Will be checked with B1 samples Statement from SQA: Early stage of 3D Datas already available at supplier. Introducing of changings is possible to solve until B1. | MD, SQA | B1 | MD and Lumberg has to solve it together and MD has to inform SQA about it. |
| 5 | Statement from Nolato regarding their Feasibility Commitment : … there are certain assumptions made in this plan. In connection to your R&D schedule this makes up to some risks. - Only very minor modification (5 days) allowed in UC + BC. - Only very minor or no modification allowed on Window, started earlier than planned B1+ data release. - No B2 modification allowed on Camera Decoration. - Camera Decoration tool start 2 weeks earlier than planned B1+ data release. - There is no time to evaluate painted UC + BC after B2 modifications before the tools need to be transferred to Nolato Alpha. - Volume production will start before BenQ B2 verification is ready based on limited releases. - There are no modifications allowed after B2. |  |  |  |  |
| 6 | Current RU Plan is agreed from supplier but not yet revised by LCM. | Statement from LCM: The current RU Plan will be available end of CW 11 | LCM 1 | CW11 | The RU Plan has to follow the absolutly peak of 90k per week at maximum. |