## CA M1
E71ObsidianConformance assessment milestone M1 |  |  |  | Additional risk costs | 1 | Major
Additional risks, miscellaneous | Name
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
Radio | [5 empty] | None/minor
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
No comment | Lind Møller Mortensen |  |  |  |  | 1
EMC antenna | [5 empty] | None/minor
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
No comment | Arne Bisgaard Kristensen |  |  |  |  | 1
Logic | [5 empty] | None/minor
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
Epson display development is set on hold.Unclear if Epson can deliver for ramp up. | Trin Bech Lendrup | S2 |  | Time delay |  | 1
Software | [5 empty] | None/minor
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
Possible update of firmware can introduce new ASP settings | Lars Termansen | S2 |  | Time delay |  | 1
CM plan strongly depended of swift DB | Lars Termansen | S2 |  | Time delay | 1 | 1
Problems in Swift such as feature cutting will also be true for Obsidian | Lars Termansen | S2 |  | Time delay |  | 1
Ressources for FM radio not Obsidian as first prioity | Lars Termansen | S2 |  | Time delay |  | 1
Requirement from PM regarding accessory "Carkit line fit" not committed by SW.Can be introduced by CR | Lars Termansen | S2 |  | Time delay |  | 1
Mechanical Design | [5 empty] | Major
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
Time schedule is very critical(Only 2 month for correction) | Christian Dupont | S2 |  | Time delay |  | 2
Camera design robustness.Camera design is raised 2mm and sensitive to drop and static load | Christian Dupont | S2 |  | Time delay |  | 1
PVD coating.No expierence with antenna transparent PVD coating , productionyield and quality level | Christian Dupont | S2 |  | Time delay |  | 1
Risk of mechanical noise, because 2 hooks is implemented in the middle instead of 2 screws | Christian Dupont | S2 |  | Time delay |  | 2
Speaker fixing during transportation not fixed | Christian Dupont | S2 |  | Time delay |  | 1
Layout Production Data | [5 empty] | None/minor
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
No comment | Randi Bak |  |  |  |  | 1
Global Sourcing | [5 empty] | None/minor
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
Capacity for mechanical parts and display not secured | Robert Mølgaard | S2 |  | Time delay |  | 1
Display second source unclear | Robert Mølgaard | S2 |  | Time delay |  | 1
Second supplier battery not finally selected | Robert Mølgaard | S2 |  | Time delay |  | 1
PVD coating is a new process at BenQ | Robert Mølgaard | S2 |  | Time delay |  | 1
LCM3 Production technology | [5 empty] | None/minor
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
No comment | Josef Schwarz |  |  |  |  | 1
SD QM Material availability | [5 empty] | Major
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
Material disposition of housing & assembly is very risky,delivery only 5 days before due date | Jurgen Krell | S2 |  | Time delay |  | 2
No modifications is allowed after B2 run | Jurgen Krell | S2 |  | Time delay |  | 2
Quality Management | [5 empty] | Major
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
Look at other departments | Poul Søndergaard |  |  |  |  | 2
System Test | [5 empty] | None/minor
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
No comment | Kim Ankeraa |  |  |  |  | 1
Service | [5 empty] | None/minor
Problem description | Responsible | Due date | Date completed | Risk potential 1) | Additional costs in € | Milestone assessment 2)
No comment | Henning Boll |  |  |  |  | 1
1)e.g.: Time to Market delay; Returnrate rise; Additional R&D effort
2): Milestone assessment: Issues are ranked as follows:
prohibitive | M | Milestone declaration not signed by CCQ.Milestone declaration blocked.State of emergency.Most strictly follow up.
major (2) | K | Major deviation according to conformance assesment of CCQ
none (1) | J | Milestone declaration recommended or at least possible.Action items in case of deviation to be tracked by SPM.
The Conformance Assessment will be issued by the responsible Quality Project Manager (QM Product Lifecycle). It is binding to the project team.
The final Round Table meeting in the project team has to take place one week prior to envisaged Milestone declaration at the latest.
The Product Generation Manager (PGM) or the PM / ODM Board members can overrule the milestone decision due to strategic reasons. In this case the decision maker takes all responsibility undivided. The decision maker has the responsibility to inform the MP Board on the decision.