## Release_Notice
SW Releae Reuqest
A. Basic Information:
Project | Macc1a
Date(YYYY/MM/DD) | 2006-09-22
Initiator/Department | Jimmy Lin
Release Purpose | 2L: For Slovenia local PM approval, 10: For SmarTone 3rd test, 00: For CHT 2nd test, 2P: Backup for Greece local PM approval
Expect Release Date | 2006/9/25 (Please build on 2006/9/24 18:00)
Last Version | 1.09
Current Version | 1.10
PLMN Table Version
Product Information
Product Type: | Project ID | Hardware Version | Customer ID | For Factory Use | *#300# Info. | Comment | Comment | SyncQ Version | Memory Size (K) | Code Size (K)
|  | 5 | 2L | N | Normal version |  | For Slovenia local PM approval
|  | 5 | 10 | N | Normal version |  | For SmarTone 3rd test
|  | 5 | 00 | N | Normal version |  | For CHT 2nd test
|  | 5 | 2P | N | Normal version |  | Backup for Greece approval. Fix www.ego.gr crash issue
|  | Y | Changed File List
Use All Tip File from VM (Yes / No) |  |  |  | Impact to current status of All PPF files |  |  | No
|  | Service Version |  | Impact to current status of user manuals |  |  | No
Information for Factory
Download Tool Version
RD Version
B. Change List
B.1.Changed DSP Lib in Current version | Description
DSP Lib version
B.2. Solved Bugs in Current Version
Item | Description | Tracker_Number | Severity
B.3 Improment Feature | [ PHE ST OAM ][ Germany ][ Vodafone ] German DRM Details not completely german
1 | [OST][V1.06_2K]When MS displays the Messages Full Popup LSK 'Options'Overlaps from the previous screen | 4585 | 3-Moderate
2 | [CRVT V1.07][SMS] Handset cannot receive MT SMS after receiving a WAP vcard | 4591 | 1-Critical
3 | [SNT v1.08][Video Call]There's a "/" in last caller time dialog. | 4612 | 3-Moderate
4 | [FST V1.08][STK]STK msg have a strange grid | 4620 | 3-Moderate
5 | CHT: 常出現”內部應用程式錯誤，將被關閉” | 4624 | 2-Serious
6 | [MMI]Fix error when move one record from view one record | 4626 | 3-Moderate
7 | CHT: Memory leakage when enter CHT portal | 4628 | 1-Critical
8 | WAP input: Can't input space in WAP input box | 4633 | 1-Critical
9 | [MMI] STK選單文字沒有垂直置中 | 4635 | 5-Transparent
10 | Add "3G only" option | 4636 | 3-Moderate
11 | [OST][V1.09_2P]Power cut observed after removing the Pure Cable. | 4637 | 1-Critical
12 | [MMI] Java permission menu issue | 4640 | 3-Moderate
C. Testing Requirement
Test Report Location
| Test Item | Sub Item | Test Time | Required (Y/N) | Test Report |  | Comment
MMI | CR |  |  | Y
| Sanity Test |  |  | Y
L1 | Manufacture Process Validation | Tool Version Control | 0.5 day | N
Station Verification
| Unit Validation | RF Timing Test | 1 day | N
LCD Test
Charging Test
Accessory Test
Melody Test
Flash Test
Combination Test
BB | Charge Function (Normal condition) |  | 3 hr | N |  |  | *#301#, Add contrast item on *#402#
| Power Consumption (Real network) |  | 1 day | N
| Ear Phone Jack (Hansfree & DSC) |  | 10 min | N
| Acoustic performance |  | 15 min | N
RF | Calibration | AFC | 1 min | N
AGC
APC
| GSM | Call 112 Test | Full ch; Full PCLS; 2 min and 10 sec | N
Output Power
ORFS
PVT
Frequency Error
Phase Error
BER
| GPRS | Attaching | 40 sec | N
GPRS Class
Output Power
ORFS
PVT
Frequency Error
Phase Error
BLER
| Calibration Tool Test | Loop Test (20 Loops) | 14 min | N
| Factory Tool Test GSM_Test_XXXXXX | Loop Test (20 Loops) | 44 min | N
| Factory Tool Test GPRS_Test_XXXXXX | Loop Test (20 Loops) | 20 min | N
System | Standard ETSI Test Case | GSM | 2 day | N
|  | GPRS | 4 day | N
| Cell-Reselection |  |  | N

## Changed Item Test
Test Case Location: | \\gsm-server\Public\Document\Changed_Item_Test_MMI
Test Item | Sub Item | Required (Y/N)
Call Control | Voice Mode
Multiple Call
Active call SMS
Active SMS-CB
Identification
Auto Redial
MPTY
Call Waiting
DTMF
International Access
Ative call option Messages
Active Call Option | Active call -STK Menu
Active call Mute
Active call Send Tone
Active call Conferences
Active call --Phone Book
Active call -- Call List
WAP | MMI -WAP
WAP Setting
GPRS WAP Service
Operator Service | MMI-STK
STK
Tools | Stopwatch
Calculator
Game
Calendar
World Clock
Set Alarm
Setting | GPRS Setting
Browser Setting/WAP Setting
Time And Data/Clock Setting
Hour Minder
Power On/Off
Phone Setting | Back Light & Back Light Color
Back Light Level & Screen Contrast
Color Design
LED Indicator
Active Flip
Screen Saver
Animation
Wallpaper
Input Mode | Input Mode
GPRS Data Service | GPRS Data Transfer Service
SS | FAX & DATA
Call Forwarding
Call Barring
USSD
Call Divert | Call Divert-CFU
Call Divert-CFB
Call Divert-CFNRy
Call Divert-CFNRc
Call Divert-All Conditional
Call Divert-Divert Voice
Call Divert-Divert Data
Call Divert-Diverrt Fax
Call Divert-Cancel All
Call Communication Setting
Active Line
Call Barring | Call Barring-BAOC
Call Barring-BOIC
Call Barring-BOIC-EXHC
Call Barring-BAIC
Call Barring-BAIC-When Roaming
Call Barring-Cancel All and Change Code
Network Setting | Network/Network Option
PLMN Selection
Security Setting | PIN/PIN2/SIM Lock/Fixed Dial / (Network Lock Code)
MEP Lock
Phone releate setting | Quick Access
Language
Menu Style
Other Info
Restore
Auto Time Zone
Profile / Select Profile & Edit Profile
Melody / Melody Composer
Phone Book | Call List
Call Count Meters
View Names*
Find Record / Search
Add Record / Add Name
Add Entry To Phone
Add Entry To SIM
Flash Dial / Speed Dial
Call Group
Copy Record
Memory Status And Memory Assign / Used Space
Save nos. to (Reference 14-6-10)
Owner Number
Black/White list
Message | Message Box (In / Out) / Incoming Message
Outgoing Message (Reference 14-7-1)
Create Message (New message / Template)
Quick Message (Reference 14-7-3)
Ring Message
Melody Message
Animation Message
Picture Message
Icon Message
Create EMS
Chat Room / SMS Chat
Message Setting
Message Delete All
Voice Mail
BroadCast Setting
Operator Client | Download Animation
Download Picture
Download Screensaver
Flip/Sub-Window | Flip
Sub-Window
VAS AP | JAVA
MMS
E-mail
SyncML
DSC related | DSC test
Album
Key Access | Hot Key
Key Lock
Display Frame
No SIM Card
Battery & Charging Mode
Engineering Mode

## Changed File List
Based on :
Author | File | Rev. | CR No. | Reason | Note